## Matrix
Source or Program | Strategy | Specific Actions | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost | Reporting Year or Plan Year | Activity (Reporting) Summary 2018-2019
I. Implement TMDL Program using existing programs and updating or creating programs as needed. | A. Use existing programs and available resources to implement programs. | 1. Develop an inventory or schedule of anticipated TMDL related activity being conducted by the City including department responsibilities. | 1. Draft List by November 1st, revised list in March, final updated for annual report. | City Staff - Public Works, Parks, Planning, and Engineering. | Annually | The schedule of annual regional activities was reviewed and updated for 2018-2019. Additional meetings, tasks, and deliverables were added (and completed). The schedule is included as a separate tab in the full matrix. Copies of the one page report and full version with the tabs is available on the Grants Pass TMDL webpage located on the RVCOG website (http://rvcog.org/grants-pass-tmdl/).
|  | 2. Work with the Josephine SWCD, RVCOG, Grants Pass Irrigation District, OSU Extension, the Rogue River Watershed Council, the Rogue Basin Partnership, Middle Rogue Steelheaders Assoc, RCC and/or local schools to implement and promote TMDL programs. | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Annually | The City and the Regional Coordinator (RC) worked with North Valley High School, Hidden Valley High School, Parkdale Elementary School, Grants Pass Irrigation District (GPID), the Stream Smart program, the Rogue Basin Partnership (RBP), CWMA's, other municipalities, the Bear Creek MS4s, agencies, the Rogue River Watershed Council (RRWC), and other groups to implement and promote the TMDL program. Specific activities are documented in the matrix and in the tabs (E.g., Activity Summary). Tab I.A.2 contains a list of groups that can help with TMDL programs (and other needs). The list is reviewed and updated annually.
|  | 3. Identify resources available for program (e.g. staff hours, available funds, etc.) and program needs (gaps). | 3. Summary of available resources and needs. | Public Works Staff, Engineering and Planning Staff | Annually | The City contracts with RVCOG annually for coordination and implementation services ($15,000.00). The contract has been adjusted to coincide with the TMDL implementation Year so the period runs from July 1st through June 30th. The scope of services provided in the RC contract detail is $22,545.00 which included a portion for the previous year and $15,000 for 2018-2019 implementation. City Staff continues to contribute an estimated 100 hours to the TMDL program for meetings, implementation actions including maintaining doggie bag stations, implementing stormwater programs, managing invasive species, planting natives, working with volunteers and schools, reporting, networking with other groups, participating in Stream Smart, and other activities. Other resources include staff of the RRWC, ODFW, RBP, and other programs (e.g., Stream Smart). In addition, the City partners on funding opportunities for program implementation in conjunction with the RC. Funding for implementation includes $5,000.00 from the Meyer Memorial Trust for a restoration project managing invasives species (knotweed), planting native species along the Rogue River, educational activities, and working with volunteers. In addition, the City is a Salmon Watch Partner and helped leverage the $9,340 received from the Gray Family Foundation. A funding summary is provided in the funding tab. Program needs include additional funding for invasive species managemen and riparian restoration.
|  | 4. Review existing code and ordinances to evaluate the status of other TMDL related concerns from DEQ's Key Strategies for Rogue River Implementation that are not addressed in other matrix sections including Floodway/Floodplains and wetlands. | 4. Summary of existing code sections and potential changes or additions that may be needed. | Public Works Staff, Engineering and Planning Staff | Year 1, Review annually | The ordinances are reviewed annually. The ordinances_stormwater tab has a list of the existing ordinances relevant activity, and references to the relevant sections of the TMDL Matrix. The City worked through a public process to increase the level of riparian buffer protection in new urban growth area expansion and is using this process to work to revise and/or replace their riparian ordinance (see II.D.1.1, and II.D.2.2). No major developments or changes have occurred this year.
|  | 5. Review existing code and enforcement procedures to evaluate adequacy to address riparian and wetland issues and other TMDL related concerns. | 5. Summary of existing code and identify sections that may need to be revised and/or updated. | Public Works Staff, Engineering and Planning Staff | Year 1, Year 5, Review annually | To be completed with updated riparian ordinance revisions. Anticipated activity includes a review of code enforcement procedures and resources, recommendations on potential revisions to the enforcement procedure, and identification of resource needs. If changes are needed, a schedule will be developed for updating and implementing the enforcement procedures. No activity has occurred this year other than a review of the anticipated activity beginning in Year 5.
| B. Update codes, ordinance, and other programs (e.g. incentives) as needed to assist in program implementation. | 1. Develop an schedule of anticipated TMDL needs including code and ordinance revision and other activities. | 1. Summary included in annual report/matrix. | City Staff - Public Works, Parks, Planning, and Engineering. | Year 2-3 Year 5 | A schedule is anticipated to be completed in Year 5.
|  | 2. Modify matrix with proposed schedule for revisions and other activities. Potential activities may include revising/updating/creating floodway and floodplain protection, wetland protection, and incentives for riparian protection | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Years 3-4 | Suggested modifications appear in the notes column or in the reporting year or plan year in red and selected replacements are made using the strikethrough feature. This task is reviewed annually as part of the adaptive management plan component of the matrix. The review was completed in 2018-2019.
II. Solar Radiation – Near-Stream vegetation disturbance/ removal. Increase effective shade through restoration and protection. | A. Continue to identify and inventory new areas to restore, plant, and protect by reviewing and updating maps, lists, and/or other materials as needed. | 1. Continue to use open space, public lands, wetlands and parks inventories, watershed assessments, local knowledge, and GIS maps to identify areas. | 1. Updated maps, lists, and/or other materials. Shape files will be created for identified areas. Shape file attributes will be updated as sites are prioritized, invasives are removed, and/or the sites are planted. | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually | Sites identified are added annually to the prioritized sites lists and highlighted in yellow to distinguish them since the last report. In addition, the scoring matrix is adjusted to include any new information and maps are updated. Areas identified this year included four small areas of knotweed located in Reinhart Park that are currently being managed and will be replanted when the knotweed is controlled (3-5 year estimated timeline from invasive species control through planting of native species). In 2019-2020, the RC is creating an ArcGIS Online map with a survey (using Survey 1-2-3) in partnership with the Bear Creek DMAs to collect data on all existing and planned projects along local creeks and rivers by all participating partners. The survey is being designed with a few simple questions to allow the region to catalogue and map all known restoration sites. The online map is anticipated to be finished in the 2019-2020 implementation year. Funding provided through the TMDL program allows the RC to integrate the work of the two TMDL programs.
| B. Prioritize any newly identify areas. | 1. Use established criteria to prioritize identified sites. | 1. Updated summary/list of prioritized sites as needed. | City Staff - Public Works, Parks, Planning, and Engineering, RVCOG, other partners. | Annually | The established prioritization criteria including the scoring metric is included in the prioritization tab. Any new sites scores are on the sites identified tab and highlighted in yellow. In addition, locations of pollinator gardens are being considered and location identified will be added to the map where the coincide with riparian areas. The restoration site in Reinhart Park was added and prioritized this year.
|  | 2. Field check prioritized areas to verify needs for implementation. | 2. Summary of field checks completed | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually | No field checks were completed this year by the RC. A visit to Reinhart Park site is scheduled for early in the 2019-2020 implementation year.
| C. Restore, protect, and plant areas. | 1. Seek opportunities to plant native trees and shrubs in public areas, open spaces, city parks and along streams and rivers. Specific creeks to evaluate include Gilbert Cr., Skunk Cr., Mill Cr., Grouse Cr., Jones Cr., Sand Cr. and the Rogue River along City Park property. | 1. List of areas planted including numbers of trees and shrubs. In addition, create shape files of areas planted. | Public Works Staff, Parks Staff, Public Contracts, Volunteers, County work crews, RVCOG, Partners | Annually | The RC and the City worked with the RRWC, RBP, local schools (Grants Pass High School, Parkside Elementary, RCC, and others) to identify planting opportunities. In 2018-2019, the RC and the City worked to develop a long term project in Reinhart Park with Parkside Elementary or other schools to assist in managing weeds, planting along the Rogue River, and other activities. City crews and contracted labor groups (such as the Josephine County Work Crews), when pruning or cutting along any waterway, continue to protect all vegetation shading the streams or waterways. Tall grass buffers are maintained during the summer season when there is no other streamside vegetation. No planting projects were completed by the RC during the implementation year.
|  | 2. Identify partnering opportunities, for public and private lands, during each plan year by contacting local groups (the Rogue Basin Partnership, Rogue River Watershed Council, Middle Rogue Steelheaders, Roe Motors, Josephine SWCD, Josephine County Public Works, local volunteer groups and schools) and summarizing project opportunities. | 2. Summary of opportunities available. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC and the City worked with the RRWC, RBP, local schools (Grants Pass High School, RCC, and others to identify planting opportunities. Local groups were contacted in person, at events (Land Steward Workshop, August Institute), through programs (Salmon Watch, Stream Smart), through mailings, emails, and at meetings. In addition, the RC served on RBP's riparian working group which focuses on restoration needs (including implementation of projects) in the Rogue Basin. Members of the working group include groups working in restoration in Grants Pass (the Freshwater Trust, Rogue River Watershed Council), and others (Lomakatsi).
|  | 3. Work with local groups to schedule and complete projects annually as time and funding permit. | 3. Summary of projects scheduled and completed including number and locations of trees and shrubs planted. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | No planting projects were completed during the implementation year by the RC.
|  | 4. Evaluate funding options for restoring, planting, and protecting priority sites and pursue finding options as time and resources permit. | 4. Summary of funding sources identified, applications submitted, and funding received. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC worked with the City and RBP to secure $5,000.00 from Meyer Memorial Trust for the project at Reinhart Park for invasive species management and restoration. The RC continues to work as part of the Rogue Basin Partnership to implement the Rogue Basin Action Plan. Primary funding for restoration is through grants, member organizations including the Freshwater Trust and Rogue River Watershed Council, and volunteer efforts. The City will continue to work with the RC and other groups to submit proposals to OWEB and other programs to fund restoration work.
| D. Riparian Ordinance –Evaluate, strengthen, or develop riparian ordinances as needed (Goal 5) to protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under the City of Grants Pass jurisdiction. | 1. Draft new ordinances or revise ordinance as needed based on recommendations from earlier TMDL reports and/or other programs. | 1. Completed draft ordinance. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations. | The revised General Permit conditions were released by DEQ in November 2018. Under the permit, the City needs to have a program implemented including any ordinance revision completed by September 1st, 2023. While not a specific requirement under the MS4 program, the City has been moving forward with the revision process for the ordinance. The City will continue the process and tie them into the Stormwater Program updates as needed/appropriate. The City and RC reviewed existing ordinances region wide and statewide to identify potential models to use. The models are being used to update and/or replace existing ordinances. In Year 5, the City is planning to develop a recommended riparian ordinance revision or a revised ordinance through a public process. With the Urban Growth Boundary expansion, the buffer zones in the new properties were enhanced to meet our current code. This resulted in larger setbacks from the existing county ordinances and enhanced protection of new riparian areas.
|  | 2. Public notice of new or revised ordinances and Grants Pass review procedure. | 2. Summary of noticing and procedures used to move the ordinance towards adoption. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations. | No noticing or meetings occured. In Year 5, the City is planning to develop a recommended riparian ordinance revision or a revised ordinance through a public process. With the Urban Growth Boundary expansion, the buffer zones in the new properties were enhanced to meet our current code. This resulted in larger setbacks from the existing county ordinances and enhanced protection of new riparian areas.
|  | 3. Adopt new ordinances or revised ordinances as needed. | 3. Adopted ordinances or ordinance revisions. | Public Works, Planning and Engineering Staff, Public Safety and Code Enforcement | Pending, based on new Phase II regulations. | To be completed in Year 5.
III. Solar Radiation –Near stream vegetation disturbance - overrun by invasive species. | A. Continue to implement invasive species management programs in public areas. | 1. Manage invasive species in parks and other City owned properties. | 1. Summary of acres of invasive areas treated. | Public Works Staff, Engineering, Planning Staff, Volunteers, Partners. | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event was held at Whitehors Park Ramp in May. Attendees and volunteers included local scouts, RBP, community volunteers. City staff and/or contractors also maintains invasives on all City Parks and properties. We also have utilized the Josephine County Correctional crews to clear invasive blackberries from tributaries throughout the City as the need arises. We estimate that we have cleared 5 acres of blackberries this year.
|  | 2. Train staff on noxious/invasive weeds including identification and treatment options. | 2. Summary of any training conducted, promoted, or that staff was sent to. | City Staff | Annually | Drainage crews have completed internal trainings on noxious/invasive weeds (most notably blackberries) and have been trained on treatment options.
|  | 3 Work with watershed groups to manage invasive species on private land and protect and/or plant native species in riparian areas where invasives are removed. | 3. Number of trees and shrubs planted annually. Number of acres of invasives removed. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, the Freshwater Trust, and others to promote weed related projects including the Annual Weed Pull (Let’s Pull Together), the Weed Wrangle, and on the ground removal projects..
|  | 4. Coordinate invasive weed management activities with the County Weed Management Area. | 4. Activity Summary. | Public Works Staff, Parks Staff, Josephine County Public Works, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC coordinates with the CWMAs (currently coordinated by RBP) regarding activities in both Counties and the City of Grants Pass. The RC is on the CWMA list serve, periodically attends meetings, promotes events, and participates in selected activities. In addition, worked with the CWMA, Josephine County, Grants Pass, and others to promote the Annual Weed Pull (Let’s Pull Together). Participated in discussions with the CWMA, coordinated activities when appropriate, and attended the weed pull.
IV. Other Anthropogenic Sources: Urban Runoff – Reduce runoff, promote infiltration and low impact development practices. | A. Promote the use of methods and practices that reduce urban runoff and impervious surface area. | 1. Create or update map locations where low impact development practices are being used or will be used to reduce urban runoff and creation of impervious surface area. | 1. Map of Locations. | Public Works Staff, Planning and Engineering Staff | Annually | The City and RC are working on documenting where locations are using Google Earth and GIS. A link to the map will be placed on the City's TMDL page located on the RVCOG website (http://rvcog.org/grants-pass-tmdl/). The City also has a map showing impervious areas within the City that will be used to identify locations of and/or locations needing low impact development practices.
|  | 2. Work with the development of the stormwater program (V) to revise codes and ordinances revision to incorporate low impact development practices. | 2. Summary of revised code. | Public Works, Planning and Engineering Staff | Annually - summary after NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City of Grants Pass continues to review our draft Stormwater Management Manual to make sure it meets the needs of the stormwater requirements under the DEQ General Permit. This Manual is a LID document that will require water quality and retention control on new developments. We plan to get this adopted into our City Codes in 2019/2020.
|  | 3. Require new construction to minimize impervious surface and treat stormwater onsite using LID techniques or other appropriate methods. | 3. Summary of requirements. | Public Works, Planning and Engineering Staff | Incorporate in V. | The City of Grants Pass continues to review our draft Stormwater Management Manual to make sure it meets the needs of the stormwater requirements under the DEQ General Permit. This Manual is a LID document that will require water quality and retention control on new developments. We plan to get this adopted into our City Codes in 2019/2020.
V. Other Anthropogenic Sources: Urban Runoff – Stormwater Management Program. | A. Develop a stormwater management program addressing the six elements of Phase II Stormwater Management. | 1. Outline existing programs that meet each of the six minimum control measures for NPDES Phase II Stormwater Management. | 1. Existing program summary. | Public Works, Planning and Engineering Staff | Year 1 | A stormwater management program to meet the conditions of the DEQ General Permit is under development. The City has until September 2023 to implement the program and we are using the regional guidance document as a template. The City participated in meetings to develop the document and also provided review and input to the recommended strategies. The document can be found online at http://rvcog.org/wp-content/uploads/2017/01/SWMP-Draft-June-28th-2019.pdf. The City will use this document to assist in refining items V.1 - V.6. Recommendations are anticipated to be included (or referenced) in future iterations of the TMDL Implementation plans. Current ongoing activities that contribute to meeting stormwater requirements include: participation in the Regional Stormwater Advisory Team (City and RC), providing support to the Stream Smart Program including participating in the Advisory Team, supporting the Salmon Watch Program, and events (e.g., the Land Steward Workshop). In addition, the Ordinances_Stormwater Sections tab summarizes elements of City codes and ordinances and matrix sections that will contribute to the development of the stormwater program.
|  | 2. Identify gaps, needs, and next steps needed to develop program. | 2. Summary of gaps and next steps. | Public Works, Planning and Engineering Staff | Year 2 | A stormwater management program to meet the conditions of the DEQ General Permit is under development. The City has until September 2023 to implement the program and we are using the regional guidance document as a template. The City participated in meetings to develop the document and also provided review and input to the recommended strategies. The document can be found online at http://rvcog.org/wp-content/uploads/2017/01/SWMP-Draft-June-28th-2019.pdf. The City will use this document to assist in refining items V.1 - V.6. Recommendations are anticipated to be included (or referenced) in future iterations of the TMDL Implementation plans.
|  | 3. Develop or adopt a Storm and Surface Water standards manual | 3. Draft manual (year 4) and completed manual (year 5) | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. Beginning in Year 5, continuing in new 5-year cycle. | The City is currently developing a stand alone City of Grants Pass Stormwater Management Manual and have recently received the draft manual for review. Staff is reviewing the draft manual and sending comments back to the consulting engineer while soliciting comments from local development engineers. Additional review and updatind is needed to consider the recommendations outlined in the General Permit. Manual to be completed and adopted in 2020.
|  | 4. Develop a Pollution Prevention/Good Housekeeping Program | 4. Summary of Program | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. Beginning in Year 5, continuing in new 5-year cycle. | The City and RC are reviewing the Ecobiz program, specifically the certification of shops and fleets to evaluate the applicability in the City for meeting Good Housekeeping needs. The City is requesting moving the work plan for completing this task to years 5/6. Work plan: - the City will inventory existing work practices and procedures being done and compile a list in the annual report starting in Year 5. In Years 5-6, the City will review model programs and evaluate revisions/improvements needed to the existing programs and report on activity. In Year 5-6, the City will develop a pollution prevention/good housekeeping program.
|  | 5. Develop and implement an erosion prevention and sediment control program. | 5. Summary of programs and procedures. | Public Works Staff, Planning and Engineering Staff | Year 1 | All proposed or planned developments within the City of Grants Pass, including the Urban Growth Boundary, are required to submit a detailed "Erosion and Sediment Control Plan" to the city before any construction begins. Plans are review and inspections completed before and during the length of the project. Inspectors have taken trainings in Erosion Control and Prevention provided by RVSS and other APWA Conferences. These practices will also be detailed in the Stormwater Management Manual and enforceable pending adoption. The City has used the Nuisance ordinance (5.12.020) to regulate construction/development sites.
|  | 6. Provide incentives to developers and homeowners to install or retrofit landscapes and to provide on-site stormwater treatment and detention. | 6. Summary of incentives | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City has started reviewing incentive programs and is considering a cash incentive for storage and treatment of stormwater onsite in conjunction with the adoption of a stormwater utility. In Year 5, the City will develop a list of projected incentives to provide on-site stormwater treatment and detention. In year 5, the City's Stormwater Management Manual, once adopted will incorporate incentives into codes and ordinances for proper onsite management of stormwater.
|  | 7. Revise and update maintenance program for existing stormwater management structures or features. | 7. Revise and update training and education programs for maintenance and a schedule for inspection and maintenance as needed. | Public Works, Planning and Engineering Staff | Annually | Planning has begun for a comprehensive maintenance plan for stormwater infrastructure. The timeline is being adjusted based on the timelines established by the DEQ general permit.
VI. Fecal Sources: Animal waste management – pet, wildlife, and livestock waste. Properly manage animal waste. | A. Provide bags for dog owners to pick up pet waste. | 1. Update inventory of parks / public areas that have pet waste disposal dispensers. | 1. List of parks and public areas with pet waste disposal dispensers | Public Works and Parks Staff | Annually | There are 24 pet waste dispensers in the City.
|  | 2. Identify additional areas where bag dispensers are scheduled to be or have been placed since the previous inventory. | 2. Document number of bags provided and number and location of new bag dispensers in annual report. | Public Works and Parks Staff | Annually | Approximately 100,000 bags were used this year which is consistent with last year.
| B. Develop partnerships with SWCDs, ODA, and other groups to work on animal waste management programs in agricultural areas. | 1. Summary of any programs identified addressing animal waste management with landowners, agriculture, ODA, IDs, County programs, and other groups. | 1. Summary of programs | Public Works and Parks Staff | Annually | Programs identified include the Inland Rogue Water Quality Management Plan, local agencies (ODA, SWCDs, OSU Extension) and the Stream Smart Program (http://www.stream-smart.com/making-bear-creek-better/agriculture-and-forestry/). Funding provide by the City supports the Stream Smart Program which has some information on animal waste management programs and contacts. In addition, the Stream Smart Program, RC, and the City support and help advertise relevant classes, workshops, events, and programs.
|  | 2. Partner with local groups to encourage proper manure, upland irrigation and nutrient management. | 2. Summary of partnerships. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | Continued to work with ODA regarding resources and recommendations that they have for meeting this task. They recommended working with local SWCD’s and implementing the Inland Rogue Water Quality Management Plan. Referred question to agencies (ODA, SWCDs, OSU Extension) and the Stream Smart Website for more information (http://www.stream-smart.com/making-bear-creek-better/agriculture-and-forestry/).
VII. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | A. Establish and/or refine illegal dumping/illicit discharge detection and elimination (IDDE) program. | 1. Create, adopt, or revise and strengthen IDDE program as needed. The development of program with element V. Development of a Stormwater Management Program. | 1. Summary of IDDE program. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. Beginning in Year 5, continuing in new 5-year cycle. | The City is developing a stormwater management program to meet the conditions of the DEQ General Permit. The City has until September 2023 to implement the program. A Guidance document for developing SWMPs that the City participated in developing can be found at http://rvcog.org/wp-content/uploads/2017/01/SWMP-Draft-June-28th-2019.pdf. Recommendations are anticipated to be included (or referenced) in future iterations of the TMDL Implementation plans. The City has used it's Nuisance Authority (5.12.020) for water quality violations including excessive erosion that has come from development sites into storm drains. The City is currently evaluating the use of the Authority for illicit discharges.
|  | 2. Implement IDDE program | 2. Program implementation summary. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. Beginning in Year 5, continuing in new 5-year cycle. | Anticipated starting in Year 5 based on completion of VII.A.1.1.
|  | 3. Create, update, or refine storm drain system map for the City. | 3. A summary of the existing status of the storm drainage system mapping including what format it's in, any updates, and if not completed, a general strategy for completing the mapping. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. Beginning in Year 5, continuing in new 5-year cycle. | The City's Stormwater Master Plan has been completed and adopted by the City Council. The plan includes maps of the drainage system. GIS map are updated on an ongoing basis as discrepancies are located by field staff or as new structures are installed.
|  | 4. Evaluate the use of stormwater system maps to assist in identifying illegal dumping and sources of bacteria. Revise and/or create maps or use existing maps. | 4. Map identified areas of high bacteria. | Public Works, Engineering and Planning Staff. | Completed after VII.A.3 is completed. | Completed following VII.A.3.3
|  | 5. Track any IDDE concerns reported in the City. | 5. Summaries of any concerns identified, tracked, and/or reported. | Public Works, Engineering and Planning Staff. RVCOG, DEQ, other partners. | Annually | The RC documents calls regarding regional water quality including IDDE and septic systems. Any calls documented are included on the Activity Summary tab. No calls were documented this year for septic concerns.
|  | 6. Enforce illegal dumping as identified or found. | 6. Description of enforcement including number of contacts made, warnings issue and fines levied. | Public Works (Drainage and Utilities) and Engineering Staff and Public Safety. | Annually | The City responds to complaints as reported. In the reporting period, the City responded to two calls on Fruitdale and Jones Creek. The complaints were refered to DEQ and the State Police.
VIII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | A. Notify DEQ of failing systems when found. | 1. The City of Grants Pass will notify DEQ of failing systems when found. | 1. Summarized referrals. | Public Works (Drainage and Utilities) and Engineering Staff. RVCOG. | Annually | The RC documents calls regarding regional water quality including IDDE and septic systems. Any calls documented are included on the Activity Summary tab. No calls were documented this year for septic concerns.
IX. Outreach and Education | A. Continue to implement outreach strategy that addresses water quality parameters in the TMDL. | 1. Review materials (e.g., brochures, activities, web sites) from educational programs. | 1. Summary of review in annual report including examples of materials and/or links. | Public Works and Engineering Staff, RVCOG | Annually | The RC reviews and updates materials from educational programs annually. New materials are incorporated into the Stream Smart website, TMDL websites, hands on displays, posters, and other materials. Examples of materials are in the Stream Smart Tab and include posters used at the August Institute and a Pollinator Poster for use with pollinator gardens along streams and rivers.
|  | 2. Adopt, customize, and/or develop regional materials from programs reviewed. | 2. Copies of information created, customized, and/or distributed. | Public Works and Engineering Staff, RVCOG | Annually | The City is participating in and a partner in the Stream Smart Program. The program provides regional messaging on a number of topics throughout the Rogue Basin and a pledge campaign to encourage behavior change to help improve and protect water quality. A pledge for responsible pesticide use from the Pesticide Stewardship Partnership (PSP) was added this year. Program post cards are being printed and will be distributed in 2019-2020. Activities related to water and pollution were collected from Protecting Our Water Resources: Student Activities in the Classroom for use in events and from https://learning-center.homesciencetools.com/article/water-pollution-demonstration/. One activity is included in the Events and Activity Photos tab and the other can be accessed from the web link. In addition, the Stream Smart website was used to promote programs, events, workshops, and other programs.
|  | 3. Promote local and/or regional success stories as applicable by preparing information for summary on websites and contacting media outlets. | 3. Summary of information on regional projects. | Public Works and Engineering Staff, RVCOG | Annually | Regional success stories are promoted in the media, at meetings, at events, posted on websites including the Stream Smart main page, posts on the Stream Smart Facebook site, RVCOG's, Jefferson Public Radio, the Grants Pass TMDL site, and other websites.
|  | 4. Participate in regional education opportunities with other groups and DMAs in the Rogue Basin. | 4. List of activities. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City through the activities of the RC participates in several regional education efforts annually. Specific examples include the annual Living on Your Land Steward Workshop held at Rogue Community College in Grants Pass for Josephine and Jackson County Residents, participation in the Salmon Watch program, participation in the World Fish Migration Day, RCC Earth Day at the Redwood Campus, Rogue Valley Earth Day, and the Stream Smart program. Details regarding attendance, event summaries, and other deliverables can be found in the Activity Summary Tab.
| B. Hold, participate in, and/or promote annual water quality events. | 1. Update list of annual events related to water quality, riparian planting, the benefits of healthy riparian areas, native plants and other TMDL topics. | 1. Event list or summary of events in annual report. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The annual event list is reviewed annually, and events the RC is attending are added to the implementation schedule. In additional, annual events that the City supports are promoted by advertising at meetings, through emails, personal contacts, and through posting events on the Stream Smart, Rogue Basin Partnership, and/or RVCOG event calendars.
| C. Provide citizens, landowners and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. Revise and update list of local agencies, nurseries, and other resources for planting as needed. | 1. Summary of updates and/or updated list of resources including contact information and location. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | The resource list in tab I.A.2 was revised and updated.
|  | 2. Distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | Materials distributed included the Taking Care of Streams in Josephine County, Stream and Wetland Enhancement Guide, Garden Smart Oregon: a guide to non-invasive plants, Rogue Valley Native Plant and Seed Sources, Trees and Shrubs for Attracting Pollinators, Garden-Worthy Native Trees and Shrubs, and the Native Plant Pledge in English and Spanish. Materials were distributed at the City, at meetings, at RVCOGs front counter, and through events (e.g., Land Steward Workshop). In addition, materials are available at and residents were referred to the Stream Smart website, links on Grants Pass's TMDL website (RVCOG), and RVCOG's riparian web pages. Numbers provided are tracked in the Activity Summary Spreadsheet.
|  | 3. Coordinate partnerships with DMAs and other organizations to provide technical assistance and other resources as needed. | 3. Document technical assistance and resources provided, including the number of any plants distributed and associated planting locations. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | Partnered with other DMAs and organizations including the Land Steward Workshop and World Fish Migration Day with the Bear Creek Ms4s, the Stream Smart Program with other TMDL communities, and distributing materials in the City and online.
| D. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Continue to target areas of high animal usage including public areas near waterways and dog oriented businesses. | 1. Activity summary in annual report. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City has signs in conjunction with their dog parks and pet waste stations. In addition, the RC has referred people to information on the Stream Smart website including the Poop Pledge. Additional information in English and Spanish on the Stream Smart Program and other water quality topics including animal waste was available at events throughout the County including the Land Steward Workshop, RCC Earth Day, and World Fish Migration Day which were both held in Grants Pass. A hands-on activity identifying different stormwater pollutants including bacteria (poop) is used at most events. The activity allows us to discuss sources of bacteria from animal wastes, solutions, and resources to help.
|  | 2. Collect, develop, and/or distribute brochures, pamphlets and other materials to target areas. | 2. Documentation of materials distributed. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City has signs in conjunction with their dog parks and pet waste stations. In addition, the RC has referred people to information on the Stream Smart website including the Poop Pledge. Additional information in English and Spanish on the Stream Smart Program and other water quality topics including animal waste was available at events throughout the County including the Land Steward Workshop, RCC Earth Day, and World Fish Migration Day which were both held in Grants Pass. A hands-on activity identifying different stormwater pollutants including bacteria (poop) is used at most events. The activity allows us to discuss sources of bacteria from animal wastes, solutions, and resources to help. Deliverables are tracked in the Activity Summary spreadsheet.
| E. Provide outreach and technical assistance to private landowners and the public above the removal of invasives and weed control. | 1. Work with the Josephine County Weed Management Area (CWMA), O.S.U. Extension, and/or other groups working on weeds to provide technical assistance, educational opportunities, and/or materials on managing invasive weeds. | 1. Summary of activity with groups including any meetings attended, materials collected and distributed, contacts made, and documentation of any assistance provided. | Public Works and Engineering Staff, RVCOG, CWMA, OSU Extension, other local groups | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event at Whitehorse Park in May. Participated in discussions with the CWMA and coordinated activities when appropriate. In addition to the RC and the City referring residents to the CWMA, OSU Extension, and SWCD's, and information on noxious weed management on the City's TMDL page, the program has several brochures that provide guidance for invasive species removal (Weed Invasion Insert, Oregon Smart Garden, and BLM's "Noxious Weeds are Pretty, But..." In addition, we have a hands on activity (goat head maze) for younger participants at events which allows us to engage attendees (parents) about weeds.
|  | 2. Promote and/or support activities for the public to participate in opportunities to learn about weeds and participate in training and events related to invasive weed control. | 2. List of events promoted, supported, and/or attended by staff or a city representative (e.g., RVCOG). Potential events include the Annual Josephine County Weed Pull, and OSU's Land Steward workshops. | Public Works and Engineering Staff, RVCOG, CWMA, other local groups | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event held at Whitehorse Park in May. Participated in discussions with the CWMA and coordinated activities when appropriate.
| F Staff Training | 1. Train staff as needed on topics related to TMDL Implementation. (Include Management Staff and Elected Officials) | 1. List of how training was conducted and frequency. | Public Works, Planning, Building and Engineering Staff | Annually | A number of online webinars, local, regional, and statewide trainings were also promoted at TMDL meetings and through TMDL distribution lists by the RC, DMAs, and partners (e.g., RVSS).
X. Regional Water Quality Coordination | A. Continue participation in the TMDL program. | 1. The City of Grants Pass will continue participation in the TMDL program. | 1. Attendance (in person, phone or video conferencing if available) at quarterly meeting and other meetings as requested. | Public Works, Planning, Building and Engineering Staff | Annually | Funding provided by Grants Pass supports the coordination of quarterly TMDL Meetings including developing agendas, facilitating meetings, arranging speakers, and providing program updates. Attendance records for all meetings were submitted to DEQ and provided on the TMDL meeting attendance tab. Grants Pass attended all meetings.
XI. Funding | A. Evaluate the costs of program implementation. | 1. Establish costs of program implementation for the next plan year and identify funding sources as needed including staff time, grant funding, and other resources. | 2. List program costs and sources (e.g., staff time, direct funding, grants, etc.). | Public Works, Planning, Building and Engineering Staff | Annually | RVCOG provides the City with annual costs for continued assistance. The City has set aside approximately $15,000.00 per year for implementation assistance. The City contracts with RVCOG to provide support. Details of the specifics are in the RC Contract detail tab. In addition, implementation in the City the Streets and Drainage Superintendent (10% time), Maintenance personnel (15% of time). The City has also hired a consulting firm (Keller and Associates) to help update it's stormwater master plan. The City has also negotiated with GPID to design a plan to design a plan to work together on stormwater. The City has established a stormwater utility. Other resources included grants outlined in the funding tab.
| B. Identify program funding opportunities. | 1. Evaluate existing resources available to begin program implementation. | 1. Summary of existing resources used. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The City contracts with RVCOG annually for coordination and implementation services ($15,000.00). Additional funding has been provided through grants (Gray Family ($9,450.00) and from Meyer Memorial Trust administered by RBP ($5,000.00)). The estimated breakdown per year for grant use is in the funding tab.
|  | 2. Provide an inventory of funding, potential Regional Program grants. | 2. List of identified funding sources and deadlines provided to The City of Grants Pass and other agencies. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The RC continues to participate in Regional meetings including the Rogue Basin Partnership representing urban interests (TMDL and NPDES Stormwater Phase II). RBP works in partnership with local watershed councils Rogue River Watershed Council, NGOs, and others (Medford Water Commission, Jackson SWCD) to develop a process for prioritize restoration and other projects across the Rogue Basin. A major goal of the program is to attract outside funding from foundations and other large investors to implement regional projects. Working groups, including the riparian working group on which the RC participates, are working on packaging projects together related to TMDL including restoration and monitoring. Grant cycles including OWEB restoration are provided to region including the City.
|  | 3. Collectively (regionally) apply for funding for implementation and region-wide projects. | List of participation in regional implementation opportunities. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The RC applied to and the Grey Family foundation for Salmon Watch for the 2018 program and 2019 program. Classes are planned in for fall 2019.
|  | 4. Document any funding and/or in-kind support for projects or partner projects. | List of funding and in-kind support. | Public Works Staff, RVCOG, Local Watershed groups | Annually | Funding activity including partner support is tracked using TMDL tracking forms, program spreadsheets, and other formats. In-kind support from grants and staff time is estimated at $17,500.00. Collectively, the Salmon watch grants were over $20,000.00 with an estimated $4,000.00 supporting classes for Grant Pass Schools and/or locations. In addition, an estimated $2,500.00 of the Meyer Memorial Trust funding was spent in 2018-2019.
XII. Monitoring and Reporting | A. Use the matrix as a template to track the implementation plan. | 1. Compile information from completed activities into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually | Tracking of activities is done by the RM regularly using calendars, spreadsheets, attendance sheets, manual counters, log sheets, reports, and other methods. Additional detail is provided in reports, project summaries, online, and invoices. Details are included on separate tabs and/or in the reporting columns as needed. In addition, selected deliverables including completed matrixes are posted on the RVCOG, Grants Pass TMDL, and/or Stream Smart website.
| B. Submit annual reports to DEQ. | 1. Submit annual reports to DEQ. | 1. Completed annual reports submitted to DEQ by September 30 of each year, reporting on implementation actions for the July 1-June 30 plan year. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually, November 1st of each year. | Completed. The matrix was submitted to DEQ and a detailed report containing all supplemental pages can be accessed on the Grants Pass TMDL Homepage under RVCOG's website at http://rvcog.org/grants-pass-tmdl/.
| C. Use existing programs to track program effectiveness. | 1. Work with DEQ, RVCOG, and other DMAs to evaluate methods for evaluating and tracking program effectiveness. | 1. Summary of methods evaluation. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually | Currently, the RC tracks effectiveness through a number of metrics including: attendance at events/workshops/trainings/meetings/etc, number of website visits, number of educational materials (e.g., brochures) handed out, surveys completed, number of trees and shrubs planted, number of stream miles or acres protected, amount of invasive species managed (acres), map of project activities (completed, in progress, proposed), limited surveys, samples collected, contacts made, calls/reports received, and other methods. For example, the top 10 Stream Smart Pages received over 12,000 visits (12,320). Please see the information on the Stream Smart Web Stats Tab for the visitor breakdown and most visited pages. Other statistics are tracked in the activity summary tab. Effectiveness is measured by meeting specific deliverables/milestones and other implementation plan targets.
|  | 2. Work with DEQ, RVCOG, and other DMAs to use existing programs (DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. | 2. Summary of regional water quality. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually | The RC is participating as part of RBP's monitoring work group which is evaluating monitoring across the Rogue Basin. A long term goal of the working group is to use the data to be able to tell the story about the watershed health in the Rogue Basin including in the Grants Pass area. For water quality, one item being discussed is creating a watershed report card which will summarize water quality conditions. The report card may be able to be used to evaluate program effectiveness related to the water quality elements of the report. There are no interim results from RBP's work that are currently available to help the City evaluate effectiveness. Limited data exists to summarize water quality conditions. The Bear Creek TMDL communities applied for funding through DEQ's 319 grant program to analyze the monitoring data collected over the last 5-7 years to evaluate trends in the data and the effective of the TMDL implementation program. Work on the project is being completed in 2019-2020. Results of the analysis will be reviewed by the City for potential adaptation in future years of the TMDL Implementation program. In addition, the City and RC are evaluating the use of Story Maps and other tools to summarize water quality conditions.
| D. Adaptive Management Plan. This is an ongoing plan and modifications and adjustments will take place. | 1. Modify plans as needed. | 1. Summary of any revisions to Water Quality Implementation Plans. | Public Works, Planning, Engineering Staff, RVCOG, other DMAs. | Annually | Any changes in terms of requests for annual plan modifications is included in the reporting column. Previous requested changes were left in the columns in addition to any new requested changes. Most of the changes requested reflect the finalizing the DEQ General Permit for Stormwater (November 2018) and the anticipated timeline for program development.
Note on C27: gstabach:III.A.3 and II.A.4 were the same so I deleted one.

## Implementation Schedule
Implementation Activity | July | August | September | October | November | December | January | February | March | April | May | June
TMDL Implementation Year Begins | 1st
Quarterly TMDL Meetings
Quarterly SWAT Meetings
Quarterly Stream Smart Advisory Team Meetings
Stream Smart Support
Salmon Watch
Annual Weed Pull
Annual Reports Due |  |  |  |  | 1st
Weed Management
Riparian Planting
Irrigating/site watering
CWMA Meetings
Web Updates, Postings
Review and Update Annual Event List
Promoting events, trainings, workshops
Annual Schedule Review
Annual Resource Review (staffing, contracting, other resources)
Annual Deliverable Review
Stormwater Phase II General Permit Released
SWMP Development Recommendations includes tie ins/overlap with TMDL
RCC Earth Day
World Fish Migration Day
Rogue Valley Earth Day
Land Steward Workshop
TMDL Implementation Year Ends | [11 empty] | 30th

## Activity Summary
TMDL Related Implementation Activity and Event Summary Information
Note: The table includes selected items only related to matrix tasks. As a result, not all matrix items are reflected in the table.
Summary Information |  |  |  |  | Statistics/Tracking Variables
Date | Event/Activity | Time and Location (if needed) | Description | Activity Type | Number of People | Number of Samples Collected | Brochures and Give-aways Distributed | Acres restored and/or number of trees planted | Acres of invasives treated | Funding Leveraged
2018-08-02 | Stream Bank Riparian Monitoring Meeting and Training | 9:00 a.m - 1:00 p.m. | Attended TFT's Stream Bank Monitoring Program Training to evaluate their tool for monitoring riparian areas and restoration projects. | Solar Radiation - Restoration and Planting | 12
2018-08-02 | Salmon Watch Meeting | 2:00 pm - 3:00 p.m. | Met with RVSS to discuss the Salmon Watch program including logistics for fall of 2018. | Outreach and Education | 2
2018-08-13 | August Institute | 11:00 am - 12:30 pm | Recruited for Salmon Watch Instructors and advertised the program to teachers. Talked to potential instructors from SOU and teachers about the program. Interested instructors (4) and teachers (11) who were not already on our email lists signed up for the program. | Outreach and Education | 35 |  | 15
2018-08-17 | Jefferson Exchange Interview | 8:00 am - 11:00 am | On-air interview at the Jefferson Exchange. Program focused on the Stream Smart Program and upcoming events and activities including the Adopt A River Program, Go Blue, the Bear Creek Clean-ups, the Bear Creek Fall Festival, and Salmon Watch. Link to the interview https://www.ijpr.org/post/encouraging-bear-creek-care-stream-smart#stream/0 | Outreach and Education
2018-08-23 | RBP Monitoring Team |  | Participated in a meeting with the RBP monitoring team discussing monitoring issues, needs, and results in the Rogue Basin. | Meetings, Program Coordination | 5
2018-09-12 | Salmon Watch Instructor Training | 3:00 pm - 5:00 pm | Completed a training at Bear Creek Park with RVSS, ODFW, and other for contracted and volunteer Salmon Watch instructors in preparation for the 2018 field season. | Outreach and Education | 19
2018-09-19 | Stream Smart Advisory Committee Meeting | 9:00 a.m. to 11:00 a.m. | Quarterly meeting of the Stream Smart Advisory Committee. Agenda topics included website update needs, Go Green, and Ecobiz. | Outreach and Education, Solar Radiation - Planting, Invasive Species (GO Green), Regional Water Quality Coordination Meetings
2018-10-06 | Salmon Festival | 11:00 am - 4:00 pm | Staffed a booth at the Salmon Festival featuring information on water quality and Salmon and the Stream Smart Program. Hands on activities included the good/bad riparian habitat matching game and the goathead maze. | Outreach and Education | 225 |  | 155
2018-10-08 | Salmon Watch | 8:45 am - 2:45 pm | Class stats for the season to include in counts. Details on the Salmon Watch Program are in the Salmon Watch tab. Funding estimate includes Gray Family Foundation grant for 2018 season program. | Outreach and Education. Funding. | 1220 |  |  |  |  | 10000
2018-12-13 | RBP Board Meeting | 2:00 pm - 4:00 pm | Board meeting with RBP. | Regional Coordination
2018-12-19 | Stream Smart Advisory Committee Meeting | 9:00 am - 11:00 am | Quarterly meeting of the Stream Smart Advisory Committee. Agenda topics included a detailed discussion of website overhaul and revision needs and adding the Pesticide Pledge Program to the website. | Regional Water Quality Coordination, Outreach and Education | 7
2019-01-14 | Ecobiz Meeting | 1:00 pm - 2:30 pm | Quarterly program meeting. | Meetings, Program Coordination | 6
2019-01-26 | Salmon Watch Video and Interview | 9:00 am - 12:00 pm | Filmed the Adventures in Education Program with Rogue Valley Community Television (RVTV) featuring Salmon Watch . The program runs approximately 30 minutes and is available on RVTV's website. | Outreach and Education
2019-02-07 | RBP Board Meeting | 2:00 pm - 5:00 pm | Board meeting with RBP. | Regional Coordination
2019-02-13 | TMDL Run | 8:30 am - 5:30 pm | Monitoring Run | Monitoring |  | 46
2019-02-14 | Riparian Working Group | 9:00 am - 11:00 am | Restoration collaborative meeting to discuss riparian restoration activities including blanket permits for different areas. | Solar Radiation 1, Solar Radiation 2
2019-02-21 | BC Fall Festival Planning Meeting | 2:00 pm - 4:00 pm | Planning meeting for Fall 2019 | Outreach and Education | 6
2019-02-27 | Imagine a Day Without Water Meeting | 9:00 am - 10:30 am | Planning meeting for Fall 2019 | Outreach and Education | 8
2019-03-08 | Riparian Practioners Workshop | 8:00 am to 5:00 pm | Attended and contributed to a workshop focused on restoring streams and riparian corridors in the region by planting native plants and removing invasive species. | Training, Regional Coordination
2019-03-20 | Stream Smart Advisory Committee Meeting | 9:00 a.m. to 11:00 a.m. | Quarterly meeting of the Stream Smart Advisory Committee. Agenda topics included a detailed discussion of the role of Stream Smart including tie ins to the Phase II Stormwater Programs. | Regional Water Quality Coordination, Outreach and Education | 10
2019-04-06 | World Fish Migration Day | 10:30 am - 3:00 pm | Participated as an exhibitor for the activity fair from 10:45 to 2:45. RVCOG/Stream Smart's main activity was to identify the polluntants in jars and discuss how humans can keep pollutants out of creeks and rivers. For younger children, we had a stormwater maze to take home with them. We also had several salmonid life cycle posters, salmon brochures, Oregon trout cards, salmon tattoos, salmon enhancement pencils, and Stream Smart stickers and pledge cards that we distributed. Overall, we had 51 people stop at our booth to play our pollutant in a jar game or talk about salmon, taking pledges, getting involved in other events, or providing resources to other organizations. | Outreach and Education | 51 |  | 27
2019-04-18 | RCC Earth Day Event (Redwood) | 12:00 pm - 2:00 pm | Participated as an exhibitor from 11:30 to 2:05. A variety of information was available, including internship opportunities and Salmon Watch instructor openings. Spoke with 24 people. | Outreach and Education | 24 |  | 22
2019-04-20 | Rogue Valley Earth Day | 11:00 am - 4:00 pm | Participated as an exhibitor and provided two Eco Quest activities. Spoke to 58 people. 14 children participated in an Eco Quest activity (salmon cards and/or stormwater maze). | Outreach and Education | 58 |  | 71
2019-04-27 | Living on Your Land - Land Steward Workshop RCC Grants Pass | 7:30 a.m. to 3:30 p.m. (event time) | Participated in the annual land steward workshop. Attendees included residents and landowners from both Jackson and Josephine County including streamside landowner. Our exhibit featured information on the Stream Smart Program and Pledges, water quality, and urban runoff management. Of particular interest to attendees included riparian restoration (native plant recommendations and invasive species managemenet), the pledge programs, and how to manage runoff at home (e.g., rain gardens, rain barrels, etc.) | Outreach and Education | 83 |  | 45
2019-06-18 | Stream SmartAdvisory Committee Meeting | 9:00 am to 10:30 am | Quarterly meeting of the Stream Smart Advisory Committee. Agenda topics included a detailed discussion of website overhaul including funding needs, program goals, tasks ot achieve in 2019/2020. | Regional Water Quality Coordination, Outreach and Education | 9
Program Stats |  |  | Totals |  | 1780 | 46 | 335 | 0 | 0 | 10000
[5 empty] | Number of People | Number of Samples Collected | Brochures/Giveways | Acres restored and/or number of trees planted | Acres of invasives treated | Funding Leveraged

## I.A.2
Community Resources List Water Quality, Riparian Planting, and Restoration Projects- Grants Pass Updated June 2019
Water Quality, Planting, and Restoration Partners | Contact(s) | Contact Number | Address | Website | Email | Subject(s)
Technical Assistance, Forums, Volunteers
Josephine County
Rogue Valley Council of Governments | Greg Stabach, Craig Tuss, Amie Siedlecki | (541) 664-6674 | 155 North First Street | www.rvcog.org | gstabach@rvcog.org | Monitoring, restoration, planting designs, invasive species management, permitting, contract/contractor management, plant selection, maintenance, technical assistance, project development, grant/funding assistance, Stream Smart, Salmon Watch, educational programs.
OSU Extension (serves both Counties) |  | (541) 476-6613 | 215 Ringuette Street | http://extension.oregonstate.edu/ | Varies | Forestry, Training, Riparian Planting, Invasive Species Control, Rural Landowners
Rogue Community College Redwood Campus |  | (541) 956-7500 | 3345 Redwood Highway | http://www.roguecc.edu/ Resource Directory - http://www.roguecc.edu/AboutRCC/Contacts.asp |  | Sustainability Club, Education, Volunteers. Also has been the host of the Land Steward workshop in 2015 and 2016.
Siskiyou Field Institute | Sarah Worthington | (541) 597-8530 | P.O. Box 207/1241 Illinois River Road, Selma, OR. 97538 | http://www.thesfi.org/Page.asp?NavID=108 | youthprograms@thesfi.org | Education, Events, Trainings
Josephine County Fairgrounds | Wes Brown | (541) 476-3215 | 1451 Fairgrounds Road Grants Pass, OR. 97527 | http://www.co.josephine.or.us/Calendar.asp?SectionID=146 | wbrown@co.josephine.or.us | Varies.
Rogue Basin Partnership | Greg Weber, Sarah Sauter |  | P.O Box 1214 Medford, OR. 97501 | http://www.roguepartners.org/ | greg.weber@roguepartners.org | Regional collaborative implementing the Rogue Basin Action Plan and other projects throughout the Rogue Basin.
Oregon Stewardship | Jim Hutchins, Eric Dittmer | (541) 770-2703 | 4015 S. Stage Road Medford, OR. 97501 | http://www.oregonstewardship.org/ | jim@oregonstewardship.org | Contractor for invasive species management and riparian restoration programs. Organizations uses local students and funding is provided to the studnets via scholarships.
Jackson County Weed Management Area | Sarah Sauter, RBP | (541) 261-7099 | P.O Box 1214 Medford, OR. 97502 | sarah@roguepartners.org | info@roguepartners.org | Meetings vary. Support annual weed pull events.
Josephine County Weed Control Program | Josephine SWCD | (541) 474-6840 | 576 NE E Street Grants Pass, OR. 97526 |  | joswcd@charterinternet.com
Josephine County Weed Management Area | Sarah Sauter, RBP | (541) 261-7099 | P.O Box 1214 Medford, OR. 97501 | http://rogueweeds.info/ | thera@roguepartners.org | Meetings vary. Support annual weed pull events.
Rogue River Watershed Council | Brian Barr, Executive Director | (541) 664-1070 ext. 433 | 89 Alder Street Central Point, OR. 97502 | http://www.rogueriverwc.org/ | bbarrrrwc@gmail.com | Local Watershed Council that is the consolidation of four councils including the Stream Restoration Alliance that covers Grants Pass.
Rogue Basin Partnership | Greg Weber, RBP | (541) 690-8799 | P.O Box 1214 Medford, OR. 97501 | http://www.roguepartners.org/ | info@roguepartners.org | Regional collaborative implementing the Rogue Basin Action Plan and other projects throughout the Rogue Basin.
Lomakatsi | Niki Del Pizzo | (541) 488-0208 | 90 Van Ness Avenue, Ashland | http://www.lomakatsi.org/ | info@lomakatsi.org | Riparian Restoration, Fuels Treatment, Education, Nurseries with native plants.
Worksource Rogue Valley | Christie Lawson, Crew Field Specialist Medford and Grants Pass | (541) 621-2619 | 1569 Northeast F Street, Grants Pass, OR. 97526 | www.jobcouncil.org | christiel@jobcouncil.org | Provide labor for invasive species management and restoration projects.
Jackson County
Rogue Valley Council of Governments | Greg Stabach, Craig Tuss, Amie Siedlecki | (541) 664-6674 | 155 North First Street | www.rvcog.org | gstabach@rvcog.org | Monitoring, restoration, planting designs, invasive species management, permitting, contract/contractor management, plant selection, maintenance, technical assistance, project development, grant/funding assistance, Stream Smart, Salmon Watch, educational programs.
Bear Creek Watershed Education Partners (BCWEP) | Greg Stabach | (541)-423-1370 | P.O. Box 3275 Central Point, OR. 97502 | http://www.bcwep.org/ | bearcreekwatershed@gmail.com | Volunteers for planting and restoration, Education and Outreach. Primarily in Bear Creek, but members are willing to travel to other locations. RVCOG is the contact for the group. Former members volunteer for Salmon Watch, educational events, and other programs.
North Mountain Park | Jennifer Aguayo | (541) 488-6606 | 620 North Mountain Ave Ashland | http://www.northmountainpark.org/ | jennifer.aguayo@ashland.or.us | Varies per season. Lending Library, nature programs and workshops, stormwater features on-site, trails, riparian restoration, invasive species control, water quality, biology, native plants, gardens.
Coyote Trails Nature Center | Molly Kreuzman | (541) 772-1390 | 2931 South Pacific Highway, Medford | http://www.coyotetrails.org/index.php/ct-nature-center |  | Education programs. Riparian planting, water quality, salmonwatch, low impact development (on -site), facilities and labor/participation for workshops and programs.
Rogue Basin Partnership | Greg Weber | (541) 690-8799 | P.O Box 1214 Medford, OR. 97501 | http://www.roguepartners.org/ | info@roguepartners.org | Regional collaborative implementing the Rogue Basin Action Plan and other projects throughout the Rogue Basin.
Rogue River Watershed Council | Brian Barr, Executive Director | (541) 664-1070 ext. 433 | 89 Alder Street Central Point, OR. 97502 | http://www.rogueriverwc.org/ | bbarrrrwc@gmail.com | Local Watershed Council that is the consolidation of four councils including the Stream Restoration Alliance that covers Grants Pass.
Oregon Stewardship | Jim Hutchins, Eric Dittmer | (541) 770-2703 | 4015 S. Stage Road Medford, OR. 97501 | http://www.oregonstewardship.org/ | jim@oregonstewardship.org | Contractor for invasive species management and riparian restoration programs. Organizations uses local students and funding is provided to the studnets via scholarships.
Scienceworks |  | (541) 482-6767 | 1500 East Main Street, Ashland | http://www.scienceworksmuseum.org/ | rachel@scienceworksmuseum.org | Current location of Earth Day Celebration. Have had programs in the past addressing water quality, wetlands, and native plants including hands-on activities and speaking forums.
Southern Oregon University |  |  | Southern Oregon University, Science Hall, Ashland | http://www.sou.edu/ |  | Groundwater, GIS, GPS, monitoring, student projects.
Lomakatsi | Niki Del Pizzo | (541) 488-0208 | 90 Van Ness Avenue, Ashland | http://www.lomakatsi.org/ | info@lomakatsi.org | Riparian Restoration, Fuels Treatment, Education, Nurseries with native plants.
Worksource Rogue Valley | Multiple Contacts | (541) 776-5100 | 673 Market Street Medford, OR. 97504 | www.jobcouncil.org |  | Riparian Restoration and planting, site maintenance, labor for projects, programs should have an educational component for Job Council Participants.
Jackson Soil and Water Conservation District | Kora Mousseaux | (541) 734-3143 | 573 Parsons Drive, Medford | http://www.jswcd.org/Index.asp |  | Programs with rural homeowners and the agricultural community. Education and outreach programs. Provide implementation assistance of the Agricultural Water Quality Management Plan.
Randy White
Jackson County Community Justice | Shane Hagey, Director | (541) 774-4900 | 1101 W. Main St., Suite 101, Medford, OR. 97501 | http://www.co.jackson.or.us/Page.asp?NavID=187 | HageySL@jacksoncounty.org | Crews are available to provide service for projects. Crews have been used for site preparation, invasive species removal, and limited site planting.
OSU Extension SOREC (Southern Oregon Research and Extension Center) | Max Bennett, Rachel Werling | 541-776-7371 | 569 Hanley Road Central Point, OR 97502-1251 | http://extension.oregonstate.edu/sorec/ |  | Forestry, Training, Riparian Planting, Invasive Species Control, Rural Landowners
Plants and Seeds
Forest Farm |  | (541) 846-7269 | 990 Tetherow Road, Williams, OR. 97544 | http://www.forestfarm.com/ | plants@forestfarms.com
Plant Oregon | Dan Bish | (541) 535-3531 | 8651 Wagner Road, Talent, OR 97540 | www.plantoregon.com | dan@plantoregon.com
Shooting Star Nursery |  | (541) 840-6453 | 3223 Taylor Road, Central Point, OR 97502 | http://roguevalleynursery.com/ | info@roguevalleynursery.com | Nursery also offer classes.
Siskiyou Rare Plant Nursery |  | (541) 535-7103 | 2115 Talent Ave, Talent, OR. 97540 | http://siskiyourareplantnursery.com/index.aspx | customerservice@srpn.net
Silver Falls Seed Company |  | (503) 874-8221 | P.O. Box 8851 5648 Evans Valley Loop Silverton, OR. 975381 | www.silverfallsseed.com
Sunmark Seed Company |  | 1-888-214-7333 | 2255 NE 19th Ave Portland, OR. 97230 | www.sunmarkseeds.com
Internet Database |  |  |  | http://www.nwplants.com/information/resources/nurseries.html
Local Contacts
Other Groups

## Funding
Funding Leveraged including Grants | Matrix Item X.B.
Riparian Restoration/Planting Projects
Project | Funder | Amount requested | Awarded | Date of Award/Notice
Reinhart Park Knotwood Removal and Restoration | Meyer Memorial Trust/RBP | 5000 | Yes | 2018-05-01
Other Projects - RC as the applicant and/or project manager
Salmon Watch 2018 | Gray Family Foundation | 11415 | Yes
Salmon Watch 2019 | Gray Family Foundation | 9450 | Yes | 2019-03-04
1 Indicates a multi-year project/funding |  |  | 25865 | Funding Requested
|  |  | 25865 | Funding Received
|  |  | 11950 | 2019-2020 Funding (next year)
|  |  | 13915 | Total Funding Leveraged

## Ordinances_Stormwater Sections
Existing Stormwater and TMDL related ordinances
Most of the relevant ordinances in the Development Code are located in Article 24: Environmental Design Standards. This section includes Water Quality Regulations (24.330), Water Quality Standards (24.340), Stream Corridor Setbacks (34.341), Preservation of Riparian Vegetation (24.343), Wetlands (24.345 and 24.500), and Stormwater Detention and Retention (34.347). Article 13: Special Purpose Districts also has provisions for Slope Hazard Districts (13.100) and Sections 13.133 and 13.143 address Erosion Control for developments in Steep slope areas.
TMDL Matrix/Program Implementation (program proposed to be developed)
The TMDL implementation plan contains many sections that once completed form the framework for a stormwater management program. Relevant sections are summarized below:
Annual/Review Updates
Source | Strategy | Specific Actions | Notes | RC | City
I | A, B | All | Outlines existing resources, regulations (ordinances), and responsibilities for implementing stormwater programs in the City. It also identifies begins the review and revision procedure for ordinances and updating the matrix. | X | X
IV | A | All | Address urban runoff, ways to reduce impervious surface areas, and low impact development. Includes mapping LIDS and BMPs, revising codes and ordinances to incorporate LID's in conjunction with the development of the SW program (V) and requiring new construction to use LIDs and other appropriate management methods. | X | X
V | A | 1 through 7 | Portion of the TMDL implementation plan that address developing a stormwater management program addressing the six minimum control measures (elements). Includes pollution prevention/good housekeeping, adopting or developing a design manual, incentives for homeowners, and maintenance of features. Adaptive management may be needed to adjust the program to meet the elements of the new General Permit. | X | X
VII | A | 1 through 6 | Establishes and/or refines illicit discharge detection and elimination programs (IDDE). | X | X
IX | A, B, F | All | Outlines education and outreach programs including some public participation and involvement (events) and training of staff. | X | X
XI | A, B | All | Outlines establishing funding for program implementation which could include stormwater utilities. | X | X
XII | A,C,D | All | Outlines tracking and reporting requirements for the TMDL program which includes stormwater. Established Phase II programs have strict tracking and reporting requirement. The TMDL tracking and reporting can provide a basis for the MS4 program. | X | X

## Events, Activity Photos
Activity Photos
Salmon Watch | Fish Migration Day | New Activities
Riparian Habitat Activity used for the World Fish Migration Day

## GP TMDL webpage
http://rvcog.org/grants-pass-tmdl/

## Prioritization Criteria
Critical Factor | Explanation of Matrix critical factors: | Score |  |  | Score
|  | High | Medium | Low | High | Medium | Low | Not Applicable/No Score
Accessibility | Includes physical constraints to land: willing landowner (including agencies), physical barriers (e.g., fencing and vegetation), and accessibility (equipment, maintenance, plant deliveries, etc.). | Lots of constraints and barriers to completing the project. | Moderate constraints. | Easy access for people, equipment, and vehicles. | 1 | 2 | 3 | 0
Partner Interest | Indicated a willing partner/expressed interest in a project by landowner or agency/ organization/ school. | Willing partner, organized group that owns or has access to the site. | Willing partner. Limited access to the site. | No partners. | 3 | 2 | 1 | 0
Coordination with existing plans | Has the site been recommended for restoration - plans may include watershed assessments and action plans, parks plans, Rogue Restoration work, the WISE project, Freshwater Trust, and other groups. | Yes, as a high priority in one or more plans. | Moderately rated site in plans and assessments. | No or rated as low/limited potential. | 3 | 2 | 1 | 0
Habitat Enhancement Need | Includes both terrestrial and aquatic habitat- increase in diversity of species, erosion control, bank stability, channel undercutting, recent disturbance, large woody debris, reduction in algal growth or temperature, overstory building for shade, etc. | Site has a high need and significant potential for restoring habitat. | Site has some need and potential for restoration. | Site is in good shape. No/Limited enhancement needed. | 3 | 2 | 1 | 0
Irrigation availability | Assessment of watering needs including accessibility to an available water source for irrigation. | Site has irrigation or a water supply in close proximity. | Water is available through a limited duration water right or a supply that is located far away or requires regular site visits (e.g., watering truck or crew). | Limited or no water availability. | 3 | 2 | 1 | 0
Restrictive Site Conditions/ Limitations | Assessment of site conditions that would reduce the survival of seedlings including: soil conditions, invasives, existing uses of area and potential for vandalism. | Lots of constraints and difficult site conditions identified. |  | Limited/no constraints. | 1 | 2 | 3 | 0
Key habitat area | Includes assessment of connectivity potential to other habitat areas and T&E spp. Presence, sensitive wetland feature or adjacent to sensitive area including a cultural resource area. | Key/critical habitat. High value. | Important habitat, disturbed, moderate value. | Low value. Highly disturbed site. | 3 | 2 | 1 | 0
Flood Abatement/ Storage | Assess areas potential for flood storage and abatement. | High potential, floodplain connection, existing storage provided. | Moderate storage provided. | Low storage. Low/limited connectivity (e.g., incised, narrow channel). | 3 | 2 | 1 | 0
Site preparation | How much preparation will be needed before the site is planted (blackberry removal, soil amendments, etc) prior to plantings? | Significant preparation needed. Lots of invasives, soil amendments needed, tough site conditions. | Some preparation needed. | Minimal preparation work needed. | 1 | 2 | 3 | 0
Proximity to stream/river | Will the planting shade the stream or provide riparian protection (e.g., buffers)? | Yes. Planting of the site will result in increasing the overstory vegetation and the aspect will greatly reduce the amount of direct solar loading to the stream. |  | Planting will provide minimal shade benefits only. | 3 | 2 | 1 | 0
Fire Risk | Is area a potential fire risk? Dead trees, invasive plants, dense small diameter forest, etc. This does not include areas that were already burned. | High fire risk. Lots of invasive species, no/low water, lots of fire prone species, close to source area (e.g., I-5, Greenway). High fire occurrence history. | Moderate fire risk. | Low fire risk. | 1 | 2 | 3 | 0
Invasive species presence | Does the site have a high percentage of invasive species? | Dominated by invasive species (<50%). | 25-50% invasives. | <25 % invasives. | 1 | 2 | 3 | 0
Potential/Existing Recreational Area | Is there existing recreation at or near the site? Is there the potential to incorporate new recreation/recreational access to the site? | Yes. Existing trail or greenway. | Some. Opportunity for future connection/path. | No. | 3 | 2 | 1 | 0
Potential for adoption of site monitoring/ maintenance | Is there an established or the potential for an established entity to conduct site maintenance and monitoring? Entities could be local schools, watershed groups, watershed councils, Municipalities, the Job Council, contractors, and others. | Yes. | There are potential groups, but no agreements are in place to complete monitoring and maintenance. | No. | 3 | 2 | 1 | 0
Shading Potential/Shading Needs | Is there an identified shading need at the site? Identified need could be from a watershed survey, visual surveys, air photos, shade surveys, etc.? | High potential for shade (shade potential). | Moderate shade potential. | Low shade potential (existing | 3 | 2 | 1 | 0
Thermal Credits Available | Is there potential for thermal credits to be available for the project and funding provided by the Freshwater Trust? | Yes. |  | No. | 3 | 2 | 1 | 0
RBP Action Plan Priority Watershed | Is the planting project located in or a near an identified priority watershed in the RBP Action Plan? | Yes | Within 0.5 mile | Within 1 mile | 3 | 2 | 1 | 0
In or Near a RBP Confluence Area | Is the planting project located in or a near an identified confluence area in the RBP Action Plan? | Yes | Within 0.5 mile | Within 1 mile | 3 | 2 | 1 | 0
RBP Action Plan Priority Corridor | Is the planting project located in or a near an identified priority corridor in the RBP Action Plan? | Yes | Within 0.5 mile | Within 1 mile | 3 | 2 | 1 | 0
Other TMDL Parameters or Need Addressed | Are there other pollutants or TMDL parameters that will benefit by restoring or protecting this site? e.g., wetland function. Are there other needs addressed? E.g. education and outreach, demonstration site, BMP/LID location, etc. | Yes. |  | No. | 3 | 2 | 1 | 0
Other potential parameters to add
Aspect | Sites that will block southern exposure to afternoon sun in the summer are higher priority.
Planting plan completed? | Is there a planting plan completed for the site, so the site is essentially ready to go?
Proximity to another restoration site, planting project, or healthy riparian zone. | If there is a site nearby or adjacent that the project would connect to, the potential benefits increase resulting in a higher overall benefit for the project.
Public Land | Is the site located on public land?
Public benefit | Does the project benefit the public?
Regulatory Compliance | Does the project meet the needs of multiple regulations?
Funding | Is there funding available for the project? E.g., smaller projects may be achievable with the amounts available.
Stream/River Size | Is the flow or size of the stream greater than some set threshold? 50 feet? 200 cfs?
Other?

## Prioritized Sites
Bear Creek and Rogue Basin Riparian Planting Prioritization Matrix---DRAFT May 2012-Grants Pass Sites
Planting sites are prioritized based on a rating system of L- Low (1 point), M- Medium (2 points) and H- High (3 points). 0 points are used where criteria are not applicable. U indicates unknown. Field verification is required.
Indicates new sites added since previous report.
*For restrictive site conditions, a yes and a high rating equates to a low score(1).
**Unknown attributes are assigned a score of 0 and need to be evaluated as part of the field surveys.
Number | Planting/Restoration Site | Waterbody: See Codes Below | DMA(s): See Below | Site code | Accessibility | Partner interest | Coordination with exist. plans | Habitat enhancement need | Irrigation availability | Restrictive Site Conditions/Limitations* | Key habitat area | Flood abatement/ storage | Site preparation minimal | Proximity to stream/ wetland | Fire risk | Invasive Species presence/ potential | Potential/ existing recreational area | Potential for adoption of site monitoring/ maintenance | Shade Potential/Shading Need | Thermal Credits Available | Other TMDL Parameter Addressed | RBP Action Plan Priority Watershed | In or Near a RBP Confluence Area | Priority Corridor | Total Points | Notes
1 | Rogue River next to proposed dog park location. | RR | GP | GP-RR-DP | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 0 | 3 | 0 | 0 | 3 | 43 | Dog park is unlikely to occur anytime in the near future. Planting would be habitat building and for a buffer between the park and the Rogue River.
2 | Rogue River next to City Water Plant | RR | GP | GP-RR-WWTP | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 2 | 0 | 0 | 3 | 45 | Canopy Cover is needed for stream shading.
3 | Skunk Creek near Skate Park | O | GP | GP-SC-1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 34 | The site will be difficult to plant in most places due to fill on site, steep bands, water, invasives species, and other factors. The site needs to be subdivided into several sub sites with individual planting prescriptions for the sites.
4 | Skunk Creek Tributary near Skate Park | O | GP | GP-SCT-1 | 3 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 0 | 0 | 0 | 31 | Skunk Creek Tributary near Skate Park
5 | Skunk Creek mainstem daylighted section north of Skate Park. | O | GP | SCCK-1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 0 | 3 | 0 | 0 | 0 | 26 | Revised Skunk Creek Site identified from 2010 Riparian Planting Plan
6 | Rogue River North Bank | RR | GP | GP-RR-P-3 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 36 | Identified from aerial photos. On Private land. Field verification is needed.
7 | Rogue River North Bank | RR | GP | GP-RR-P-2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 35 | Identified from aerial photos. On Private land. Field verification is needed.
8 | Rogue River North Bank | RR | GP | GP-RR-P-1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 35 | Identified from aerial photos. On Private land. Field verification is needed.
9 | Rogue River North Bank | RR | GP | GP-2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 0 | 2 | 0 | 0 | 3 | 36 | Identified from aerial photos. Field verification is needed.
10 | Rogue River North Bank | RR | GP/JOCO | GP-1 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 41 | Identified from aerial photos. On Josephine County property. Field verification is needed.
11 | Rogue River North Bank | RR | GP | GP-RR-P-5 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 3 | 33 | Identified from aerial photos. On Private land. Field verification is needed.
12 | Rogue River South Bank at Riverside Park | RR | GP | GP-RR-RP-1 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 43 | Canopy and habitat building at Riverfront Park. Will need to be ground truthed and designed to enhance the park and not limit access.
13 | Rogue River South Bank at Riverside Park | RR | GP | GP-RR-RP-2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 3 | 45 | Canopy and habitat building at Riverfront Park. Will need to be ground truthed and designed to enhance the park and not limit access.
14 | Rogue River North Bank | RR | GP | GP-RR-P-4 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 36 | Identified from aerial photos. On Private land. Field verification is needed.
15 | Tussing Park Drainage | RR | GP | GP-TP-1 | 3 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 2 | 0 | 0 | 3 | 41 | Storm drain and drainage in Tussing Park. Excellent opportunity for understory/habitat building and education by tying it into surrounding activities.
16 | Rogue River at All Sports Park | RR | GP | GP-RR-ASP-1 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 42 | Invasive species control and planting (canopy and understory) near All Sports Park bridge (north side of river)
17 | Rogue River at All Sports Park | RR | GP | GP-RR-ASP-2 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 42 | Invasive species control and planting (canopy and understory) near All Sports Park bridge (north side of river)
18 | Rogue River at All Sports Park | RR | GP | GP-RR-ASP-3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 42 | Invasive species control and planting (canopy and understory) near All Sports Park bridge (north side of river)
19 | Gilbert Creek at Gilbert Creek Park | O | GP | GP-GC-1 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 38 | Potential project with local schools and the Rogue River Watershed Council.
20 | Rogue River South Bank Near Baker Park | RR | GP | GP-RR-BP | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 0 | 2 | 3 | 3 | 3 | 45
21 | Reinhart Park Knotweed (North Bank) | RR | GP | GP-RR-RP-KNT1 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 48 | Areas/Subareas for knotweed control and restoration with natives. Included up and downstream of pedestrian bridge.
22 | Reinhart Park Knotweed (South Bank) | RR | GP | GP-RR-RP-KNT2 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 48 | Areas/Subareas for knotweed control and restoration with natives. Included up and downstream of pedestrian bridge.
0
| Waterbody | Code
| Rogue River | RR
| Bear Creek | BC
| Other (slough, wetland, lake, pond) | O
| DMA | Code
| Jackson County | JACO
| Josephine County | JOCO
| Curry County | CC
| Gold Beach | GB
| Cave Junction | CJ
| Grants Pass | GP
| Gold Hill | GH
| Rogue River | RR
| Eagle Point | EP
| Shady Cove | SC
| Butte Falls | BF

## Salmon Watch 2018
Rogue Basin Salmon Watch Program