## Draft Matrix
Source or Program | Strategy | Specific Actions | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost | Reporting Year or Plan Year | Activity (Reporting) Summary 2017-2018
I. Implement TMDL Program using existing programs and updating or creating programs as needed. | A. Use existing programs and available resources to implement programs. | 1. Develop an inventory or schedule of anticipated TMDL related activity being conducted by the City including department responsibilities. | 1. Draft List by November 1st, revised list in March, final updated for annual report. | City Staff - Public Works, Parks, Planning, and Engineering. | Annually | The schedule of annual regional activities was reviewed and updated for 2017-2018. Several annual reviews of the schedule, resources, and deliverables were added (and completed) for the beginning and end of the Tidal implementation year. The schedule is included as a separate tab in the full matrix. Copies of the one page report and full version with the tabs is available on the Grants Pass TMDL webpage located on the RVCOG website (http://rvcog.org/grants-pass-tmdl/).
|  | 2. Work with the Josephine SWCD, RVCOG, Grants Pass Irrigation District, OSU Extension, the Rogue River Watershed Council, the Rogue Basin Partnership, Middle Rogue Steelheaders Assoc, RCC and/or local schools to implement and promote TMDL programs. | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Annually | The City and the Regional Coordinator (RC) worked with North Valley High School, Hidden Valley High School, Grants Pass Irrigation District (GPID), the Stream Smart program, the Rogue Basin Partnership (RBP), CWMA's, other municipalities, the Bear Creek MS4s, agencies, the Rogue River Watershed Council (RRWC), and other groups to implement and promote the TMDL program. Specific activities are documented in the matrix and in the tabs. Updated tab I.A.2 which contains a list of groups that can help with TMDL programs (and other needs).
|  | 3. Identify resources available for program (e.g. staff hours, available funds, etc.) and program needs (gaps). | 3. Summary of available resources and needs. | Public Works Staff, Engineering and Planning Staff | Annually | The City contracts with RVCOG annually for coordination and implementation services ($22,500.00). The City adjusted RVCOG's contract to coincide with the TMDL implementation Year , so the contract covers 18 months and runs through June 30th, 2019. City Staff contributes an estimated 100 hours to the TMDL program for meetings, implementation actions including maintaining dog dispensers, stormwater programs, reporting, networking with other groups, participating in Stream Smart, and other activities. Other resources include staff of the RRWC, ODFW, RBP, and other programs (e.g., Stream Smart).
|  | 4. Review existing code and ordinances to evaluate the status of other TMDL related concerns from DEQ's Key Strategies for Rogue River Implementation that are not addressed in other matrix sections including Floodway/Floodplains and wetlands. | 4. Summary of existing code sections and potential changes or additions that may be needed. | Public Works Staff, Engineering and Planning Staff | Year 1, Review annually | The ordinances_stormwater tab has a list of existing ordinances (code sections), any activity (updated annually), and references to the relevant sections of the TMDL Matrix. A review of the sections was completed by the RC and City, and program activities is updated in the tab.
|  | 5. Review existing code and enforcement procedures to evaluate adequacy to address riparian and wetland issues and other TMDL related concerns. | 5. Summary of existing code and identify sections that may need to be revised and/or updated. | Public Works Staff, Engineering and Planning Staff | Year 1, Review annually | We are recommending that this be combined with item I.B.1, so the revised timeline is anticipated to be completed in Year 5.
| B. Update codes, ordinance, and other programs (e.g. incentives) as needed to assist in program implementation. | 1. Develop an schedule of anticipated TMDL needs including code and ordinance revision and other activities. | 1. Summary included in annual report/matrix. | City Staff - Public Works, Parks, Planning, and Engineering. | Year 2-3 Year 5 | Many of the codes that need updating are tied into the MS4 stormwater program. The City is waiting for final guidance from DEQ regarding program development, timelines, and other information from the revised general permit, which once completed, will designated new MS4s (including Grants Pass) and program requirements. The timeline for completion of the general permit has been delayed again as DEQ addresses comments and subsequently, the timeline for this task is proposed to be changed to later in the implementation schedule to be finalized when the general permit is released.
|  | 2. Modify matrix with proposed schedule for revisions and other activities. Potential activities may include revising/updating/creating floodway and floodplain protection, wetland protection, and incentives for riparian protection | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Years 3-4 | Suggested modifications appear in the notes column or in the reporting year or plan year in red and selected replacements are made using the strikethrough feature.
II. Solar Radiation – Near-Stream vegetation disturbance/ removal. Increase effective shade through restoration and protection. | A. Continue to identify and inventory new areas to restore, plant, and protect by reviewing and updating maps, lists, and/or other materials as needed. | 1. Continue to use open space, public lands, wetlands and parks inventories, watershed assessments, local knowledge, and GIS maps to identify areas. | 1. Updated maps, lists, and/or other materials. Shape files will be created for identified areas. Shape file attributes will be updated as sites are prioritized, invasives are removed, and/or the sites are planted. | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually | Sites identified are added to the prioritized sites lists and highlighted in yellow to distinguish them since the last report. In addition, the scoring matrix is adjusted to include new information . Updated maps are included on the Grants Pass TMDL Implementation website along with copies of the matrixes and other relevant information. The webpage can be accessed at http://rvcog.org/grants-pass-tmdl/.
| B. Prioritize any newly identify areas. | 1. Use established criteria to prioritize identified sites. | 1. Updated summary/list of prioritized sites as needed. | City Staff - Public Works, Parks, Planning, and Engineering, RVCOG, other partners. | Annually | The established prioritization criteria including the scoring metric is included in the prioritization tab. Any new sites scores are on the sites identified tab and highlighted in yellow. In addition, locations of pollinator gardens are being considered and location identified will be added to the map where the coincide with riparian areas.
|  | 2. Field check prioritized areas to verify needs for implementation. | 2. Summary of field checks completed | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually | No field checks were completed this year.
| C. Restore, protect, and plant areas. | 1. Seek opportunities to plant native trees and shrubs in public areas, open spaces, city parks and along streams and rivers. Specific creeks to evaluate include Gilbert Cr., Skunk Cr., Mill Cr., Grouse Cr., Jones Cr., Sand Cr. and the Rogue River along City Park property. | 1. List of areas planted including numbers of trees and shrubs. In addition, create shape files of areas planted. | Public Works Staff, Parks Staff, Public Contracts, Volunteers, County work crews, RVCOG, Partners | Annually | The RC and the City worked with the RRWC, RBP, local schools (Grants Pass High School, RCC, and others) to identify planting opportunities. City crews and contracted labor groups (such as the Josephine County Work Crews), when pruning or cutting along any waterway, continue to protect all vegetation shading the streams or waterways. Tall grass buffers are maintained during the summer season when there is no other streamside vegetation. No planting projects were completed by the RC during the implementation year.
|  | 2. Identify partnering opportunities, for public and private lands, during each plan year by contacting local groups (the Rogue Basin Partnership, Rogue River Watershed Council, Middle Rogue Steelheaders, Roe Motors, Josephine SWCD, Josephine County Public Works, local volunteer groups and schools) and summarizing project opportunities. | 2. Summary of opportunities available. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC and the City worked with the RRWC, RBP, local schools (Grants Pass High School, RCC, and others to identify planting opportunities. Local groups were contacted in person, at events, through mailings, emails, and at meetings. In addition, the RC served on RBP's riparian working group which focuses on restoration needs (including implementation of projects) in the Rogue Basin. Members of the working group include the Freshwater Trust, Rogue River Watershed Council, and Lomakatsi.
|  | 3. Work with local groups to schedule and complete projects annually as time and funding permit. | 3. Summary of projects scheduled and completed including number and locations of trees and shrubs planted. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | No planting projects were completed during the implementation year.
|  | 4. Evaluate funding options for restoring, planting, and protecting priority sites and pursue finding options as time and resources permit. | 4. Summary of funding sources identified, applications submitted, and funding received. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC continues to work as part of the Rogue Basin Partnership to implement a Rogue Action Plan which includes protecting and restoring riparian areas throughout the Rogue Basin. Primary funding for restoration is through grants and volunteer efforts. The City will continue to work with the RC and other groups to submit proposals to OWEB and other programs to fund restoration work. No proposals were submitted or received for planting during the implementation year. The RM continues to work with RBP to develop a Capital Improvement Plan for restoration projects which would includes sites identified as part of the TMDL program.
| D. Riparian Ordinance –Evaluate, strengthen, or develop riparian ordinances as needed (Goal 5) to protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under the City of Grants Pass jurisdiction. | 1. Draft new ordinances or revise ordinance as needed based on recommendations from earlier TMDL reports and/or other programs. | 1. Completed draft ordinance. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations. | The City and RC began a review of existing ordinances region wide and statewide to identify potential models to use. Models included recommendations for ordinances that serve different functions (e.g., salmonid habitat, bird habitat, sediment and nutrient reduction), recommendations for urban areas versus areas outside of urban areas, and what is being done locally, regional, and statewide. The models will be used to update or replace existing ordinances. In Years 3 and 4 , the City will develop a recommended riparian ordinance revision or a revised ordinance through a public process to be incorporated into the public process.
|  | 2. Public notice of new or revised ordinances and Grants Pass review procedure. | 2. Summary of noticing and procedures used to move the ordinance towards adoption. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations. | In Year 3, the City will begin the public process and hold meeting(s) and/or work session to present options to the City Council and the Public. In Year 4, the City will use the recommendations of the public process to finalize revisions to the existing ordinance or replacing the ordinance.
|  | 3. Adopt new ordinances or revised ordinances as needed. | 3. Adopted ordinances or ordinance revisions. | Public Works, Planning and Engineering Staff, Public Safety and Code Enforcement | Pending, based on new Phase II regulations. | To be completed in Year 5.
III. Solar Radiation –Near stream vegetation disturbance - overrun by invasive species. | A. Continue to implement invasive species management programs in public areas. | 1. Manage invasive species in parks and other City owned properties. | 1. Summary of acres of invasive areas treated. | Public Works Staff, Engineering, Planning Staff, Volunteers, Partners. | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event was held at Hog Creek Boat Ramp in May. Attendees and volunteers included local scouts, RBP, community volunteers. City staff and/or contractors also maintains invasives on all City Parks and properties. City activities removed invasives on approximately 3 acres.
|  | 2. Train staff on noxious/invasive weeds including identification and treatment options. | 2. Summary of any training conducted, promoted, or that staff was sent to. | City Staff | Annually
|  | 3 Work with watershed groups to manage invasive species on private land and protect and/or plant native species in riparian areas where invasives are removed. | 3. Number of trees and shrubs planted annually. Number of acres of invasives removed. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, the Freshwater Trust, and others to promote weed related projects including the Annual Weed Pull (Let’s Pull Together), the Weed Wrangle, and on the ground removal projects..
|  | 4. Coordinate invasive weed management activities with the County Weed Management Area. | 4. Activity Summary. | Public Works Staff, Parks Staff, Josephine County Public Works, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC coordinates with the CWMAs (currently coordinated by RBP) regarding activities in both Counties and the City of Grants Pass. The RC is on the CWMA list serve, periodically attends meetings, promotes events, and participates in selected activities. In addition, worked with the CWMA, Josephine County, Grants Pass, and others to promote the Annual Weed Pull (Let’s Pull Together). Participated in discussions with the CWMA, coordinated activities when appropriate, and attended the weed pull. In addition, information on 4 major species of interest that the CWMA are working on was added to the City's TMDL page along with other information, resources, and links for managing invasive plants.
IV. Other Anthropogenic Sources: Urban Runoff – Reduce runoff, promote infiltration and low impact development practices. | A. Promote the use of methods and practices that reduce urban runoff and impervious surface area. | 1. Create or update map locations where low impact development practices are being used or will be used to reduce urban runoff and creation of impervious surface area. | 1. Map of Locations. | Public Works Staff, Planning and Engineering Staff | Annually | The City and RC are working on documenting where locations are using Google Earth and GIS.
|  | 2. Work with the development of the stormwater program (V) to revise codes and ordinances revision to incorporate low impact development practices. | 2. Summary of revised code. | Public Works, Planning and Engineering Staff | Annually - summary after NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 3. Require new construction to minimize impervious surface and treat stormwater onsite using LID techniques or other appropriate methods. | 3. Summary of requirements. | Public Works, Planning and Engineering Staff | Incorporate in V.
V. Other Anthropogenic Sources: Urban Runoff – Stormwater Management Program. | A. Develop a stormwater management program addressing the six elements of Phase II Stormwater Management. | 1. Outline existing programs that meet each of the six minimum control measures for NPDES Phase II Stormwater Management. | 1. Existing program summary. | Public Works, Planning and Engineering Staff | Year 1 | The City and the RC participate in the Regional Stormwater Advisory Team. In addition, elements of the education and outreach programs (e.g., Salmon Watch, the Land Steward Workshop) meet multiple objectives including stormwater. In addition, the Ordinances_Stormwater Sections tab summarizes elements of City codes and ordinances and matrix sections that will contribute to the development of the stormwater program. In 2017 and 2018 a stormwater brochure was developed and printed with Green Street Design for distribution. Copies of the brochure were provided to the City.
|  | 2. Identify gaps, needs, and next steps needed to develop program. | 2. Summary of gaps and next steps. | Public Works, Planning and Engineering Staff | Year 2 | The City is waiting for final guidance from DEQ regarding program development, timelines, and other information from the revised general permit, which once completed, will designated new MS4s (including Grants Pass) and program requirements. The timeline for completion of the general permit has been delayed and subsequently, the timeline for this task is proposed to be changed to later in the implementation schedule to be finalized when the general permit is released.
|  | 3. Develop or adopt a Storm and Surface Water standards manual | 3. Draft manual (year 4) and completed manual (year 5) | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City is currently developing a stand alone City of Grants Pass Stormwater Management Manual with an anticipate delivery of a draft manual in the fall of 2017. Staff will review the draft manual and will send comments back to the consulting engineer. Manual to be completed and adopted in 2018.
|  | 4. Develop a Pollution Prevention/Good Housekeeping Program | 4. Summary of Program | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City will inventory existing work practices and procedures being done by City work groups and compile a list in the annual report starting in Year 3. In Years 3-4, the City will review model programs and evaluate revisions/improvements needed to the existing programs and report on activity. In Year 4-5, the City will develop a pollution prevention/good housekeeping program.
|  | 5. Develop and implement an erosion prevention and sediment control program. | 5. Summary of programs and procedures. | Public Works Staff, Planning and Engineering Staff | Year 1 | All proposed or planned developments within the City of Grants Pass, including the Urban Growth Boundary, are required to submit a detailed "Erosion and Sediment Control Plan" to the city before any construction begins. Plans are review and inspections completed before and during the length of the project. Inspectors have taken trainings in Erosion Control and Prevention provided by RVSS and other APWA Conferences.
|  | 6. Provide incentives to developers and homeowners to install or retrofit landscapes and to provide on-site stormwater treatment and detention. | 6. Summary of incentives | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City will review programs providing incentives and report on activity in Year 3. In Years 3-4, the City will develop a list of projected incentives to provide on-site stormwater treatment and detention. In year 5, the City's Stormwater Management Manual, once adopted will incorporate incentives into codes and ordinances for proper onsite management of stormwater.
|  | 7. Revise and update maintenance program for existing stormwater management structures or features. | 7. Revise and update training and education programs for maintenance and a schedule for inspection and maintenance as needed. | Public Works, Planning and Engineering Staff | Annually
VI. Fecal Sources: Animal waste management – pet, wildlife, and livestock waste. Properly manage animal waste. | A. Provide bags for dog owners to pick up pet waste. | 1. Update inventory of parks / public areas that have pet waste disposal dispensers. | 1. List of parks and public areas with pet waste disposal dispensers | Public Works and Parks Staff | Annually
|  | 2. Identify additional areas where bag dispensers are scheduled to be or have been placed since the previous inventory. | 2. Document number of bags provided and number and location of new bag dispensers in annual report. | Public Works and Parks Staff | Annually
| B. Develop partnerships with SWCDs, ODA, and other groups to work on animal waste management programs in agricultural areas. | 1. Summary of any programs identified addressing animal waste management with landowners, agriculture, ODA, IDs, County programs, and other groups. | 1. Summary of programs | Public Works and Parks Staff | Annually | Programs identified include the Inland Rogue Water Quality Management Plan, local agencies (ODA, SWCDs, OSU Extension) and the Stream Smart Program (http://www.stream-smart.com/making-bear-creek-better/agriculture-and-forestry/). Funding provide by the City supports the development and maintenance of the Stream Smart Program.
|  | 2. Partner with local groups to encourage proper manure, upland irrigation and nutrient management. | 2. Summary of partnerships. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | Continued to work with ODA regarding resources and recommendations that they have for meeting this task. They recommended working with local SWCD’s and implementing the Inland Rogue Water Quality Management Plan. Referred question to agencies (ODA, SWCDs, OSU Extension) and the Stream Smart Website for more information (http://www.stream-smart.com/making-bear-creek-better/agriculture-and-forestry/).
VII. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | A. Establish and/or refine illegal dumping/illicit discharge detection and elimination (IDDE) program. | 1. Create, adopt, or revise and strengthen IDDE program as needed. The development of program with element V. Development of a Stormwater Management Program. | 1. Summary of IDDE program. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City is waiting for final guidance from DEQ regarding program development, timelines, and other information from the revised general permit, which once completed, will designated new MS4s (including Grants Pass) and program requirements. The timeline for completion of the general permit has been delayed and subsequently, the timeline for this task is proposed to be changed to later in the implementation schedule to be finalized when the general permit is released.
|  | 2. Implement IDDE program | 2. Program implementation summary. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | Anticipated in Years 5 based on completion of VII.A.1.1.
|  | 3. Create, update, or refine storm drain system map for the City. | 3. A summary of the existing status of the storm drainage system mapping including what format it's in, any updates, and if not completed, a general strategy for completing the mapping. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City's Stormwater Master Plan has been completed and adopted by the City Council. City is in the process of completing a Stormwater Management Manual. Anticipated to be completed and adopted in 2018. GIS map are updated on an ongoing basis as discrepancies are located by field staff or as new structures are installed.
|  | 4. Evaluate the use of stormwater system maps to assist in identifying illegal dumping and sources of bacteria. Revise and/or create maps or use existing maps. | 4. Map identified areas of high bacteria. | Public Works, Engineering and Planning Staff. | Completed after VII.A.3 is completed. | Completed following VII.A.3.3
|  | 5. Track any IDDE concerns reported in the City. | 5. Summaries of any concerns identified, tracked, and/or reported. | Public Works, Engineering and Planning Staff. RVCOG, DEQ, other partners. | Annually | The RC documents calls regarding regional water quality including IDDE and septic systems. No calls were documented this year for septic concerns.
|  | 6. Enforce illegal dumping as identified or found. | 6. Description of enforcement including number of contacts made, warnings issue and fines levied. | Public Works (Drainage and Utilities) and Engineering Staff and Public Safety. | Annually
VIII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | A. Notify DEQ of failing systems when found. | 1. The City of Grants Pass will notify DEQ of failing systems when found. | 1. Summarized referrals. | Public Works (Drainage and Utilities) and Engineering Staff. RVCOG. | Annually | The RC documents calls regarding regional water quality including IDDE and septic systems. No calls were documented this year for septic concerns.
IX. Outreach and Education | A. Continue to implement outreach strategy that addresses water quality parameters in the TMDL. | 1. Review materials (e.g., brochures, activities, web sites) from educational programs. | 1. Summary of review in annual report including examples of materials and/or links. | Public Works and Engineering Staff, RVCOG | Annually | The RC reviews and updates materials from educational programs annually. New materials are incorporated into the Stream Smart website, TMDL websites, hands on displays, posters, and other materials. Examples of materials are in the Stream Smart Tab.
|  | 2. Adopt, customize, and/or develop regional materials from programs reviewed. | 2. Copies of information created, customized, and/or distributed. | Public Works and Engineering Staff, RVCOG | Annually | The City is participating in the StreamSmart Program which provides regional messaging on a number of topics throughout the Rogue Basin. A revised stormwater brochure was completed in 2018 and printed with the Stream Smart logo replacing the list of all communities involved. The logo represents all participants including the City. The logo was also used to promote programs, events, and on other brochures (including the pledge cards in English and Spanish).
|  | 3. Promote local and/or regional success stories as applicable by preparing information for summary on websites and contacting media outlets. | 3. Summary of information on regional projects. | Public Works and Engineering Staff, RVCOG | Annually | Regional success stories are promoted in the media, at meetings, at events, posted on websites including the Stream Smart main page, posts on the Stream Smart Facebook site, RVCOG's, Jefferson Public Radio, the Grants Pass TMDL site, and other websites.
|  | 4. Participate in regional education opportunities with other groups and DMAs in the Rogue Basin. | 4. List of activities. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City through the activities of the RC participates in several regional education efforts annually. Specific examples include the annual Living on Your Land Steward Workshop held at Rogue Community College in Grants Pass for Josephine and Jackson County Residents, participation in the Salmon Watch program, participation in the World Fish Migration Day (new in 2018), and the Stream Smart program.
| B. Hold, participate in, and/or promote annual water quality events. | 1. Update list of annual events related to water quality, riparian planting, the benefits of healthy riparian areas, native plants and other TMDL topics. | 1. Event list or summary of events in annual report. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The annual event list is reviewed annually and updated as needed. In additional, annual events that the City supports by promoting and/or attending are added to the calendar. Events are posted on the Stream Smart, Rogue Basin Partnership, and/or RVCOG event calendars.
| C. Provide citizens, landowners and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. Revise and update list of local agencies, nurseries, and other resources for planting as needed. | 1. Summary of updates and/or updated list of resources including contact information and location. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | The resource list in tab I.A.2 was revised and updated.
|  | 2. Distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | Materials distributed included the Taking Care of Streams in Josephine County, Stream and Wetland Enhancement Guide, Garden Smart Oregon: a guide to non-invasive plants, Rogue Valley Native Plant and Seed Sources, Trees and Shrubs for Attracting Pollinators, and Garden-Worthy Native Trees and Shrubs. Materials were distributed at the City, at meetings, at RVCOGs front counter, and through events (e.g., Land Steward Workshop). In addition, materials are available at and residents were referred to the Stream Smart website, links on Grants Pass's TMDL website (RVCOG), and RVCOG's riparian web pages.
|  | 3. Coordinate partnerships with DMAs and other organizations to provide technical assistance and other resources as needed. | 3. Document technical assistance and resources provided, including the number of any plants distributed and associated planting locations. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | Partnered with other DMAs and organizations including the Land Steward Workshop and World Fish Migration Day with the Bear Creek Ms4s, the Stream Smart Program with other TMDL communities, and distributing materials in the City and online.
| D. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Continue to target areas of high animal usage including public areas near waterways and dog oriented businesses. | 1. Activity summary in annual report. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City has signs in conjunction with their dog parks and pet waste stations. In addition, the RC has referred people to information on the Stream Smart website including the Poop Pledge. Additional information in English and Spanish on the Stream Smart Program and other water quality topics including animal waste was available at the Stream Smart cart located in the Rogue Valley Mall and at events throughout the County including the Land Steward Workshop and World Fish Migration Day which were both held in Grants Pass..
|  | 2. Collect, develop, and/or distribute brochures, pamphlets and other materials to target areas. | 2. Documentation of materials distributed. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City has signs in conjunction with their dog parks and pet waste stations. In addition, the RC has referred people to information on the Stream Smart website including the Poop Pledge. Additional information in English and Spanish on the Stream Smart Program and other water quality topics including animal waste was available at the Stream Smart cart located in the Rogue Valley Mall and at events throughout the County including the Land Steward Workshop and World Fish Migration Day which were both held in Grants Pass..
| E. Provide outreach and technical assistance to private landowners and the public above the removal of invasives and weed control. | 1. Work with the Josephine County Weed Management Area (CWMA), O.S.U. Extension, and/or other groups working on weeds to provide technical assistance, educational opportunities, and/or materials on managing invasive weeds. | 1. Summary of activity with groups including any meetings attended, materials collected and distributed, contacts made, and documentation of any assistance provided. | Public Works and Engineering Staff, RVCOG, CWMA, OSU Extension, other local groups | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event held at Hogs Creek in May. Participated in discussions with the CWMA and coordinated activities when appropriate. In addition to the RC and the City referring residents to the CWMA, OSU Extension, and SWCD's, and information on noxious weed management on the City's TMDL page, the program has several brochures that provide guidance for invasive species removal (Weed Invasion Insert, Oregon Smart Garden, and BLM's "Noxious Weeds are Pretty, But..."
|  | 2. Promote and/or support activities for the public to participate in opportunities to learn about weeds and participate in training and events related to invasive weed control. | 2. List of events promoted, supported, and/or attended by staff or a city representative (e.g., RVCOG). Potential events include the Annual Josephine County Weed Pull, and OSU's Land Steward workshops. | Public Works and Engineering Staff, RVCOG, CWMA, other local groups | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event held at High Creek Boat Ramp in May and the Weed Wrangle in August. Participated in discussions with the CWMA and coordinated activities when appropriate.
| F Staff Training | 1. Train staff as needed on topics related to TMDL Implementation. (Include Management Staff and Elected Officials) | 1. List of how training was conducted and frequency. | Public Works, Planning, Building and Engineering Staff | Annually | Topics/presentations are quarterly TMDL meetings included - the Swim Guide and Bacteria Monitoring, the Pesticide Stewardship Partnership (PSP), Groundwater (Assessment Units and local study results), ODA's Strategic Implementation Areas for Wagner Creek and Neil Creek. Specific training examples that were held that were attended by DMAs included the Salmon Watch Instructor Training (September 14th), the HazMat Spills training organized by RVSS (October 3rd), and EcoBiz (June 14th and 15th). The EcoBiz training focused on Fleets and Auto Service Stations so it was more Phase II focused. However, the program can be expanded to certify landscapers which would TMDL related. In addition, with the RC attending the training, businesses in Grants Pass could be inspected by and submitted to the program by the RC. A number of online webinars, local, regional, and statewide trainings were also promoted at TMDL meetings and through TMDL distribution lists by the RC, DMAs, and partners (e.g., RVSS).
X. Regional Water Quality Coordination | A. Continue participation in the TMDL program. | 1. The City of Grants Pass will continue participation in the TMDL program. | 1. Attendance (in person, phone or video conferencing if available) at quarterly meeting and other meetings as requested. | Public Works, Planning, Building and Engineering Staff | Annually | RVCOG worked with DEQ to coordinate quarterly meetings on July 19th and October 18th, 2017, January 31st, and April 18h, 2018. Funding provided by the City supports the TMDL meetings. In addition, Grants Pass staff attended meetings in July, October, January, and April.
XI. Funding | A. Evaluate the costs of program implementation. | 1. Establish costs of program implementation for the next plan year and identify funding sources as needed including staff time, grant funding, and other resources. | 2. List program costs and sources (e.g., staff time, direct funding, grants, etc.). | Public Works, Planning, Building and Engineering Staff | Annually | RVCOG provides the City with annual costs for continued assistance. The City has set aside approximately $15,000.00 per year for implementation assistance. The City contracted with RVCOG to provide support. Details of the specifics are in the RC Contract detail tab. Changes were made in 2017 to the contract to align the RC deliverables and contract with the Tidal year. The City is planning to contract with RVCOG to complete future activities. In addition, implementation in the City the Streets and Drainage Superintendent (10% time), Maintenance personnel (15% of time). The City has also hired a consulting firm (Keller and Associates) to help update it's stormwater master plan. The City has also negotiated with GPID to design a plan to design a plan to work together on stormwater. The City has continued work on establishing a stormwater utility.
| B. Identify program funding opportunities. | 1. Evaluate existing resources available to begin program implementation. | 1. Summary of existing resources used. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The City contracts with RVCOG annually for coordination and implementation services ($15,000.00). Additional funding has been provided through grants (Meyer, Gray Family, and Jackson SWCD ($5,000.00)and from RBP ($1,000.00).
|  | 2. Provide an inventory of funding, potential Regional Program grants. | 2. List of identified funding sources and deadlines provided to The City of Grants Pass and other agencies. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The RC has participated in Regional meetings including the Rogue Basin Partnership representing urban interests (TMDL and NPDES Stormwater Phase II). RBP works in partnership with local watershed councils Rogue River Watershed Council, NGOs (the GEOS Institute), and others (Medford Water Commission, Jackson SWCD )to develop a process for prioritize restoration and other projects across the Rogue Basin. A major goal of the program is to attract outside funding from foundations and other large investors to implement regional projects. Working groups, including the riparian working group on which the RC participates, are working on packaging projects together related to TMDL including restoration and monitoring.
|  | 3. Collectively (regionally) apply for funding for implementation and region-wide projects. | List of participation in regional implementation opportunities. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The RC worked with RBP to apply for and secure funding from the Meyer Memorial Trust for regional education and outreach programs across the Rogue Basin including Weed Pulls, Creek Clean-ups, and education symposiums. The RC is continuing to implement deliverables of the grant. In addition, the RM applied to both the Jackson SWCD (Fall 2017) and the Grey Family foundation (Fall of 2018) for Salmon Watch. Classes are planned in Grants Pass for 2018.
|  | 4. Document any funding and/or in-kind support for projects or partner projects. | List of funding and in-kind support. | Public Works Staff, RVCOG, Local Watershed groups | Annually | Funding activity including partner support is tracked using TMDL tracking forms, program spreadsheets, and other formats. In-kind support from grants and staff time is estimated at $15,000.00. Collectively, the Salmon watch grants were over $20,000.00 with an estimated $4,000.00 supporting classes for Grant Pass Schools and/or locations.
XII. Monitoring and Reporting | A. Use the matrix as a template to track the implementation plan. | 1. Compile information from completed activities into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually | Tracking of activities is done by the RM regularly using calendars, spreadsheets, attendance sheets, manual counters, log sheets, reports, and other methods. Additional detail is provided in reports, project summaries, online, and invoices. Details are included on separate tabs and/or in the reporting columns as needed. In addition, selected deliverables including completed matrixes are posted on the RVCOG, Grants Pass TMDL, and/or Stream Smart website.
| B. Submit annual reports to DEQ. | 1. Submit annual reports to DEQ. | 1. Completed annual reports submitted to DEQ by September 30 of each year, reporting on implementation actions for the July 1-June 30 plan year. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually, November 1st of each year. | Completed. The matrix was submitted to DEQ and a detailed report containing all supplemental pages can be accessed on the Grants Pass TMDL Homepage under RVCOG's website at http://rvcog.org/grants-pass-tmdl/.
| C. Use existing programs to track program effectiveness. | 1. Work with DEQ, RVCOG, and other DMAs to evaluate methods for evaluating and tracking program effectiveness. | 1. Summary of methods evaluation. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually | The RC and the City track effectiveness through the attendance at events/workshops/trainings/meetings/etc, number of visits to the websites, number of brochures handed out, surveys, number of trees and shrubs planted, number of stream miles or acres protected, amount of invasive species managed (acres), mapping, and other methods. The Stream-Smart website had 3,705 visitors. Please see the information on the Stream Smart Web Stats Tab for the visitor breakdown and most visited pages. Other statistics are tracked in the activity log tab. Effectiveness is measured by meeting specific deliverables/milestones and other implementation plan targets. In year 5, the RC and City will review previous reports to see how milestones (number of people reached, brochures distributed, etc.) have changed from year to year and overall.
|  | 2. Work with DEQ, RVCOG, and other DMAs to use existing programs (DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. | 2. Summary of regional water quality. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually | The RC is participating as part of RBP's monitoring work group which is evaluating monitoring across the Rogue Basin. A long term goal of the working group is to use the data to create a watershed report card which will summarize watershed conditions. The report card may be able to be used to evaluate program effectiveness related to the water quality elements of the report. In addition, the Bear Creek DMAs applied for and received a grant to analyze monitoring data to evaluate the effectiveness of their TMDL implementation program. Results of the analysis will be reviewed by the City for potential adaptation in future years of the TMDL Implementation program..
| D. Adaptive Management Plan. This is an ongoing plan and modifications and adjustments will take place. | 1. Modify plans as needed. | 1. Summary of any revisions to Water Quality Implementation Plans. | Public Works, Planning, Engineering Staff, RVCOG, other DMAs. | Annually | Any changes in terms of requests for annual plan modifications is included in the reporting column. Previous requested changes were left in the columns in addition to any new requested changes..
Note on C27: gstabach:III.A.3 and II.A.4 were the same so I deleted one.