## Draft Matrix
Source or Program | Strategy | Specific Actions | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost | Reporting Year or Plan Year | Activity (Reporting) Summary 2017-2018
I. Implement TMDL Program using existing programs and updating or creating programs as needed. | A. Use existing programs and available resources to implement programs. | 1. Develop an inventory or schedule of anticipated TMDL related activity being conducted by the City including department responsibilities. | 1. Draft List by November 1st, revised list in March, final updated for annual report. | City Staff - Public Works, Parks, Planning, and Engineering. | Annually | The schedule of annual regional activities was reviewed and updated for 2017-2018. Several annual reviews of the schedule, resources, and deliverables were added (and completed) for the beginning and end of the Tidal implementation year. The schedule is included as a separate tab in the full matrix. Copies of the one page report and full version with the tabs is available on the Grants Pass TMDL webpage located on the RVCOG website (http://rvcog.org/grants-pass-tmdl/).
|  | 2. Work with the Josephine SWCD, RVCOG, Grants Pass Irrigation District, OSU Extension, the Rogue River Watershed Council, the Rogue Basin Partnership, Middle Rogue Steelheaders Assoc, RCC and/or local schools to implement and promote TMDL programs. | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Annually | The City and the Regional Coordinator (RC) worked with North Valley High School, Hidden Valley High School, Grants Pass Irrigation District (GPID), the Stream Smart program, the Rogue Basin Partnership (RBP), CWMA's, other municipalities, the Bear Creek MS4s, agencies, the Rogue River Watershed Council (RRWC), and other groups to implement and promote the TMDL program. Specific activities are documented in the matrix and in the tabs. Updated tab I.A.2 which contains a list of groups that can help with TMDL programs (and other needs).
|  | 3. Identify resources available for program (e.g. staff hours, available funds, etc.) and program needs (gaps). | 3. Summary of available resources and needs. | Public Works Staff, Engineering and Planning Staff | Annually | The City contracts with RVCOG annually for coordination and implementation services ($22,500.00). The City adjusted RVCOG's contract to coincide with the TMDL implementation Year , so the contract covers 18 months and runs through June 30th, 2019. City Staff contributes an estimated 100 hours to the TMDL program for meetings, implementation actions including maintaining dog dispensers, stormwater programs, reporting, networking with other groups, participating in Stream Smart, and other activities. Other resources include staff of the RRWC, ODFW, RBP, and other programs (e.g., Stream Smart).
|  | 4. Review existing code and ordinances to evaluate the status of other TMDL related concerns from DEQ's Key Strategies for Rogue River Implementation that are not addressed in other matrix sections including Floodway/Floodplains and wetlands. | 4. Summary of existing code sections and potential changes or additions that may be needed. | Public Works Staff, Engineering and Planning Staff | Year 1, Review annually | The ordinances_stormwater tab has a list of existing ordinances (code sections), any activity (updated annually), and references to the relevant sections of the TMDL Matrix. A review of the sections was completed by the RC and City, and program activities is updated in the tab.
|  | 5. Review existing code and enforcement procedures to evaluate adequacy to address riparian and wetland issues and other TMDL related concerns. | 5. Summary of existing code and identify sections that may need to be revised and/or updated. | Public Works Staff, Engineering and Planning Staff | Year 1, Review annually | We are recommending that this be combined with item I.B.1, so the revised timeline is anticipated to be completed in Year 5.
| B. Update codes, ordinance, and other programs (e.g. incentives) as needed to assist in program implementation. | 1. Develop an schedule of anticipated TMDL needs including code and ordinance revision and other activities. | 1. Summary included in annual report/matrix. | City Staff - Public Works, Parks, Planning, and Engineering. | Year 2-3 Year 5 | Many of the codes that need updating are tied into the MS4 stormwater program. The City is waiting for final guidance from DEQ regarding program development, timelines, and other information from the revised general permit, which once completed, will designated new MS4s (including Grants Pass) and program requirements. The timeline for completion of the general permit has been delayed again as DEQ addresses comments and subsequently, the timeline for this task is proposed to be changed to later in the implementation schedule to be finalized when the general permit is released.
|  | 2. Modify matrix with proposed schedule for revisions and other activities. Potential activities may include revising/updating/creating floodway and floodplain protection, wetland protection, and incentives for riparian protection | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Years 3-4 | Suggested modifications appear in the notes column or in the reporting year or plan year in red and selected replacements are made using the strikethrough feature.
II. Solar Radiation – Near-Stream vegetation disturbance/ removal. Increase effective shade through restoration and protection. | A. Continue to identify and inventory new areas to restore, plant, and protect by reviewing and updating maps, lists, and/or other materials as needed. | 1. Continue to use open space, public lands, wetlands and parks inventories, watershed assessments, local knowledge, and GIS maps to identify areas. | 1. Updated maps, lists, and/or other materials. Shape files will be created for identified areas. Shape file attributes will be updated as sites are prioritized, invasives are removed, and/or the sites are planted. | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually | Sites identified are added to the prioritized sites lists and highlighted in yellow to distinguish them since the last report. In addition, the scoring matrix is adjusted to include new information . Updated maps are included on the Grants Pass TMDL Implementation website along with copies of the matrixes and other relevant information. The webpage can be accessed at http://rvcog.org/grants-pass-tmdl/.
| B. Prioritize any newly identify areas. | 1. Use established criteria to prioritize identified sites. | 1. Updated summary/list of prioritized sites as needed. | City Staff - Public Works, Parks, Planning, and Engineering, RVCOG, other partners. | Annually | The established prioritization criteria including the scoring metric is included in the prioritization tab. Any new sites scores are on the sites identified tab and highlighted in yellow. In addition, locations of pollinator gardens are being considered and location identified will be added to the map where the coincide with riparian areas.
|  | 2. Field check prioritized areas to verify needs for implementation. | 2. Summary of field checks completed | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually | No field checks were completed this year.
| C. Restore, protect, and plant areas. | 1. Seek opportunities to plant native trees and shrubs in public areas, open spaces, city parks and along streams and rivers. Specific creeks to evaluate include Gilbert Cr., Skunk Cr., Mill Cr., Grouse Cr., Jones Cr., Sand Cr. and the Rogue River along City Park property. | 1. List of areas planted including numbers of trees and shrubs. In addition, create shape files of areas planted. | Public Works Staff, Parks Staff, Public Contracts, Volunteers, County work crews, RVCOG, Partners | Annually | The RC and the City worked with the RRWC, RBP, local schools (Grants Pass High School, RCC, and others) to identify planting opportunities. City crews and contracted labor groups (such as the Josephine County Work Crews), when pruning or cutting along any waterway, continue to protect all vegetation shading the streams or waterways. Tall grass buffers are maintained during the summer season when there is no other streamside vegetation. No planting projects were completed by the RC during the implementation year.
|  | 2. Identify partnering opportunities, for public and private lands, during each plan year by contacting local groups (the Rogue Basin Partnership, Rogue River Watershed Council, Middle Rogue Steelheaders, Roe Motors, Josephine SWCD, Josephine County Public Works, local volunteer groups and schools) and summarizing project opportunities. | 2. Summary of opportunities available. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC and the City worked with the RRWC, RBP, local schools (Grants Pass High School, RCC, and others to identify planting opportunities. Local groups were contacted in person, at events, through mailings, emails, and at meetings. In addition, the RC served on RBP's riparian working group which focuses on restoration needs (including implementation of projects) in the Rogue Basin. Members of the working group include the Freshwater Trust, Rogue River Watershed Council, and Lomakatsi.
|  | 3. Work with local groups to schedule and complete projects annually as time and funding permit. | 3. Summary of projects scheduled and completed including number and locations of trees and shrubs planted. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | No planting projects were completed during the implementation year.
|  | 4. Evaluate funding options for restoring, planting, and protecting priority sites and pursue finding options as time and resources permit. | 4. Summary of funding sources identified, applications submitted, and funding received. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC continues to work as part of the Rogue Basin Partnership to implement a Rogue Action Plan which includes protecting and restoring riparian areas throughout the Rogue Basin. Primary funding for restoration is through grants and volunteer efforts. The City will continue to work with the RC and other groups to submit proposals to OWEB and other programs to fund restoration work. No proposals were submitted or received for planting during the implementation year. The RM continues to work with RBP to develop a Capital Improvement Plan for restoration projects which would includes sites identified as part of the TMDL program.
| D. Riparian Ordinance –Evaluate, strengthen, or develop riparian ordinances as needed (Goal 5) to protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under the City of Grants Pass jurisdiction. | 1. Draft new ordinances or revise ordinance as needed based on recommendations from earlier TMDL reports and/or other programs. | 1. Completed draft ordinance. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations. | The City and RC began a review of existing ordinances region wide and statewide to identify potential models to use. Models included recommendations for ordinances that serve different functions (e.g., salmonid habitat, bird habitat, sediment and nutrient reduction), recommendations for urban areas versus areas outside of urban areas, and what is being done locally, regional, and statewide. The models will be used to update or replace existing ordinances. In Years 3 and 4 , the City will develop a recommended riparian ordinance revision or a revised ordinance through a public process to be incorporated into the public process.
|  | 2. Public notice of new or revised ordinances and Grants Pass review procedure. | 2. Summary of noticing and procedures used to move the ordinance towards adoption. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations. | In Year 3, the City will begin the public process and hold meeting(s) and/or work session to present options to the City Council and the Public. In Year 4, the City will use the recommendations of the public process to finalize revisions to the existing ordinance or replacing the ordinance.
|  | 3. Adopt new ordinances or revised ordinances as needed. | 3. Adopted ordinances or ordinance revisions. | Public Works, Planning and Engineering Staff, Public Safety and Code Enforcement | Pending, based on new Phase II regulations. | To be completed in Year 5.
III. Solar Radiation –Near stream vegetation disturbance - overrun by invasive species. | A. Continue to implement invasive species management programs in public areas. | 1. Manage invasive species in parks and other City owned properties. | 1. Summary of acres of invasive areas treated. | Public Works Staff, Engineering, Planning Staff, Volunteers, Partners. | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event was held at Hog Creek Boat Ramp in May. Attendees and volunteers included local scouts, RBP, community volunteers. City staff and/or contractors also maintains invasives on all City Parks and properties. City activities removed invasives on approximately 3 acres.
|  | 2. Train staff on noxious/invasive weeds including identification and treatment options. | 2. Summary of any training conducted, promoted, or that staff was sent to. | City Staff | Annually
|  | 3 Work with watershed groups to manage invasive species on private land and protect and/or plant native species in riparian areas where invasives are removed. | 3. Number of trees and shrubs planted annually. Number of acres of invasives removed. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, the Freshwater Trust, and others to promote weed related projects including the Annual Weed Pull (Let’s Pull Together), the Weed Wrangle, and on the ground removal projects..
|  | 4. Coordinate invasive weed management activities with the County Weed Management Area. | 4. Activity Summary. | Public Works Staff, Parks Staff, Josephine County Public Works, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | The RC coordinates with the CWMAs (currently coordinated by RBP) regarding activities in both Counties and the City of Grants Pass. The RC is on the CWMA list serve, periodically attends meetings, promotes events, and participates in selected activities. In addition, worked with the CWMA, Josephine County, Grants Pass, and others to promote the Annual Weed Pull (Let’s Pull Together). Participated in discussions with the CWMA, coordinated activities when appropriate, and attended the weed pull. In addition, information on 4 major species of interest that the CWMA are working on was added to the City's TMDL page along with other information, resources, and links for managing invasive plants.
IV. Other Anthropogenic Sources: Urban Runoff – Reduce runoff, promote infiltration and low impact development practices. | A. Promote the use of methods and practices that reduce urban runoff and impervious surface area. | 1. Create or update map locations where low impact development practices are being used or will be used to reduce urban runoff and creation of impervious surface area. | 1. Map of Locations. | Public Works Staff, Planning and Engineering Staff | Annually | The City and RC are working on documenting where locations are using Google Earth and GIS.
|  | 2. Work with the development of the stormwater program (V) to revise codes and ordinances revision to incorporate low impact development practices. | 2. Summary of revised code. | Public Works, Planning and Engineering Staff | Annually - summary after NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 3. Require new construction to minimize impervious surface and treat stormwater onsite using LID techniques or other appropriate methods. | 3. Summary of requirements. | Public Works, Planning and Engineering Staff | Incorporate in V.
V. Other Anthropogenic Sources: Urban Runoff – Stormwater Management Program. | A. Develop a stormwater management program addressing the six elements of Phase II Stormwater Management. | 1. Outline existing programs that meet each of the six minimum control measures for NPDES Phase II Stormwater Management. | 1. Existing program summary. | Public Works, Planning and Engineering Staff | Year 1 | The City and the RC participate in the Regional Stormwater Advisory Team. In addition, elements of the education and outreach programs (e.g., Salmon Watch, the Land Steward Workshop) meet multiple objectives including stormwater. In addition, the Ordinances_Stormwater Sections tab summarizes elements of City codes and ordinances and matrix sections that will contribute to the development of the stormwater program. In 2017 and 2018 a stormwater brochure was developed and printed with Green Street Design for distribution. Copies of the brochure were provided to the City.
|  | 2. Identify gaps, needs, and next steps needed to develop program. | 2. Summary of gaps and next steps. | Public Works, Planning and Engineering Staff | Year 2 | The City is waiting for final guidance from DEQ regarding program development, timelines, and other information from the revised general permit, which once completed, will designated new MS4s (including Grants Pass) and program requirements. The timeline for completion of the general permit has been delayed and subsequently, the timeline for this task is proposed to be changed to later in the implementation schedule to be finalized when the general permit is released.
|  | 3. Develop or adopt a Storm and Surface Water standards manual | 3. Draft manual (year 4) and completed manual (year 5) | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City is currently developing a stand alone City of Grants Pass Stormwater Management Manual with an anticipate delivery of a draft manual in the fall of 2017. Staff will review the draft manual and will send comments back to the consulting engineer. Manual to be completed and adopted in 2018.
|  | 4. Develop a Pollution Prevention/Good Housekeeping Program | 4. Summary of Program | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City will inventory existing work practices and procedures being done by City work groups and compile a list in the annual report starting in Year 3. In Years 3-4, the City will review model programs and evaluate revisions/improvements needed to the existing programs and report on activity. In Year 4-5, the City will develop a pollution prevention/good housekeeping program.
|  | 5. Develop and implement an erosion prevention and sediment control program. | 5. Summary of programs and procedures. | Public Works Staff, Planning and Engineering Staff | Year 1 | All proposed or planned developments within the City of Grants Pass, including the Urban Growth Boundary, are required to submit a detailed "Erosion and Sediment Control Plan" to the city before any construction begins. Plans are review and inspections completed before and during the length of the project. Inspectors have taken trainings in Erosion Control and Prevention provided by RVSS and other APWA Conferences.
|  | 6. Provide incentives to developers and homeowners to install or retrofit landscapes and to provide on-site stormwater treatment and detention. | 6. Summary of incentives | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City will review programs providing incentives and report on activity in Year 3. In Years 3-4, the City will develop a list of projected incentives to provide on-site stormwater treatment and detention. In year 5, the City's Stormwater Management Manual, once adopted will incorporate incentives into codes and ordinances for proper onsite management of stormwater.
|  | 7. Revise and update maintenance program for existing stormwater management structures or features. | 7. Revise and update training and education programs for maintenance and a schedule for inspection and maintenance as needed. | Public Works, Planning and Engineering Staff | Annually
VI. Fecal Sources: Animal waste management – pet, wildlife, and livestock waste. Properly manage animal waste. | A. Provide bags for dog owners to pick up pet waste. | 1. Update inventory of parks / public areas that have pet waste disposal dispensers. | 1. List of parks and public areas with pet waste disposal dispensers | Public Works and Parks Staff | Annually
|  | 2. Identify additional areas where bag dispensers are scheduled to be or have been placed since the previous inventory. | 2. Document number of bags provided and number and location of new bag dispensers in annual report. | Public Works and Parks Staff | Annually
| B. Develop partnerships with SWCDs, ODA, and other groups to work on animal waste management programs in agricultural areas. | 1. Summary of any programs identified addressing animal waste management with landowners, agriculture, ODA, IDs, County programs, and other groups. | 1. Summary of programs | Public Works and Parks Staff | Annually | Programs identified include the Inland Rogue Water Quality Management Plan, local agencies (ODA, SWCDs, OSU Extension) and the Stream Smart Program (http://www.stream-smart.com/making-bear-creek-better/agriculture-and-forestry/). Funding provide by the City supports the development and maintenance of the Stream Smart Program.
|  | 2. Partner with local groups to encourage proper manure, upland irrigation and nutrient management. | 2. Summary of partnerships. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually | Continued to work with ODA regarding resources and recommendations that they have for meeting this task. They recommended working with local SWCD’s and implementing the Inland Rogue Water Quality Management Plan. Referred question to agencies (ODA, SWCDs, OSU Extension) and the Stream Smart Website for more information (http://www.stream-smart.com/making-bear-creek-better/agriculture-and-forestry/).
VII. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | A. Establish and/or refine illegal dumping/illicit discharge detection and elimination (IDDE) program. | 1. Create, adopt, or revise and strengthen IDDE program as needed. The development of program with element V. Development of a Stormwater Management Program. | 1. Summary of IDDE program. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City is waiting for final guidance from DEQ regarding program development, timelines, and other information from the revised general permit, which once completed, will designated new MS4s (including Grants Pass) and program requirements. The timeline for completion of the general permit has been delayed and subsequently, the timeline for this task is proposed to be changed to later in the implementation schedule to be finalized when the general permit is released.
|  | 2. Implement IDDE program | 2. Program implementation summary. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | Anticipated in Years 5 based on completion of VII.A.1.1.
|  | 3. Create, update, or refine storm drain system map for the City. | 3. A summary of the existing status of the storm drainage system mapping including what format it's in, any updates, and if not completed, a general strategy for completing the mapping. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4. | The City's Stormwater Master Plan has been completed and adopted by the City Council. City is in the process of completing a Stormwater Management Manual. Anticipated to be completed and adopted in 2018. GIS map are updated on an ongoing basis as discrepancies are located by field staff or as new structures are installed.
|  | 4. Evaluate the use of stormwater system maps to assist in identifying illegal dumping and sources of bacteria. Revise and/or create maps or use existing maps. | 4. Map identified areas of high bacteria. | Public Works, Engineering and Planning Staff. | Completed after VII.A.3 is completed. | Completed following VII.A.3.3
|  | 5. Track any IDDE concerns reported in the City. | 5. Summaries of any concerns identified, tracked, and/or reported. | Public Works, Engineering and Planning Staff. RVCOG, DEQ, other partners. | Annually | The RC documents calls regarding regional water quality including IDDE and septic systems. No calls were documented this year for septic concerns.
|  | 6. Enforce illegal dumping as identified or found. | 6. Description of enforcement including number of contacts made, warnings issue and fines levied. | Public Works (Drainage and Utilities) and Engineering Staff and Public Safety. | Annually
VIII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | A. Notify DEQ of failing systems when found. | 1. The City of Grants Pass will notify DEQ of failing systems when found. | 1. Summarized referrals. | Public Works (Drainage and Utilities) and Engineering Staff. RVCOG. | Annually | The RC documents calls regarding regional water quality including IDDE and septic systems. No calls were documented this year for septic concerns.
IX. Outreach and Education | A. Continue to implement outreach strategy that addresses water quality parameters in the TMDL. | 1. Review materials (e.g., brochures, activities, web sites) from educational programs. | 1. Summary of review in annual report including examples of materials and/or links. | Public Works and Engineering Staff, RVCOG | Annually | The RC reviews and updates materials from educational programs annually. New materials are incorporated into the Stream Smart website, TMDL websites, hands on displays, posters, and other materials. Examples of materials are in the Stream Smart Tab.
|  | 2. Adopt, customize, and/or develop regional materials from programs reviewed. | 2. Copies of information created, customized, and/or distributed. | Public Works and Engineering Staff, RVCOG | Annually | The City is participating in the StreamSmart Program which provides regional messaging on a number of topics throughout the Rogue Basin. A revised stormwater brochure was completed in 2018 and printed with the Stream Smart logo replacing the list of all communities involved. The logo represents all participants including the City. The logo was also used to promote programs, events, and on other brochures (including the pledge cards in English and Spanish).
|  | 3. Promote local and/or regional success stories as applicable by preparing information for summary on websites and contacting media outlets. | 3. Summary of information on regional projects. | Public Works and Engineering Staff, RVCOG | Annually | Regional success stories are promoted in the media, at meetings, at events, posted on websites including the Stream Smart main page, posts on the Stream Smart Facebook site, RVCOG's, Jefferson Public Radio, the Grants Pass TMDL site, and other websites.
|  | 4. Participate in regional education opportunities with other groups and DMAs in the Rogue Basin. | 4. List of activities. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City through the activities of the RC participates in several regional education efforts annually. Specific examples include the annual Living on Your Land Steward Workshop held at Rogue Community College in Grants Pass for Josephine and Jackson County Residents, participation in the Salmon Watch program, participation in the World Fish Migration Day (new in 2018), and the Stream Smart program.
| B. Hold, participate in, and/or promote annual water quality events. | 1. Update list of annual events related to water quality, riparian planting, the benefits of healthy riparian areas, native plants and other TMDL topics. | 1. Event list or summary of events in annual report. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The annual event list is reviewed annually and updated as needed. In additional, annual events that the City supports by promoting and/or attending are added to the calendar. Events are posted on the Stream Smart, Rogue Basin Partnership, and/or RVCOG event calendars.
| C. Provide citizens, landowners and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. Revise and update list of local agencies, nurseries, and other resources for planting as needed. | 1. Summary of updates and/or updated list of resources including contact information and location. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | The resource list in tab I.A.2 was revised and updated.
|  | 2. Distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | Materials distributed included the Taking Care of Streams in Josephine County, Stream and Wetland Enhancement Guide, Garden Smart Oregon: a guide to non-invasive plants, Rogue Valley Native Plant and Seed Sources, Trees and Shrubs for Attracting Pollinators, and Garden-Worthy Native Trees and Shrubs. Materials were distributed at the City, at meetings, at RVCOGs front counter, and through events (e.g., Land Steward Workshop). In addition, materials are available at and residents were referred to the Stream Smart website, links on Grants Pass's TMDL website (RVCOG), and RVCOG's riparian web pages.
|  | 3. Coordinate partnerships with DMAs and other organizations to provide technical assistance and other resources as needed. | 3. Document technical assistance and resources provided, including the number of any plants distributed and associated planting locations. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually | Partnered with other DMAs and organizations including the Land Steward Workshop and World Fish Migration Day with the Bear Creek Ms4s, the Stream Smart Program with other TMDL communities, and distributing materials in the City and online.
| D. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Continue to target areas of high animal usage including public areas near waterways and dog oriented businesses. | 1. Activity summary in annual report. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City has signs in conjunction with their dog parks and pet waste stations. In addition, the RC has referred people to information on the Stream Smart website including the Poop Pledge. Additional information in English and Spanish on the Stream Smart Program and other water quality topics including animal waste was available at the Stream Smart cart located in the Rogue Valley Mall and at events throughout the County including the Land Steward Workshop and World Fish Migration Day which were both held in Grants Pass..
|  | 2. Collect, develop, and/or distribute brochures, pamphlets and other materials to target areas. | 2. Documentation of materials distributed. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually | The City has signs in conjunction with their dog parks and pet waste stations. In addition, the RC has referred people to information on the Stream Smart website including the Poop Pledge. Additional information in English and Spanish on the Stream Smart Program and other water quality topics including animal waste was available at the Stream Smart cart located in the Rogue Valley Mall and at events throughout the County including the Land Steward Workshop and World Fish Migration Day which were both held in Grants Pass..
| E. Provide outreach and technical assistance to private landowners and the public above the removal of invasives and weed control. | 1. Work with the Josephine County Weed Management Area (CWMA), O.S.U. Extension, and/or other groups working on weeds to provide technical assistance, educational opportunities, and/or materials on managing invasive weeds. | 1. Summary of activity with groups including any meetings attended, materials collected and distributed, contacts made, and documentation of any assistance provided. | Public Works and Engineering Staff, RVCOG, CWMA, OSU Extension, other local groups | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event held at Hogs Creek in May. Participated in discussions with the CWMA and coordinated activities when appropriate. In addition to the RC and the City referring residents to the CWMA, OSU Extension, and SWCD's, and information on noxious weed management on the City's TMDL page, the program has several brochures that provide guidance for invasive species removal (Weed Invasion Insert, Oregon Smart Garden, and BLM's "Noxious Weeds are Pretty, But..."
|  | 2. Promote and/or support activities for the public to participate in opportunities to learn about weeds and participate in training and events related to invasive weed control. | 2. List of events promoted, supported, and/or attended by staff or a city representative (e.g., RVCOG). Potential events include the Annual Josephine County Weed Pull, and OSU's Land Steward workshops. | Public Works and Engineering Staff, RVCOG, CWMA, other local groups | Annually | Worked with the CWMA, Josephine County, Grants Pass, RBP, and others to promote the Annual Weed Pull (Let’s Pull Together) Event held at High Creek Boat Ramp in May and the Weed Wrangle in August. Participated in discussions with the CWMA and coordinated activities when appropriate.
| F Staff Training | 1. Train staff as needed on topics related to TMDL Implementation. (Include Management Staff and Elected Officials) | 1. List of how training was conducted and frequency. | Public Works, Planning, Building and Engineering Staff | Annually | Topics/presentations are quarterly TMDL meetings included - the Swim Guide and Bacteria Monitoring, the Pesticide Stewardship Partnership (PSP), Groundwater (Assessment Units and local study results), ODA's Strategic Implementation Areas for Wagner Creek and Neil Creek. Specific training examples that were held that were attended by DMAs included the Salmon Watch Instructor Training (September 14th), the HazMat Spills training organized by RVSS (October 3rd), and EcoBiz (June 14th and 15th). The EcoBiz training focused on Fleets and Auto Service Stations so it was more Phase II focused. However, the program can be expanded to certify landscapers which would TMDL related. In addition, with the RC attending the training, businesses in Grants Pass could be inspected by and submitted to the program by the RC. A number of online webinars, local, regional, and statewide trainings were also promoted at TMDL meetings and through TMDL distribution lists by the RC, DMAs, and partners (e.g., RVSS).
X. Regional Water Quality Coordination | A. Continue participation in the TMDL program. | 1. The City of Grants Pass will continue participation in the TMDL program. | 1. Attendance (in person, phone or video conferencing if available) at quarterly meeting and other meetings as requested. | Public Works, Planning, Building and Engineering Staff | Annually | RVCOG worked with DEQ to coordinate quarterly meetings on July 19th and October 18th, 2017, January 31st, and April 18h, 2018. Funding provided by the City supports the TMDL meetings. In addition, Grants Pass staff attended meetings in July, October, January, and April.
XI. Funding | A. Evaluate the costs of program implementation. | 1. Establish costs of program implementation for the next plan year and identify funding sources as needed including staff time, grant funding, and other resources. | 2. List program costs and sources (e.g., staff time, direct funding, grants, etc.). | Public Works, Planning, Building and Engineering Staff | Annually | RVCOG provides the City with annual costs for continued assistance. The City has set aside approximately $15,000.00 per year for implementation assistance. The City contracted with RVCOG to provide support. Details of the specifics are in the RC Contract detail tab. Changes were made in 2017 to the contract to align the RC deliverables and contract with the Tidal year. The City is planning to contract with RVCOG to complete future activities. In addition, implementation in the City the Streets and Drainage Superintendent (10% time), Maintenance personnel (15% of time). The City has also hired a consulting firm (Keller and Associates) to help update it's stormwater master plan. The City has also negotiated with GPID to design a plan to design a plan to work together on stormwater. The City has continued work on establishing a stormwater utility.
| B. Identify program funding opportunities. | 1. Evaluate existing resources available to begin program implementation. | 1. Summary of existing resources used. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The City contracts with RVCOG annually for coordination and implementation services ($15,000.00). Additional funding has been provided through grants (Meyer, Gray Family, and Jackson SWCD ($5,000.00)and from RBP ($1,000.00).
|  | 2. Provide an inventory of funding, potential Regional Program grants. | 2. List of identified funding sources and deadlines provided to The City of Grants Pass and other agencies. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The RC has participated in Regional meetings including the Rogue Basin Partnership representing urban interests (TMDL and NPDES Stormwater Phase II). RBP works in partnership with local watershed councils Rogue River Watershed Council, NGOs (the GEOS Institute), and others (Medford Water Commission, Jackson SWCD )to develop a process for prioritize restoration and other projects across the Rogue Basin. A major goal of the program is to attract outside funding from foundations and other large investors to implement regional projects. Working groups, including the riparian working group on which the RC participates, are working on packaging projects together related to TMDL including restoration and monitoring.
|  | 3. Collectively (regionally) apply for funding for implementation and region-wide projects. | List of participation in regional implementation opportunities. | Public Works Staff, RVCOG, Local Watershed groups | Annually | The RC worked with RBP to apply for and secure funding from the Meyer Memorial Trust for regional education and outreach programs across the Rogue Basin including Weed Pulls, Creek Clean-ups, and education symposiums. The RC is continuing to implement deliverables of the grant. In addition, the RM applied to both the Jackson SWCD (Fall 2017) and the Grey Family foundation (Fall of 2018) for Salmon Watch. Classes are planned in Grants Pass for 2018.
|  | 4. Document any funding and/or in-kind support for projects or partner projects. | List of funding and in-kind support. | Public Works Staff, RVCOG, Local Watershed groups | Annually | Funding activity including partner support is tracked using TMDL tracking forms, program spreadsheets, and other formats. In-kind support from grants and staff time is estimated at $15,000.00. Collectively, the Salmon watch grants were over $20,000.00 with an estimated $4,000.00 supporting classes for Grant Pass Schools and/or locations.
XII. Monitoring and Reporting | A. Use the matrix as a template to track the implementation plan. | 1. Compile information from completed activities into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually | Tracking of activities is done by the RM regularly using calendars, spreadsheets, attendance sheets, manual counters, log sheets, reports, and other methods. Additional detail is provided in reports, project summaries, online, and invoices. Details are included on separate tabs and/or in the reporting columns as needed. In addition, selected deliverables including completed matrixes are posted on the RVCOG, Grants Pass TMDL, and/or Stream Smart website.
| B. Submit annual reports to DEQ. | 1. Submit annual reports to DEQ. | 1. Completed annual reports submitted to DEQ by September 30 of each year, reporting on implementation actions for the July 1-June 30 plan year. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually, November 1st of each year. | Completed. The matrix was submitted to DEQ and a detailed report containing all supplemental pages can be accessed on the Grants Pass TMDL Homepage under RVCOG's website at http://rvcog.org/grants-pass-tmdl/.
| C. Use existing programs to track program effectiveness. | 1. Work with DEQ, RVCOG, and other DMAs to evaluate methods for evaluating and tracking program effectiveness. | 1. Summary of methods evaluation. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually | The RC and the City track effectiveness through the attendance at events/workshops/trainings/meetings/etc, number of visits to the websites, number of brochures handed out, surveys, number of trees and shrubs planted, number of stream miles or acres protected, amount of invasive species managed (acres), mapping, and other methods. The Stream-Smart website had 3,705 visitors. Please see the information on the Stream Smart Web Stats Tab for the visitor breakdown and most visited pages. Other statistics are tracked in the activity log tab. Effectiveness is measured by meeting specific deliverables/milestones and other implementation plan targets. In year 5, the RC and City will review previous reports to see how milestones (number of people reached, brochures distributed, etc.) have changed from year to year and overall.
|  | 2. Work with DEQ, RVCOG, and other DMAs to use existing programs (DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. | 2. Summary of regional water quality. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually | The RC is participating as part of RBP's monitoring work group which is evaluating monitoring across the Rogue Basin. A long term goal of the working group is to use the data to create a watershed report card which will summarize watershed conditions. The report card may be able to be used to evaluate program effectiveness related to the water quality elements of the report. In addition, the Bear Creek DMAs applied for and received a grant to analyze monitoring data to evaluate the effectiveness of their TMDL implementation program. Results of the analysis will be reviewed by the City for potential adaptation in future years of the TMDL Implementation program..
| D. Adaptive Management Plan. This is an ongoing plan and modifications and adjustments will take place. | 1. Modify plans as needed. | 1. Summary of any revisions to Water Quality Implementation Plans. | Public Works, Planning, Engineering Staff, RVCOG, other DMAs. | Annually | Any changes in terms of requests for annual plan modifications is included in the reporting column. Previous requested changes were left in the columns in addition to any new requested changes..
Note on C27: gstabach:III.A.3 and II.A.4 were the same so I deleted one.

## I.A.2
Community Resources List Water Quality, Riparian Planting, and Restoration Projects- Grants Pass Updated June 2017
Water Quality, Planting, and Restoration Partners | Contact(s) | Contact Number | Address | Website | Email | Subject(s)
Technical Assistance, Forums, Volunteers
Josephine County
Rogue Valley Council of Governments | Greg Stabach, Craig Tuss, Amie Siedlecki | (541) 664-6674 | 155 North First Street | www.rvcog.org | gstabach@rvcog.org | Monitoring, restoration, planting designs, invasive species management, permitting, contract/contractor management, plant selection, maintenance, technical assistance, project development, grant/funding assistance, Stream Smart, Salmon Watch, educational programs.
OSU Extension (serves both Counties) |  | (541) 476-6613 | 215 Ringuette Street | http://extension.oregonstate.edu/ | Varies | Forestry, Training, Riparian Planting, Invasive Species Control, Rural Landowners
Rogue Community College Redwood Campus |  | (541) 956-7500 | 3345 Redwood Highway | http://www.roguecc.edu/ Resource Directory - http://www.roguecc.edu/AboutRCC/Contacts.asp |  | Sustainability Club, Education, Volunteers. Also has been the host of the Land Steward workshop in 2015 and 2016.
Siskiyou Field Institute | Sarah Worthington | (541) 597-8530 | P.O. Box 207/1241 Illinois River Road, Selma, OR. 97538 | http://www.thesfi.org/Page.asp?NavID=108 | youthprograms@thesfi.org | Education, Events, Trainings
Josephine County Fairgrounds | Wes Brown | (541) 476-3215 | 1451 Fairgrounds Road Grants Pass, OR. 97527 | http://www.co.josephine.or.us/Calendar.asp?SectionID=146 | wbrown@co.josephine.or.us | Varies.
Rogue Basin Partnership | Greg Weber |  | P.O Box 1214 Medford, OR. 97501 | http://www.roguepartners.org/ | greg.weber@roguepartners.org | Regional collaborative implementing the Rogue Basin Action Plan and other projects throughout the Rogue Basin.
Oregon Stewardship | Jim Hutchins, Eric Dittmer | (541) 770-2703 | 4015 S. Stage Road Medford, OR. 97501 | http://www.oregonstewardship.org/ | jim@oregonstewardship.org | Contractor for invasive species management and riparian restoration programs. Organizations uses local students and funding is provided to the studnets via scholarships.
Jackson County Weed Management Area | Greg Weber, RBP | (541) 690-8800 | P.O Box 1214 Medford, OR. 97502 | http://www.roguepartners.org/ | info@roguepartners.org | Meetings vary. Support annual weed pull events.
Josephine County Weed Control Program | Josephine SWCD | (541) 474-6840 | 576 NE E Street Grants Pass, OR. 97526 |  | joswcd@charterinternet.com
Josephine County Weed Management Area | Greg Weber, RBP | (541) 423-1381 | P.O Box 1214 Medford, OR. 97501 | http://rogueweeds.info/ | thera@roguepartners.org | Meetings vary. Support annual weed pull events.
Rogue River Watershed Council | Brian Barr, Executive Director | (541) 664-1070 ext. 433 | 89 Alder Street Central Point, OR. 97502 | http://www.rogueriverwc.org/ | bbarrrrwc@gmail.com | Local Watershed Council that is the consolidation of four councils including the Stream Restoration Alliance that covers Grants Pass.
Rogue Basin Partnership | Greg Weber, RBP | (541) 690-8799 | P.O Box 1214 Medford, OR. 97501 | http://www.roguepartners.org/ | info@roguepartners.org | Regional collaborative implementing the Rogue Basin Action Plan and other projects throughout the Rogue Basin.
Lomakatsi | Niki Del Pizzo | (541) 488-0208 | 90 Van Ness Avenue, Ashland | http://www.lomakatsi.org/ | info@lomakatsi.org | Riparian Restoration, Fuels Treatment, Education, Nurseries with native plants.
Worksource Rogue Valley | Christie Lawson, Crew Field Specialist Medford and Grants Pass | (541) 621-2619 | 1569 Northeast F Street, Grants Pass, OR. 97526 | www.jobcouncil.org | christiel@jobcouncil.org | Provide labor for invasive species management and restoration projects.
Jackson County
Rogue Valley Council of Governments | Greg Stabach, Craig Tuss, Amie Siedlecki | (541) 664-6674 | 155 North First Street | www.rvcog.org | gstabach@rvcog.org | Monitoring, restoration, planting designs, invasive species management, permitting, contract/contractor management, plant selection, maintenance, technical assistance, project development, grant/funding assistance, Stream Smart, Salmon Watch, educational programs.
Bear Creek Watershed Education Partners (BCWEP) | Greg Stabach | (541)-423-1370 | P.O. Box 3275 Central Point, OR. 97502 | http://www.bcwep.org/ | bearcreekwatershed@gmail.com | Volunteers for planting and restoration, Education and Outreach. Primarily in Bear Creek, but members are willing to travel to other locations. RVCOG is the contact for the group. Former members volunteer for Salmon Watch, educational events, and other programs.
North Mountain Park | Jennifer Aguayo | (541) 488-6606 | 620 North Mountain Ave Ashland | http://www.northmountainpark.org/ | jennifer.aguayo@ashland.or.us | Varies per season. Lending Library, nature programs and workshops, stormwater features on-site, trails, riparian restoration, invasive species control, water quality, biology, native plants, gardens.
Coyote Trails Nature Center | Molly Kreuzman | (541) 772-1390 | 2931 South Pacific Highway, Medford | http://www.coyotetrails.org/index.php/ct-nature-center |  | Education programs. Riparian planting, water quality, salmonwatch, low impact development (on -site), facilities and labor/participation for workshops and programs.
Rogue Basin Partnership | Greg Weber | (541) 690-8799 | P.O Box 1214 Medford, OR. 97501 | http://www.roguepartners.org/ | info@roguepartners.org | Regional collaborative implementing the Rogue Basin Action Plan and other projects throughout the Rogue Basin.
Rogue River Watershed Council | Brian Barr, Executive Director | (541) 664-1070 ext. 433 | 89 Alder Street Central Point, OR. 97502 | http://www.rogueriverwc.org/ | bbarrrrwc@gmail.com | Local Watershed Council that is the consolidation of four councils including the Stream Restoration Alliance that covers Grants Pass.
Oregon Stewardship | Jim Hutchins, Eric Dittmer | (541) 770-2703 | 4015 S. Stage Road Medford, OR. 97501 | http://www.oregonstewardship.org/ | jim@oregonstewardship.org | Contractor for invasive species management and riparian restoration programs. Organizations uses local students and funding is provided to the studnets via scholarships.
Scienceworks |  | (541) 482-6767 | 1500 East Main Street, Ashland | http://www.scienceworksmuseum.org/ | rachel@scienceworksmuseum.org | Current location of Earth Day Celebration. Have had programs in the past addressing water quality, wetlands, and native plants including hands-on activities and speaking forums.
Southern Oregon University |  |  | Southern Oregon University, Science Hall, Ashland | http://www.sou.edu/ |  | Groundwater, GIS, GPS, monitoring, student projects.
Lomakatsi | Niki Del Pizzo | (541) 488-0208 | 90 Van Ness Avenue, Ashland | http://www.lomakatsi.org/ | info@lomakatsi.org | Riparian Restoration, Fuels Treatment, Education, Nurseries with native plants.
Worksource Rogue Valley | Multiple Contacts | (541) 776-5100 | 673 Market Street Medford, OR. 97504 | www.jobcouncil.org |  | Riparian Restoration and planting, site maintenance, labor for projects, programs should have an educational component for Job Council Participants.
Jackson Soil and Water Conservation District | Kora Mousseaux | (541) 734-3143 | 573 Parsons Drive, Medford | http://www.jswcd.org/Index.asp |  | Programs with rural homeowners and the agricultural community. Education and outreach programs. Provide implementation assistance of the Agricultural Water Quality Management Plan.
Randy White
Jackson County Community Justice | Shane Hagey, Director | (541) 774-4900 | 1101 W. Main St., Suite 101, Medford, OR. 97501 | http://www.co.jackson.or.us/Page.asp?NavID=187 | HageySL@jacksoncounty.org | Crews are available to provide service for projects. Crews have been used for site preparation, invasive species removal, and limited site planting.
OSU Extension SOREC (Southern Oregon Research and Extension Center) | Max Bennett, Rachel Werling | 541-776-7371 | 569 Hanley Road Central Point, OR 97502-1251 | http://extension.oregonstate.edu/sorec/ |  | Forestry, Training, Riparian Planting, Invasive Species Control, Rural Landowners
Plants and Seeds
Althouse Nursery |  | (541) 592-2395 | 5410 Dick George Road, Cave Junction, OR. | http://www.althousenursery.com/Welcome.html | althousenursery@frontiernet.net | The nursery may have been sold and the previous owners are retired.
Forest Farm |  | (541) 846-7269 | 990 Tetherow Road, Williams, OR. 97544 | http://www.forestfarm.com/ | plants@forestfarms.com
Plant Oregon | Dan Bish | (541) 535-3531 | 8651 Wagner Road, Talent, OR 97540 | www.plantoregon.com | dan@plantoregon.com
Shooting Star Nursery |  | (541) 840-6453 | 3223 Taylor Road, Central Point, OR 97502 | http://roguevalleynursery.com/ | info@roguevalleynursery.com | Nursery also offer classes.
Siskiyou Rare Plant Nursery |  | (541) 535-7103 | 2115 Talent Ave, Talent, OR. 97540 | http://siskiyourareplantnursery.com/index.aspx | customerservice@srpn.net
Silver Falls Seed Company |  | (503) 874-8221 | P.O. Box 8851 5648 Evans Valley Loop Silverton, OR. 975381 | www.silverfallsseed.com
Sunmark Seed Company |  | 1-888-214-7333 | 2255 NE 19th Ave Portland, OR. 97230 | www.sunmarkseeds.com
Internet Database |  |  |  | http://www.nwplants.com/information/resources/nurseries.html
Local Contacts
City Arborist, Medford |  | (541) 774-2690
Other Groups

## Implementation Schedule
Implementation Activity | July | August | September | October | November | December | January | February | March | April | May | June
TMDL Implementation Year Begins | 1st
Quarterly TMDL Meetings
Quarterly SWAT Meetings
Salmon Watch
Annual Weed Pull
Annual Reports Due |  |  |  |  | 1st
Weed Management
Riparian Planting
Irrigating/site watering
CWMA Meetings
Web Updates, Postings
Reviewn and Update Annual Event List
Promoting events, trainings, workshops
Annual Schedule Review
Annual Resource Review (staffing, contracting, other resources)
Annual Deliverable Review
TMDL Implementation Year Ends | [11 empty] | 30th

## Activity Log
Summary Information |  |  |  | Statistics/Tracking Variables
Activities
Date | Event/Activity | Time and Location (if needed) | Description | Number of People | Number of Brochures Distributed - includes stickers and other goodies as well | Funding Leveraged | Planting/
2017-07-03 | Salmon Watch Grant submitted | N/A | Funding for Salmon Watch submitted to the SWCD. Due to a clerical error, the funding request was not included in the packet to the grant review committee, so it will be submitted in August.
2017-07-12 | Stakeholder Public Forum (Stormwater - Salem) | 9:00 a.m. to 3:00 pm | Attended the clean rivers coalition strategy meeting to discuss statewide programs on educational activities related to urban runoff and pollutants.
2017-07-13 | RBP Board Meeting | 2-4 pm at Jackson SWCD
2017-07-19 | SWAT Meeting | 10 to 11:30 at RVSS | Quarterly Stormwater Advsiory Team Meeting. Reported on all activities related to education and outreach including Stream Smart and programs where TMDL and Stormwater overlap.
2017-07-19 | TMDL Meeting | 1 to 3 pm | Quarterly regional TMDL meeting. Attendance record attached as a separate tab.
2017-07-20 | RBP EAC Meeting | 12 to 130 pm
2017-08-02 | SOU Class. | 7-830 pm and sou higher learning center in medford | Served on a panel for a nonprofit management class talking about partnerships, grants writing, community work
2017-08-14 | August Institute Teacher Workshop |  |  | 22
2017-08-15 | August Institute Tabling Session - Salmon Watch |  |  | 14
2017-08-17 | Salmon watch meeting
2017-08-30 | Salmon Watch Planning Meeting
2017-09-07 | Salmon Watch Check in Meeting
2017-09-14 | Salmon Watch Instructor Training | 2-5 pm at Bear Creek Park |  | 21
2017-09-20 | Stream Smart Advisory Committee Meeting | 9-11 a.m. |  | 5
2017-09-21 | RBP Board Meeting | 2-4 pm at Jackson SWCD
9/26/2017- 10/30/18 | Salmon Watch Classes | Varies | Program Statistics for all Salmon Watch Classes. Conducted 23 field days with 39 classes and reached over 1000 students. See Salmon Watch Summary tab for informaiton on Program. | 1145 | 55
2017-10-07 | Salmon Festival |  |  | 178 | 25
2017-10-18 | TMDL Meeting
2017-11-08 | Clean Rivers Coalition Meeting | 10:30-3:30 pm | Attended the clean rivers coalition meeting to discuss statewide programs on educational activities related to urban runoff and pollutants.
2017-11-13 | Facebook post - oil sheen
2018-01-08 | Annual Meeting with SWCD (and RRWC) | 11:30-1:00 pm in Central Point | Met with all staff from the SWCD (except office and Randy) and Sarah, Alexis, and Donna from RRWC to talk about project needs, collaboration, working together, and sharing information and resources. Specific projects included stream smart, brownfields, drones, monitoring, stormwater, restoration, and vernal pools. | 9
2018-01-09 | Brochure Distribution |  |  | 8 | 100
2018-01-10 | Stream Smart Meeting | 9-11 RVCOG | Stream Smart meeting. Handed out brochures to medford and ashland | 6 | 150
2018-01-11 | RBP Board Meeting | 2-4 pm @SWCD
2018-01-17 | SWAT Meeting
2018-01-31 | Regional TDML Meeting
2018-03-02 | RBP Board Retreat
2018-03-08 | RBP Board Meeting | 2-4pm
2018-03-08 | SOU Intern Meeting | 8-9:30 am | Met with SOU intern to discuss summer/fall internship for 2018.
2018-03-15 | GRD removal presentation | 1:30 pm to 3 pm | Presentation to 42 land lab students from Crater Rennaissance Academy | 42 | 10
2018-03-19 | GRD removal field trip | 12:45 pm to 3:30 pm | Field visit to the former GRD site to look and talk about the removal, issues around the removal, restoration actions taken to address the issues, and importance of the Rogue and water quality.. | 37
2018-03-29 | RBP Monitoring Meeting | 9 am to 11 am
2018-04-07 | World Fish Migration Day (RRWC) | 10 am - 3 pm | Rogue River Watershed Council sponsored World Fish Migration Day event at North Highland Middle School in Grants Pass | 11 | 24
2018-04-12 | Water Quality Article Mail Tribune
2018-04-12 | Storm Drain Run | 8:00 am - 2:30 pm
2018-04-14 | Land Steward Workshop | 7:30 a.m. through 3:30 p.m. | Annual workshop for Jackson and Jospehine County residents participating in the Land Steward Program. | 87
2018-04-18 | Regional TDML Meeting
2018-04-21 | Rogue Valley Earth Day | 11:00 a.m. to 4:00 p.m. | Annual event for all ages to learn about environmental stewardship. | 170 | 33
2018-04-24 | RVCOG Quarterly Meeting | 9:00 am - 10:00 am
2018-04-26 | Cascade Christian Field Day | 9:00 am - 3:00 pm | 80 students from Cascade Christian participated in restoration activities and water quality testing. Featured news story shown on Channel 12 News. | 80
|  |  |  | 1835 | 397 | Totals

## Events, Activity Photos
Activity Photos
Salmon Watch Class - Salmon Section | Stream Smart Display Cart | Rogue Basin Stream Smart Logo
Riparian Habitat Activity used for the World Fish Migration Day

## Ordinances_Stormwater Sections
Existing Stormwater and TMDL related ordinances
Most of the relevant ordinances in the Development Code are located in Article 24: Environmental Design Standards. This section includes Water Quality Regulations (24.330), Water Quality Standards (24.340), Stream Corridor Setbacks (34.341), Preservation of Riparian Vegetation (24.343), Wetlands (24.345 and 24.500), and Stormwater Detention and Retention (34.347). Article 13: Special Purpose Districts also has provisions for Slope Hazard Districts (13.100) and Sections 13.133 and 13.143 address Erosion Control for developments in Steep slope areas.
TMDL Matrix/Program Implementation (program proposed to be developed)
The TMDL implementation plan contains many sections that once completed form the framework for a stormwater management program. Relevant sections are summarized below:
Annual/Review Updates
Source | Strategy | Specific Actions | Notes | RC | City
I | A, B | All | Outlines existing resources, regulations (ordinances), and responsibilities for implementing stormwater programs in the City. It also identifies begins the review and revision procedure for ordinances and updating the matrix. | X
IV | A | All | Address urban runoff, ways to reduce impervious surface areas, and low impact development. Includes mapping LIDS and BMPs, revising codes and ordinances to incorporate LID's in conjunction with the development of the SW program (V) and requiring new construction to use LIDs and other appropriate management methods. | X
V | A | 1 through 7 | Portion of the TMDL implementation plan that address developing a stormwater management program addressing the six minimum control measures (elements). Includes pollution prevention/good housekeeping, adopting or developing a design manual, incentives for homeowners, and maintenance of features. Adaptive management may be needed to adjust the program to meet the elements of the new General Permit. | X
VII | A | 1 through 6 | Establishes and/or refines illicit discharge detection and elimination programs (IDDE). | X
IX | A, B, F | All | Outlines education and outreach programs including some public participation and involvement (events) and training of staff. | X
XI | A, B | All | Outlines establishing funding for program implementation which could include stormwater utilities. | X
XII | A,C,D | All | Outlines tracking and reporting requirements for the TMDL program which includes stormwater. Established Phase II programs have strict tracking and reporting requirement. The TMDL tracking and reporting can provide a basis for the MS4 program. | X

## Prioritization Criteria
Critical Factor | Explanation of Matrix critical factors: | Score |  |  | Score
|  | High | Medium | Low | High | Medium | Low | Not Applicable/No Score
Accessibility | Includes physical constraints to land: willing landowner (including agencies), physical barriers (e.g., fencing and vegetation), and accessibility (equipment, maintenance, plant deliveries, etc.). | Lots of constraints and barriers to completing the project. | Moderate constraints. | Easy access for people, equipment, and vehicles. | 1 | 2 | 3 | 0
Partner Interest | Indicated a willing partner/expressed interest in a project by landowner or agency/ organization/ school. | Willing partner, organized group that owns or has access to the site. | Willing partner. Limited access to the site. | No partners. | 3 | 2 | 1 | 0
Coordination with existing plans | Has the site been recommended for restoration - plans may include watershed assessments and action plans, parks plans, Rogue Restoration work, the WISE project, Freshwater Trust, and other groups. | Yes, as a high priority in one or more plans. | Moderately rated site in plans and assessments. | No or rated as low/limited potential. | 3 | 2 | 1 | 0
Habitat Enhancement Need | Includes both terrestrial and aquatic habitat- increase in diversity of species, erosion control, bank stability, channel undercutting, recent disturbance, large woody debris, reduction in algal growth or temperature, overstory building for shade, etc. | Site has a high need and significant potential for restoring habitat. | Site has some need and potential for restoration. | Site is in good shape. No/Limited enhancement needed. | 3 | 2 | 1 | 0
Irrigation availability | Assessment of watering needs including accessibility to an available water source for irrigation. | Site has irrigation or a water supply in close proximity. | Water is available through a limited duration water right or a supply that is located far away or requires regular site visits (e.g., watering truck or crew). | Limited or no water availability. | 3 | 2 | 1 | 0
Restrictive Site Conditions/ Limitations | Assessment of site conditions that would reduce the survival of seedlings including: soil conditions, invasives, existing uses of area and potential for vandalism. | Lots of constraints and difficult site conditions identified. |  | Limited/no constraints. | 1 | 2 | 3 | 0
Key habitat area | Includes assessment of connectivity potential to other habitat areas and T&E spp. Presence, sensitive wetland feature or adjacent to sensitive area including a cultural resource area. | Key/critical habitat. High value. | Important habitat, disturbed, moderate value. | Low value. Highly disturbed site. | 3 | 2 | 1 | 0
Flood Abatement/ Storage | Assess areas potential for flood storage and abatement. | High potential, floodplain connection, existing storage provided. | Moderate storage provided. | Low storage. Low/limited connectivity (e.g., incised, narrow channel). | 3 | 2 | 1 | 0
Site preparation | How much preparation will be needed before the site is planted (blackberry removal, soil amendments, etc) prior to plantings? | Significant preparation needed. Lots of invasives, soil amendments needed, tough site conditions. | Some preparation needed. | Minimal preparation work needed. | 1 | 2 | 3 | 0
Proximity to stream/river | Will the planting shade the stream or provide riparian protection (e.g., buffers)? | Yes. Planting of the site will result in increasing the overstory vegetation and the aspect will greatly reduce the amount of direct solar loading to the stream. |  | Planting will provide minimal shade benefits only. | 3 | 2 | 1 | 0
Fire Risk | Is area a potential fire risk? Dead trees, invasive plants, dense small diameter forest, etc. This does not include areas that were already burned. | High fire risk. Lots of invasive species, no/low water, lots of fire prone species, close to source area (e.g., I-5, Greenway). High fire occurrence history. | Moderate fire risk. | Low fire risk. | 1 | 2 | 3 | 0
Invasive species presence | Does the site have a high percentage of invasive species? | Dominated by invasive species (<50%). | 25-50% invasives. | <25 % invasives. | 1 | 2 | 3 | 0
Potential/Existing Recreational Area | Is there existing recreation at or near the site? Is there the potential to incorporate new recreation/recreational access to the site? | Yes. Existing trail or greenway. | Some. Opportunity for future connection/path. | No. | 3 | 2 | 1 | 0
Potential for adoption of site monitoring/ maintenance | Is there an established or the potential for an established entity to conduct site maintenance and monitoring? Entities could be local schools, watershed groups, watershed councils, Municipalities, the Job Council, contractors, and others. | Yes. | There are potential groups, but no agreements are in place to complete monitoring and maintenance. | No. | 3 | 2 | 1 | 0
Shading Potential/Shading Needs | Is there an identified shading need at the site? Identified need could be from a watershed survey, visual surveys, air photos, shade surveys, etc.? | High potential for shade (shade potential). | Moderate shade potential. | Low shade potential (existing | 3 | 2 | 1 | 0
Thermal Credits Available | Is there potential for thermal credits to be available for the project and funding provided by the Freshwater Trust? | Yes. |  | No. | 3 | 2 | 1 | 0
RBP Action Plan Priority Watershed | Is the planting project located in or a near an identified priority watershed in the RBP Action Plan? | Yes | Within 0.5 mile | Within 1 mile | 3 | 2 | 1 | 0
In or Near a RBP Confluence Area | Is the planting project located in or a near an identified confluence area in the RBP Action Plan? | Yes | Within 0.5 mile | Within 1 mile | 3 | 2 | 1 | 0
RBP Action Plan Priority Corridor | Is the planting project located in or a near an identified priority corridor in the RBP Action Plan? | Yes | Within 0.5 mile | Within 1 mile | 3 | 2 | 1 | 0
Other TMDL Parameters or Need Addressed | Are there other pollutants or TMDL parameters that will benefit by restoring or protecting this site? e.g., wetland function. Are there other needs addressed? E.g. education and outreach, demonstration site, BMP/LID location, etc. | Yes. |  | No. | 3 | 2 | 1 | 0
Other potential parameters to add
Aspect | Sites that will block southern exposure to afternoon sun in the summer are higher priority.
Planting plan completed? | Is there a planting plan completed for the site, so the site is essentially ready to go?
Proximity to another restoration site, planting project, or healthy riparian zone. | If there is a site nearby or adjacent that the project would connect to, the potential benefits increase resulting in a higher overall benefit for the project.
Public Land | Is the site located on public land?
Public benefit | Does the project benefit the public?
Regulatory Compliance | Does the project meet the needs of multiple regulations?
Funding | Is there funding available for the project? E.g., smaller projects may be achievable with the amounts available.
Stream/River Size | Is the flow or size of the stream greater than some set threshold? 50 feet? 200 cfs?
Other?

## Prioritized Sites
Bear Creek and Rogue Basin Riparian Planting Prioritization Matrix---DRAFT May 2012-Grants Pass Sites
Planting sites are prioritized based on a rating system of L- Low (1 point), M- Medium (2 points) and H- High (3 points). 0 points are used where criteria are not applicable. U indicates unknown. Field verification is required.
Indicates new sites added since previous report.
*For restrictive site conditions, a yes and a high rating equates to a low score(1).
**Unknown attributes are assigned a score of 0 and need to be evaluated as part of the field surveys.
Number | Planting/Restoration Site | Waterbody: See Codes Below | DMA(s): See Below | Site code | Accessibility | Partner interest | Coordination with exist. plans | Habitat enhancement need | Irrigation availability | Restrictive Site Conditions/Limitations* | Key habitat area | Flood abatement/ storage | Site preparation minimal | Proximity to stream/ wetland | Fire risk | Invasive Species presence/ potential | Potential/ existing recreational area | Potential for adoption of site monitoring/ maintenance | Shade Potential/Shading Need | Thermal Credits Available | Other TMDL Parameter Addressed | RBP Action Plan Priority Watershed | In or Near a RBP Confluence Area | Priority Corridor | Total Points | Notes
1 | Rogue River next to proposed dog park location. | RR | GP | GP-RR-DP | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 0 | 3 | 0 | 0 | 3 | 43 | Dog park is unlikely to occur anytime in the near future. Planting would be habitat building and for a buffer between the park and the Rogue River.
2 | Rogue River next to City Water Plant | RR | GP | GP-RR-WWTP | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 2 | 0 | 0 | 3 | 45 | Canopy Cover is needed for stream shading.
3 | Skunk Creek near Skate Park | O | GP | GP-SC-1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 34 | The site will be difficult to plant in most places due to fill on site, steep bands, water, invasives species, and other factors. The site needs to be subdivided into several sub sites with individual planting prescriptions for the sites.
4 | Skunk Creek Tributary near Skate Park | O | GP | GP-SCT-1 | 3 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 0 | 0 | 0 | 31 | Skunk Creek Tributary near Skate Park
5 | Skunk Creek mainstem daylighted section north of Skate Park. | O | GP | SCCK-1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 0 | 3 | 0 | 0 | 0 | 26 | Revised Skunk Creek Site identified from 2010 Riparian Planting Plan
6 | Rogue River North Bank | RR | GP | GP-RR-P-3 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 36 | Identified from aerial photos. On Private land. Field verification is needed.
7 | Rogue River North Bank | RR | GP | GP-RR-P-2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 35 | Identified from aerial photos. On Private land. Field verification is needed.
8 | Rogue River North Bank | RR | GP | GP-RR-P-1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 35 | Identified from aerial photos. On Private land. Field verification is needed.
9 | Rogue River North Bank | RR | GP | GP-2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 0 | 2 | 0 | 0 | 3 | 36 | Identified from aerial photos. Field verification is needed.
10 | Rogue River North Bank | RR | GP/JOCO | GP-1 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 41 | Identified from aerial photos. On Josephine County property. Field verification is needed.
11 | Rogue River North Bank | RR | GP | GP-RR-P-5 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 3 | 33 | Identified from aerial photos. On Private land. Field verification is needed.
12 | Rogue River South Bank at Riverside Park | RR | GP | GP-RR-RP-1 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 43 | Canopy and habitat building at Riverfront Park. Will need to be ground truthed and designed to enhance the park and not limit access.
13 | Rogue River South Bank at Riverside Park | RR | GP | GP-RR-RP-2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 3 | 45 | Canopy and habitat building at Riverfront Park. Will need to be ground truthed and designed to enhance the park and not limit access.
14 | Rogue River North Bank | RR | GP | GP-RR-P-4 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 36 | Identified from aerial photos. On Private land. Field verification is needed.
15 | Tussing Park Drainage | RR | GP | GP-TP-1 | 3 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 2 | 0 | 0 | 3 | 41 | Storm drain and drainage in Tussing Park. Excellent opportunity for understory/habitat building and education by tying it into surrounding activities.
16 | Rogue River at All Sports Park | RR | GP | GP-RR-ASP-1 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 42 | Invasive species control and planting (canopy and understory) near All Sports Park bridge (north side of river)
17 | Rogue River at All Sports Park | RR | GP | GP-RR-ASP-2 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 42 | Invasive species control and planting (canopy and understory) near All Sports Park bridge (north side of river)
18 | Rogue River at All Sports Park | RR | GP | GP-RR-ASP-3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 0 | 2 | 0 | 0 | 3 | 42 | Invasive species control and planting (canopy and understory) near All Sports Park bridge (north side of river)
19 | Gilbert Creek at Gilbert Creek Park | O | GP | GP-GC-1 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 38 | Potential project with local schools and the Rogue River Watershed Council.
20 | Rogue River South Bank Near Baker Park | RR | GP | GP-RR-BP | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 0 | 2 | 3 | 3 | 3 | 45
0
0
0
| Waterbody | Code
| Rogue River | RR
| Bear Creek | BC
| Other (slough, wetland, lake, pond) | O
| DMA | Code
| Jackson County | JACO
| Josephine County | JOCO
| Curry County | CC
| Gold Beach | GB
| Cave Junction | CJ
| Grants Pass | GP
| Gold Hill | GH
| Rogue River | RR
| Eagle Point | EP
| Shady Cove | SC
| Butte Falls | BF

## Stream Smart_Regional Materials
Stream Smart Rogue Basin Logo
Brochures
Salmon Habitat Postcards (activity used with posters)
Posters

## Funding
Other Applications - RC
Bear Creek Effectiveness Monitoring Analysis | DEQ 319 | 31000 | Yes, partial
Salmon Watch | Jackson SWCD | 10000 | Yes
Salmon Watch | Gray Family Foundation | 11951 | Yes
Other Applications - RM partnered on
Riparian and Water Quality Monitoring - Planning, Training, and Implementation | Rogue Basin Partership | 5000 | Yes