## Sheet1
Source or Program | Meets Requirements for: |  | Strategy | Specific Actions [Recommend DMAs remove actions highlighted in red, either due to redundancy or action was completed in the first 5 year cycle] [Recommend changing RVCOG to RVCOG if DMAs are hiring RVCOG to coordinate or complete the action] | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost [For all actions specify DMA staff. Example: Public Works, Parks, Planning…] | Reporting Year or Plan Year [For all actions add a target date to the annual benchmark. Example: March TMDL meeting] | Status /Reporting Summary
| Bacteria | Temperature
I. Solar Radiation - streamside vegetation unprotected or inadequately protected. | X | X | A. Identify and inventory areas for protection. | 1. RVCOG and DMAs will update the map as new areas are identified. | 1. Copies of updated map(s). | RVCOG and DMA Staff | Annually. Review December TMDL meeting. Revision by June (year-end) | Regional Manager updated the restoration map of existing and known projects with input from cities, Jackson County, watershed partners, and other local groups. Shapefiles are updated annually with: 1.) planted sites or sites actively being planted and 2.) potential planting sites. The map is included in a separate tabs in this report as an overall map and zoomed in sections that provide more detail. In addition, the RM continues to coordinate activities including basin wide mapping with the riparian working group and staff of the Rogue Basin Partnership (RBP). In 2017-2018, restoration project locations(planted and projected) were incorporated in mapping completed for the Vegetation Management Plan for the Bear Creek Greenway. The plan focused on management recommendations integrating recreation corridor maintenance already being done with the transitional areas (between recreational maintenance and restoration zones) and restoration areas.
|  | X | B. Prioritize areas for planting. | 1. DMAs and the RVCOG will use a GIS based process to prioritize projects throughout the watershed and incorporate new sites into the GIS based prioritization process. | 1. RVCOG will provide a list of prioritized sites by DMA. DMAs will provide input to assist in identifying and prioritizing sites. List of newly prioritized or reprioritized areas. | RVCOG and DMA Staff | Meetings, data collection, process overview - Year 1 Prioritized list - Year 2 Updated Annually as needed Years 3-3 | The project list is updated on an ongoing basis as new sites are identified and prioritized (RM or DMA sites). The Expo Center, Scenic Middle School, and Crater High School were added this year. Sites were added to the planting matrix and scored. The prioritization chart was also updated with sites that have been completed (in green) or are known to be underway (yellow). In addition, a plan for a comprehensive restoration of Bear Creek including management of invasive species and restoration of native plants, improving shade, and other values was completed.
|  | X | C. Plant native trees and shrubs in public areas. | 1. RVCOG will identify restoration projects and other opportunities during each plan year, provide a planting and restoration project list, and work with DMAs and/or partners to coordinate and complete projects as time and funding permit. | 1. Summary of opportunities and activities identified and completed. The goal is to plant 500 trees in the watershed per year. | RVCOG, DMA Staff, Partners | Annually. Draft project list September TMDL meeting. March update and schedule of activities or activities completed. | Opportunities identified and in process or completed unless otherwise noted- Bear Creek at the Expo Center, Bear Creek at the Crater Land Lab, and Griffin Creek at Scenic Middle School. Approximately 1700 trees and shrubs (including willow stakes) were planted in the watershed by DMAs working with the RM. Other groups conducting activity but not included in the tree count include Lomakasti Restoration, the Rogue River Watershed Council, ODFW, the Freshwater Trust (TFT) and Oregon Stewardship. See detail in I.C.4.
|  |  |  | 2. Identify resources and available funding to promote collaborative on-the-ground actions | 2. Identify and quantify staff resources, direct funding, equipment, in-kind labor, and other assistance available each year. | DMA Staff, RVCOG, Partners | Annually. Projected resources available September. Actual resources expended in June. | Funding available in 2017-2018 included $5,000 from Jackson SWCD, $35,000 from the Pacific Power Blue Sky Habitat fund, $700.00 from the United States Fish and Wildlife Service, $15,000 from Jackson County, and an estimated $10,000 from TMDL dues. Other sources include in-kind from ODOT, Oregon Stewardship, RVCOG, Crater High School, Local Scouts, and volunteers. Some of the funding, especially through grants are available across multiple years. As a result, the sources appear on multiple reports.
|  | X |  | 3. RVCOG and DMAs will develop proposals and apply for funding and/or work with groups including the Freshwater Trust to protect and restore riparian areas. [In addition to parting with the FWT to restore private lands, cities need to continue to restore publicly owned lands and list a goal/measure of progress, such as number of trees planted, restoration projects completed, or area restored.] [DMAs should list proposed planting locations and timing for projects within their jurisdiction] | 3. List of projects, partnerships, or grant applications, including submittal dates, status (funded, not funded, pending), and general project location (DMAs and Creek(s)). | Grant funding, partners, general funds, staff. Specify project funding sources for each identified project. | Summary of activity annually | The Regional Manager continues to work with many local partners and pursues new opportunities with additional partners. During FY 2017-2018, the RM worked with the Freshwater Trust, the Rogue Basin Partnership, the Rogue River Watershed Council, ODOT, the City of Medford, the City of Central Point, Jackson County Expo Center, Jackson Soil and Water Conservation District, Jackson County, Oregon Stewardship, and others on restoration and protection proposals in the Bear Creek Watershed. In addition, the RM applied or reapplied for restoration projects In addition to the funding, RVCOG worked with Jackson County to secure an agreement to be able to contract with the Community Justice Crew to work on restoration projects. For private landowners, landowners were referred to the SWCD Landowner Assistance Program which provides technical assistance and funding for eligible projects which includes invasive species removal and planting/restoration of natives. Potentially qualifying projects/projects of interest were also referred to the Freshwater Trust (TFT) for inclusion in their Thermal Credit Program or BOR planting program in Bear Creek.
|  | X |  | 4. Implement planting and restoration projects. Work with landowners to restore riparian areas. Specify projects if known. | 4. List of planned projects, projected completion dates, and actual completion dates. | General Funds. Volunteers. Grant funds (from C.2.2) | Summary of activity annually | Active restoration conducted by the RM (directly or in partnership with other organizations) included planting and invasive species management work includes Bear Creek at the Expo Center, Bear Creek at Crater High School's Land Lab, and at Griffin Creek at Scenic Middle School. Information on planting statistics can be found in tab I.C.4
|  | X | D. Riparian Ordinance - Protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under each DMAs jurisdiction. | 1. DMAs will enforce ordinance or new ordinance as needed [Cite ordinance number including reference to the listed creeks that are included in riparian protection ordinance. Track code variances] | 1. Annual reports will document enforcement and code variances. | DMA Staff – Code Enforcement Officer | Annually
II. Solar Radiation -Streamside vegetation removed or overrun by invasive species. |  | X | A. Manage invasive species in public areas. | 1. DMAs and RVCOG will summarize activities completed to manage invasive species in riparian areas. Activities will include management by DMA staff, regional activities, map(s) and/or activities completed by partners. [DMAs should list proposed management locations and timing for projects within their jurisdiction] | 1. Annual summary of Activities. The goal is to manage invasives in public areas including parks and rights of way. The goal is to treat 5 acres or 5% of public areas annually. Invasive weed management projects will be coordinated with restoration projects (and funding application) in I.C.3 | DMA Staff and RVCOG, Jackson County Weed Management area, and partners. | Annually [One project should be completed annually]. Proposed Project list by September. Actual projects in June to be included in the annual report. | Invasive species removal was conducted as part of all restoration projects (refer to tab I.C.4), for three projects completed (approximately 15 acres). In addition, invasive weeds continue to be treated along the greenway and restoration projects from Jackson Street to McAndrews Boulevard and north. The RM also worked on a vegetation management plan for restoration projects near the greenway that includes recommendations and costs of managing invasive species. A link to the plan can be found at: http://rvcog.org/wp-content/uploads/2018/10/March-2018-Update.pdf. In addition, invasive species management has been added to the clean up events resulting in treatment of invasives. At the April 2018 event, 1 acre of blackberries was treated. Over 16 acres of invasives were removed meeting (and exceeding) the annual target.
III. Solar Radiation – Urban Forestry Program |  | X | A. Urban forestry program implementation to reduce thermal inputs from urban areas. | 1. DMAs will continue to implement programs. Plant street trees to reduce thermal loading on impervious surfaces. [DMAs should list proposed planting locations and timing for projects within their jurisdiction and address funding needs.] | 1. Program activity summary. Keep records of trees planted for new, redevelopment and street tree infill projects | DMA Staff [specify], tree costs funded by (?) | Annually
IV. Fecal Sources – pet, wildlife, and livestock waste. Properly manage animal waste. | X |  | A. Provide bags for dog owners to pick up pet waste. | 1. Add any new or planned stations to inventory. | 1. Updated inventory and/or map. | DMA Staff | Annually
| X |  |  | 2. Record number of bags purchased annually | 2. Document number of bags in matrix. | DMAs Staff or RVCOG | Annually
| X |  | B. Manage animal waste - livestock. | 1. Partner with Jackson SWCD, ODA, and/or other groups to address livestock issues and concerns within the jurisdiction | 1. Document activity. | City of Ashland and RVCOG | Annually | Concerns brought to the RM through the hot spot contact list, by the public, partners, and DMAs are followed up on by referring them to the appropriate agency which includes ODA for CAFO issues among. Referrals are also logged in the Tracking and Reporting spreadsheet (included as the Activity and Event Summary Tab) for the TMDL program. No referrals were made during the implementation year. Landowners in Jackson County who contact RVCOG with questions regarding livestock or help with on farm/ranch projects are generally referred to the SWCD for assistance through the landowner assistance program. The updated "hot spot" contact lists contain contact information for animal waste concerns.
V. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | X |  | A. Illegal dumping/illicit discharge detection and elimination (IDDE) programs. | 1. DMAs and RVCOG will continue to work to implement and strengthen their IDDE programs through their the Phase II Stormwater programs and enforce illegal dumping regulations under the NPDES Phase II program and/or codes and ordinances. | 1. Phase II Annual Report. Submit report to the MS4 Stormwater Coordinator and submit an electronic copy with the TMDL annual report. | DMA Staff and RVCOG | Annually | The RM continued to implement the hot spot monitoring program for illicit discharge and the storm drain monitoring program. Under these programs, storm drains are visited 3 times during the year for visual inspection and sample collection for discharge water quality. 18 sites are monitored under the storm drain program with additional samples collected for QA/QC for approximately 60 samples collected per year. Samples are analyzed for bacteria, temperature, phosphorus, BOD, turbidity, conductivity, and pH. Reports are sent to the TMDL committee. In addition, the RM follows up on concerns observed in the field or as requested by DMAs or partners. Hot spot calls are reported on the Activity and Event Summary Tab. Storm drain sampling data, hot spot contact sheets, stream postings, and other relevant information are uploaded to the Monitoring website on RVCOG's website http://rvcog.org/mn.asp?pg=NR_WQ_Monitoring. Information on reporting concerns is also included on RVCOG's website and on the Stream Smart website. In 2018, the RM worked with the Oregon State Police to investigate impacts including hot spots of bacteria from homeless camps along Bear Creek.
| X |  |  | 2. Continue illicit discharge monitoring (hot spot and storm drain) as part of the monitoring program administered by RVCOG. Review and refine hot spot monitoring program as needed including updating the contact list. | 2. List of any program refinements, list of hot spot monitoring completed for the year, and copy of hot spot contact list. | DMA Staff and RVCOG | Annually | RM continues to serve as a point of contact for water quality concerns. The hot spot contact list was updated for the year and uploaded to the website. Concerns are referred to the appropriate contact, the Stream Smart website, and/or the Riverkeeper Swim Guide for information on bacteria levels in local swimming areas. In addition, information on the program including links to OERS and the contact lists are on the Stream-Smart and RVCOG's website.
VI. Urban Runoff – Reduce runoff, promote infiltration and low impact development practices, and control sediment. | X | X | A. Use of methods and practices that reduce urban runoff. | 1. DMAs and the RVCOG will continue to identify and implement low impact development practices through their Phase II Stormwater programs and/or municipal codes and ordinances. [ DMA must identify specific projects that will be implemented over the next 5 years.] | 1. Track the features installed, size and treatment expectations as they are installed or reference the pertinent sections in the NPDES Phase II annual Report. | DMA Staff and RVCOG [clarify if this action is completed by RVS under the Phase II Permit] | Annually | The RM participates as part of the Stormwater Advisory Team as part of their work with the NPDES Phase II Programs for the local MS4s.
| X | X | B. Regional review and discussion of BMP databases and studies for treatment technologies (e.g., swales, wetlands, in-line systems) that will reduce bacteria levels in runoff. | 1. RVCOG will update the BMP database list and add new technologies as they are identified. DMAs will review and participate in a regional discussion regarding the use of the treatment technologies locally. | 1. Copies of updated list and recommended locations for installation of new treatment technologies. | RVCOG and DMA Staff | Annual Review of list Year-3 Hold a meeting or discuss technologies at quarterly TMDL and update list if needed following meeting. [Modify based on DMAs need] | RM reviewed the database. No updates were made this year.
| X | X | C. Inventory and map existing facilities installed in the Bear Creek watershed | 1. Review and update inventory and regional map of treatment facility locations. | 1. Inventory tracking form and map location of the features installed or reference to appropriate sections of the NPDES Phase II annual report. | RVCOG and DMA Staff | Annually | RVSS has completed online maps of facilities in Central Point and Talent available on https://rvss.maps.arcgis.com/apps/MapTour/index.html?appid=c4b907bf60dc40c99bd83e92cbbffe13. Ms4s have maps of these programs through their stormwater programs.
| X | X | D. Identify priority areas for installation of BMPs. | 1. Review and update list of priorities and locations or refer to appropriate sections of NPDES Phase II Plan. [ DMA must identify specific projects that will be implemented over the next 5 years.] | 1. Track the proposed features size and treatment expectations. | RVCOG and DMA Staff Project funding through (?) | Annually | Reported through MS4 programs.
| X | X |  | 2. Incorporate low impact development approaches into capital improvements, development and redevelopment projects in accordance with Rogue Valley Stormwater Quality Design manual to reduce impervious areas and infiltrate runoff. | 2. Track implemented features including relevant statistics (e.g., cost, size, treatment expectations.) | RVCOG and DMA Staff Project funding through (?) | Annually | Reported through MS4 programs.
VII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | X |  | A. Notify DEQ of failing systems when found. | 1. DMAs will notify DEQ of failing septic systems when found. | 1. Summary of any reported activity. Activity will be coordinated with NPDES Phase II MS4 programs. | DMA Staff and RVCOG | Annually | No septic system concerns were reported the RM this year.
| X |  | B. Cities will work with the NPDES Phase II programs, DEQ, and RVCOG to identify homes on septic systems within city limits. | 1. Develop an identification process and list of any homes on septic systems within city limits. | 1. Program summary and list of homes. | DMA Staff, DEQ, MS4s, RVCOG | Discuss procedures September 2014, March 2015 Complete method. List by June 2016. Updated Annually as needed. | A potential procedure was discussed to identify and list any homes on septic systems using GIS information combined with local knowledge to look at homes within City limits that are within a certain distance of creeks, not shown as connected to the existing sewer line coverage, and built before a certain date (e.g., prior to 1950). In addition, areas of consistent high bacteria results based on TMDL sampling results will be looked at to see if there are any areas that are of concern that could be septic related. These homes are the priority areas of concerns. In addition, the process will also look at other homes that may not be on septic systems. We are requesting that the timeline for this task be moved back, with addition procedure revision, mapping, and process occurring in 2018-2019. In early 2018, we are reviewing monitoring data collected to look at consistently high bacteria levels. Results should be completed by be end of the calendar year.
VIII. Outreach and Education | X | X | A. Implement regional outreach strategies targeting water quality parameters addressed in the TMDL. | 1. RVCOG and DMAs will coordinate with local groups (e.g., O.S.U. Extension, Bear Creek Watershed Education Partners, North Mountain Park, Coyote Trails, local schools) to implement outreach programs. RVCOG and DMAs will hold, participate in, and/or promote annual events benefitting TMDL related activities. | 1. Summary of events attended, activities/presentations conducted, and number of people attending and/or participating in activities. Attend a minimum of 3 outreach events per year for TMDL only or in partnership with other programs (e.g., NPDES Phase II, Riparian Restoration, etc.). | RVCOG and DMA Staff | Annually | Refer to the Activity and Event tab for specifics on events. Many events, but not all were done in conjunction with other programs, most notably the NPDES Phase II Stormwater programs and Stream Smart. Events and activities included: Rogue Valley Annual Earth Day Celebration at Scienceworks (SW and TMDL), two Bear Creek Clean-ups (SW and TMDL), the Land Steward Workshop (SW and TMDL), field programs for McGloughlin Middle School Students and Cascade Christian High School, the Bear Creek Salmon Festival (TMDL), the Stream Smart Mall cart (SW and TMDL), and the Salmon Watch Program (Stormwater and TMDL). Combined programs reached over 2000 people including students and the general public (including adults). The mall cart had an estimated 1,860 visitors in July, which brings the total people reached to over 3800. There were also over 3,700 visitors to the Stream Smart website. See events tab for photos of activities completed this year.
| X | X |  | 2. RVCOG and DMAs will provide and coordinate strategies with the Stream Smart Program and provide support to the Program as directed by the DMAs. | 2. Summary of activity and copies of or references to materials (brochures, web sections, etc.) in annual report. | RVCOG and DMA Staff | Annually | The RM coordinated events, trainings, workshops, clean ups, and other activities with the Stream Smart program. In January 2018, the Stream Smart Program kicked off the Go Blue! Campaign by adopting Bear Creek under SOLVE's Adopt-A-River Program. As part of the Adopt A River and Go Blue!, the clean up events, the Bear Creek Fall Festival (Kids and Creeks), and Salmon Watch were all put under the programs to increase exposure and participation. In addition, the logo, event calendar, facebook website postings, and materials at events all helped to increase exposure for the Stream Smart program and attendance at the events/activities. In addition, the RM worked with the RRWC, SWCD, RVSS, and others to post on the Facebook website information related to water quality, TMDL programs, urban runoff, events, and other relevant activities. The RM coordinated the StreamSmart Advisory Committee which meets quarterly to identify needs of the program and make recommendations including how to keep it up and running, how to revamp and expand it, and identify needs and projects for the year. In addition to DMAs serving on the committee, the DMAs are supporting the program financially by funding the domain registration, website hosting, google email, and basic site maintenance. Work with the Regional Project team is also being integrated with the Stream Smart Program. Examples of Stream Smart supported activities include the Salmon Watch Program, Kids and Creeks, geocaches (GC6C28T, GC3CPT6, AND GC3C9QX), and the Bear Creek Clean-ups. In addition, the RM worked with the Rogue Valley Mall to provide an education and information cart that included materials on urban runoff, water quality, riparian restoration, and creek clean ups. The cart and subsequent materials were under the Stream Smart program. The cart operated through July 2017.
| X | X |  | 3. RVCOG will adopt, customize, and/or develop regional materials to be used in the program and/or in coordination with the Stream Smart Program. | 3. Summary of activity. | RVCOG and DMA Staff | Annually | RM continued to develop, refine, and incorporate materials (including the logo and websites) for use in the program on an ongoing basis. Specific activities/items kicked off the Go Blue! Campaign by adopting Bear Creek under SOLVE's Adopt-A-River Program. As part of the Adopt A River and Go Blue!, the clean up events, the Bear Creek Fall Festival (Kids and Creeks), and Salmon Watch were all put under the programs to increase exposure and participation. Other activities include the refinement and addition of event materials, creation of posters, Car Wash Kit materials, incorporation of materials into geocaches, refinement of the website, use of the logo to replace individual DMA contact information on brochures, and using social media to advertise for events and distribute information. Examples of materials can be found in the Stream Smart tab. The RM also printed 10,500 pledge cards 7,500 in English and 2,500 in Spanish. The RM also coordinated logistics for the Salmon Watch program with the World Salmon Council who is taking the lead at keeping track of programs statewide. Programs are currently independent, but there may be future coordination of programs Statewide. The RM also participated in two meetings with the Clean Rivers Coalition to talk about Statewide communication strategies, pooling resources, and messaging related to water quality (Phase II and TMDL related, but more emphasis was focused on stormwater related pollutants).
| X | X |  | 4. RVCOG will assist DMAs in promoting regional success stories and other program activities through the local media, websites, newsletters, and/or other methods. | 4. Summary of activity and copies of any materials produced. | RVCOG and DMA Staff | Annually | RM regularly updates its website which features information on projects. In addition, throughout the year, the RM reports on activities at meetings, gives presentations, and provides information at events about regional successes. Specific successes and program activities include TMDL and Stormwater program implementation elements (leading to long term improvements in Bear Creek water quality), the Bear Creek Clean-ups, and the 2017-2018 Salmon Watch Program. A flyer on the success of the Salmon Watch Program is included on the Salmon Watch Stats tab.
|  | X | B. Provide citizens, landowners, and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. RVCOG and DMAs will work with local agencies, nurseries, landowners, and citizens to provide technical assistance and resources for planting. | 1. Summary of activities, contacts meeting, meetings, and presentations. | RVCOG and DMA Staff | Annually | RM participated in a number of events and activities throughout the year where resources were provided for citizens, landowners, and other groups. Specifically, a number of referrals were made to Jackson SWCD's Landowner Assistance Program, through the Stream Smart website and Planting Pledge, recommendations on plants and resources were made at events (e.g., Land Steward Workshop, Earth Day, Bear Creek Clean Up, Salmon Festival), and copies of the Stream and Wetland Enhancement Guide, Taking Care of Streams in Jackson County, and Garden Worthy Native Trees and Shrubs, and other riparian brochures were distributed were distributed. Information on the events and brochures distributed can be found in the Activity and Event Summary. The RM also worked with Oregon Stewardship, the Jackson County Community Justice Crew, the Greenway (Joint Powers), and others to provide technical assistance with restoration projects. In 2017-2018, the RM also worked with Scenic Middle School and Crater High School to develop and implement restoration projects on Griffin Creek and Bear Creek.
|  | X |  | 2. DMAs and RVCOG will distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | RVCOG and DMA Staff | Annually | Copies of brochures are available on RVCOG's website. In addition, brochures handed out and locations are tracked in the Activity and Event Summary Tab. Brochures were distributed at libraries, to local businesses, at events including Salmon watch and where the RM (and others) staffed booths. In addition to visiting libraries, the RM worked with the Library District to distribute brochures and the Stream Smart Pledge Cards in English and Spanish to all of the libraries in Jackson County.
| X |  | C. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Outreach will continue to target areas of high animal usage including public areas near water ways and dog oriented businesses. | 1. Annual activity summary, documentation of deliverables including number and location of materials distributed, presentations, etc. | RVCOG and DMA Staff | Annually | RM helped organize the Kids and Creek event (renamed Bear Creek Fall Festival for 2018) which is held at Bear Creek Park. The event targets park users including the Dog Park. In addition, the RM staffs a booth featuring information on Yard Care and the Stream Smart Program which includes pledges and poop dispensers for picking up after your pets. Information is also available on the Stream Smart website and facebook site including the pledges. Remaining poop dispensers and/or pledge cards were distributed at all events attended throughout the year, in geocaches, and at other locations.
| X | X | D. Staff Training [Modify to reflect staff training needs within your DMA and develop a training schedule. Include internal coordination and communication] [Could be stormwater BMPs, erosion prevention, pesticide use, roads maintenance, floodplain management etc...] | 1. DMA will train staff as needed on topics related to TMDL Implementation. RVCOG will compile, coordinate, and conduct staff training opportunities. | 1. List of how training was conducted and frequency. Activities may include classes, webinars, presentations, and seminars. | DMA Staff and RVCOG | Annually | Topics/presentations are quarterly TMDL meetings included - the Swim Guide and Bacteria Monitoring, the Pesticide Stewardship Partnership (PSP), Groundwater (Assessment Units and local study results), ODA's Strategic Implementation Areas for Wagner Creek and Neil Creek. Specific training examples that were held that were attended by DMAs included the Salmon Watch Instructor Training (September 14th), the HazMat Spills training organized by RVSS (October 3rd), and EcoBiz (June 14th and 15th). The EcoBiz training focused on Fleets and Auto Service Stations so it was more Phase II focused. However, the program can be expanded to certify landscapers which would TMDL related. A number of online webinars, local, regional, and statewide trainings were also promoted at TMDL meetings and through TMDL distribution lists by the RM, DMAs, and partners (e.g., RVSS).
IX. Regional Water Quality Coordination | X | X | A. Continue participation in the TMDL program. | 1. DMAs will continue participation in the TMDL program. RVCOG will continue to facilitate the meetings work with DEQ to develop agendas and arrange speakers. | 1. DMAs will send a representative to the quarterly TMDL meetings. RVCOG will provide a record of attendance and agenda topics for each meeting. Copies of completed sign-in sheets will be provided to DEQ. | DMA Staff and RVCOG | Annually | Funding provided by the DMAs supports the coordination of quarterly TMDL Meetings including developing agendas, facilitating meetings, arranging speakers, and providing program updates. Attendance records for all meetings were submitted to DEQ and provided on the TMDL meeting attendance tab.
X. Funding | X | X | A. Evaluate the costs of program implementation. | 1. RVCOG will work with DMAs to establish costs of regional program implementation including staff time, hiring of a RVCOG, existing grant funding, and other resources. [DMAs need to identify the cost of TMDL implementation for each action. Sources of funding from each DMA for each action needs to be noted (staff, grants, fees, or other sources), resulting in the development of a preliminary budget for implementing the next 5 years of implementation. Annual budgeting for specific projects will also need to occur.] | 1. Development of a preliminary budget for TMDL implementation which lists program costs and sources for all actions listed in the TMDL Implementation Plan Matrix (e.g., staff time, direct funding, grants, etc.). | RVCOG and DMA Staff with assistance from RVCOG | Annually | RM established the costs of several implementation items in developing the annual TMDL contracts. Additional implementation items including costs are provide in scopes for specific items (e.g., Greenway Management Plan - $15,000.00, Salmon Watch $10,0000.00) have been prepared for DMAs or grants. Specific TMDL related scopes/grants have included riparian restoration, invasive species management, additional water quality services, trainings, workshops, and educational activities. In addition, a cost to keep the Stream Smart Program going with basic updates and keeping the website up and running was completed ($3,500.00) and included as part of the TMDL contracts. Major website changes will require additional funding and scopes to be developed by the RM or partners.
| X | X | B. Seek additional funding for program implementation as needed. | 1. RVCOG will work with DMAs to apply for regional funding for implementation. [Develop a list of needs or projects eligible for grant funding and a schedule for applying for grant funding.] | 1. List of funding applied for and copies of grant applications as requested. | RVCOG and DMA Staff | Annually | Additional funding applied for included restoration projects from the U.S. Fish and Wildlife Service ($700.00). In addition, the RM received funding through DEQ's 319 program (23,000.00), Jackson SWCD ($10,000.00), the Gray Family Foundation ($11,951.00), and the Rogue Basin Partnership. The RM also received small grants and/or contributions for projects from SOLVE, Starbucks, REI, Fred Meyer, and Food for Less. Information on funding applications can be found on the funding applications tab.
XI. Monitoring and Reporting | X | X | A. Use the matrix as a template to track the implementation plan Submit annual reports to DEQ. | 1. RVCOG and DMAs will compile information on the measures of progress and benchmarks into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. Completed annual reports submitted to DEQ by November 1st of each year, reporting on implementation actions for the July 1-June 30 plan year. | RVCOG and DMA Staff | Annually, September 30 of each year. | Tracking of activities is done by the RM regularly using calendars and a spreadsheet. Additional detail is provided in reports, project summaries, online, and invoices. Details are included on separate tabs and/or in this reporting column as needed. In addition, selected deliverables including completed matrixes are posted on the RVCOG and/or Stream Smart website.
| X | X | B. Use existing programs to track program effectiveness. [Specify how DMAs are tracking program effectiveness.] | 1. RVCOG will work with DEQ and the DMAs to implement methods for evaluating and tracking program effectiveness (e.g., surveys, check lists, meeting milestones and measures of progress). [Each DMA should specify how they are tracking program effectiveness.] | 1. Summary of methods evaluation and results. | RVCOG and DMA Staff | Year 3 [timeline based on selected method] | Currently, the RM tracks effectiveness through the monitoring program, attendance at events/workshops/trainings/meetings/etc, number of visits to the websites, number of brochures handed out, surveys, number of trees and shrubs planted, number of stream miles or acres protected, amount of invasive species managed (acres), mapping, and other methods. The Stream-Smart website had 3,705 visitors. Please see the information on the Stream Smart Web Stats Tab for the visitor breakdown and most visited pages.
| X | X |  | 2. RVCOG will work with DEQ and the DMAs to use existing programs (TMDL monitoring program, DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. [Please be specific - RVCOG water quality data should be evaluated for trends and TMDL effectiveness] | 2. Summary of regional water quality. | RVCOG and DMA Staff | Year 3 [timeline based on selected method] | RVCOG collected and analyzed water quality samples in 2017-2018. Monitoring runs conducted included the monthly TMDL effectiveness run, bimonthly QA/QC splits with DEQ, hot spot monitoring, and the Illicit Discharge (storm drain) run. Sampling stations include streams and storm drains from the headwaters to the mouth. Data is looked at on a monthly basis and quarterly or annual data is sent to the DMAs. In addition, the RM has been working with the Rogue River Watershed Council, the Freshwater Trust, and Oregon Department of Fish and Wildlife to find cold water refugia areas in Bear Creek by installing a series of in stream temperature loggers throughout Bear Creek (23 loggers). Data from the loggers will be used to identify potential refugia areas, evaluate the impacts of the drought, and also to evaluate effectiveness of restoration projects. This is the third year of the temperature monitoring project. In addition, we collected samples for metals analysis and petroleum in selected storm drains and collected bacteria samples near homeless camps with Oregon State Police. Results of the monitoring did not identify any bacteria hot spots, but camps have a great potential to impact temperature and bacteria levels in the creek and provide other impacts as well (see photos in monitoring photos).
| X | X | C. Adaptive Management Plan. | 1. RVCOG will assist DMAs to modify plan as needed. | 1. Revised TMDL Implementation Plans. | RVCOG and DMA Staff | Year 5 | The RM developed a 319 grant application with TMDL DMAs and other partners to conduct an in-depth analysis of the monitoring data collected to evaluate the effectiveness of the program designed by Cadmus. The program was designed to evaluate the effectiveness of the TMDL implementation efforts. Results of the study will be used to modify the monitoring program and TMDL implementation program as needed or if needed.