## DEQ Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Develop an inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time | Track number of existing stations and report new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks/public areas with stations. Add a percentage of stations added until 100% of parks/public areas that need stations have stations. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volume (Post Construction). | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track the features installed, size and treatment expectations as they are installed. | Ongoing as development occurs. | This strategy is tied into the Phase II program and dependent on funding availability to design and construct capital improvements, as well as on private investment in new or redevelopment projects. Report out on features being installed and maintained in capital projects that incorporate these. | The RC created an electronic survey form that can be used to inventory and map features (https://arcg.is/1Xe10i0). All tracking and other information collected is included in the City's stormwater program and included in the annual reports. No tracking was completed in 2020-2021. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education through design workshops, volunteer opportunities, and/or other methods. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Part of phase II program. Annual update on program development and relevant statistics in Phase II report. | General information, workshops, volunteer opportunities, and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/), and information on the City's TMDL page on RVCOGs website (https://rvcog.org/grants-pass-tmdl/). Activity was limited due to COVID19 and regional fires. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Address water quality impacts of stormwater | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RC during the implementation year. The OWEB small grant program is anticipated to be available in the Fall of 2021 and do feature a category for Urban Impact Reduction which could be used to fund BMPs. The RC will work with the City to evaluate potential funding for BMP implementation. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Pollution Prevention/Good Housekeeping - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage, sediment controls, street sweeping to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken in NPDES Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). | Review and refine illicit discharge and hot spot water sampling program as needed | Staff Time. RVCOG | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, | The RC serves a point of contact for regional water quality concerns. Calls that are received for Grants Pass and other jurisdictions are documented and referred to the appropriate entity, agency, or response including OERS, In addition, hot spot contact information including lists are available online through the Stream Smart program and in other locations and are updated annually. The hot spot monitoring form is also used to record and document occurrences reported (https://arcg.is/1byiCy). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Annual update on actions taken in NPDES Phase II report. | As part of the IDDE program, the RC is available as directed by the City to conduct visual inspections of storm drains and areas of concern and document what is found. In addition, the RC can collect samples to see what the impact is on TMDL parameters. All activity is documented in the matrix. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Annual update on actions taken in NPDES Phase II report. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time. RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RC during the implementation year are reported to the City and/or DEQ. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. | Staff time. RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Temp
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Implement current riparian buffer standards/riparian ordinance | Review site and land division proposals to ensure consistent buffers. Implement and enforce riparian ordinance | Staff Time | List of riparian buffer standards or riparian ordinance actions taken. | Ongoing | Annual reports will track buffer standards or riparian ordinance actions taken. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Incentivize new land division proposals to reserve floodplains as a natural open space | Review site and land division proposals for opportunities | Staff time | Program development. Keep records of protected areas. | Ongoing | Annual reports and 5-year reviews will track progress including number of projects, acres preserved/restored, and establish recommendations for improvements as needed. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for implementation of projects (active management of invasives, planting, etc.). RVCOG. Contractor(s), partners. | Line item established in budget with annual funding. | first year with line item and funding; annually thereafter | Budget development and reporting will demonstrate progress. Number of plantings or projects. | RC has been working with the City for developing and implementing riparian restoration programs and remove invasive species. Support for riparian species restoration and invasive species removal projects are included in the contract with RVCOG. New sites for restoration were identified, surveyed, and mapped (Riparian Projects tab). In addition, we worked with the County Weed Management Agency to identify and implement projects for invasive species removal at Reinhart Park and as part of the Rogue River Clean-up. English Ivy, blackberry, starthistle, and other species were removed (3.3 acres). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. | Staff time, RVCOG, partners. | Completion and record of annual efforts | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | 10 new sites were identified and catalogued using Survey 1-2-3. The sites were also prioritized using the riparian matrix developed in previous years. In addition, the City and RC continue to participate in regional programs with partners that focus on wider scale restoration activities including the Bear Creek Restoration Initiative (BCRI), and the Rogue Basin Restoration Working Group. Most of the focus in 2020-2021 has been on fire restoration from the Almeda, Table Rock, and Obenchain Fires. Lessons learned including restoration and stabilization strategies following fires and building fire resiliency are being added to local restoration programs. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City participates in events: Events include at least one featured tree planting project, tree giveaways to residents, or restoration project activity (monitoring, maintenance, watering, invasive species management). | Staff time, RVCOG, partners. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | Events held each year with local participants and activities that educate and implement tree planting. | The City and RC participated in two events focused on invasive species management. An estimated 3.3 acres of invasives were removed by 25 volunteers. Restoring the sites with natives is being evaluated for future implementation years. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publically owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time, RVCOG, partners. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify Implemented projects on an annual basis | 10 new sites were identified and catalogued using Survey 1-2-3. The sites were also prioritized using the riparian matrix developed in previous years. The City is evaluating options for funding including applying for individual grants or participating in larger restoration programs that will include several projects and target larger funding sources. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Reduce warm stormwater runoff volumes (Post Construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from stormwater utility fund, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects (mostly vegetative buffer strips and such associated with new road projects) that incorporated LID or other methods into development and redevelopment plans. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Riparian restoration strategies are being re-evaluated in the region following the area fires in Jackson and Josephine County. As part of the strategies, initial stabilization protocols following areas being burned are being finalized. In addition, planning for increased fire resiliency, pollinator habitat, and drought are also being considered. All changes in restoration strategies have the potential to impact the goals of the Temperature TMDL program. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Ed and Outreach
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter and/or other publications. | Staff. RVCOG. Partners. | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Articles, social media posts, and interviews were conducted throughout the year on various topics through the Stream Smart Program, the City's Website, and the City's TMDL page on RVCOG's website. Articles and interviews have featured Stream Smart's adopting of the section of the Bear Creek Greenway, the Rogue River Clean-up and other activities, Example articles are in the Articles tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics | Staff time, RVCOG | City’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | The Stream Smart website is updated monthly with new content, links and events. In 2020, a complete overhaul and update was completed for the website. Context was moved to a test website and new content was added. In the fall of 2020, the new website went live ( https://www.stream-smart.com/ ). The GP website on RVCOG's website is updated quarterly on a regular basis and as needed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Example: Rain Garden, downspout disconnects, demonstration workshops, Salmon Watch Program, don’t feed wildlife etc | Continue to support the Regional Programs by working with RVCOG. Additional Grants Pass specific programs will be conducted by City Staff, RVCOG, and/or volunteers. | Workshop/Program participation and measurable results (i.e. number of rain gardens installed, downspouts disconnected, number of students participating in Salmon Watch, etc.) | Annually | Annual Action Plan and Subsequent Report | Due to the ongoing impacts of COVID19, events, workshops, and volunteer activities were extremely limited. Salmon Watch was conducted on a limited basis virtually (5 hybrid zoom/field sessions) and 12 field session with almost 800 participants (794) attending both sessions. The Rogue River Clean-up had 60 participants and picked up 15 cubic yards of trash and removed invasive species (estimated 1 acre). In addition, there was a weed pull/removal event at Reinhart Volunteer Park (0.3 acres) and a trash clean-up on a different day with 25 Dutch Brothers volunteers. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns | Staff time & support funding. | City’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report | The City of Grants Pass provides direct funding for the Stream Smart Program and participates as a member of the Advisory Committee. An example of Stream Smart activity can be found in the Stream Smart tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Participate in a basin-wide riparian restoration program and provide outreach to target areas. | Staff time. RVCOG. Other DMAs. Partners. Volunteers | Focus is on identifying, prioritizing, and moving toward implementation of projects | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | New sites were identified and documented using Survey 1-2-3 and other methods. 10 sites were documented in 2020-2021. The locations of the sites are included in the map (Riparian Projects Map tab). Planting a restoration strategies that are used in restoration by the City follow recommendations found in the Bear Creek and Rogue Basin Planting Plan. Updates and changes to strategies follow recommendation completed by the Bear Creek Restoration Initiative and other groups. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | The City has participated in meetings developing new technologies particularly in the form of electronic data collection forms for TMDL and stormwater using Survey 1-2-3 and online mapping. Funding provided by the City supported the creation of the forms, data collection, and mapping activities. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. | Staff time. RVCOG. Partners. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | TMDL implementation actions are tracked on an ongoing basis by RVCOG electronically through the use of surveys, maps, and/ or spreadsheets. In addition, data has been collected by the City as part of the Rogue Drinking Water Partnership to look at the impacts of the local fires (Almeda, Table Rock, and Obenchain) on the Rogue River and potential treatment and drinking water concerns. Data collected as part of this program is being evaluated for the TMDL program. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | No reports were given to management by the RC. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | Staff attended quarterly meetings and provided updates during the roundtable updates. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Completed with the submittal of this document and accompanying forms. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Prioritization_Criteria
Critical Factor | Explanation of Matrix critical factors: | Score |  |  | Score
|  | High | Medium | Low | High | Medium | Low
Accessibility | Includes physical constraints to land: willing landowner (including agencies), physical barriers (e.g., fencing and vegetation), and accessibility (equipment, maintenance, plant deliveries, etc.). | Lots of constraints and barriers to completing the project. | Moderate constraints. | Easy access for people, equipment, and vehicles. | 1 | 2 | 3
Partner Interest | Indicated a willing partner/expressed interest in a project by landowner or agency/ organization/ school. | Willing partner, organized group that owns or has access to the site. | Willing partner. Limited access to the site. | No partners. | 3 | 2 | 1
Coordination with existing plans | Has the site been recommended for restoration - plans may include watershed assessments and action plans, parks plans, Rogue Restoration work, the WISE project, Freshwater Trust, and other groups. | Yes, as a high priority in one or more plans. | Moderately rated site in plans and assessments. | No or rated as low/limited potential. | 3 | 2 | 1
Habitat Enhancement Need | Includes both terrestrial and aquatic habitat- increase in diversity of species, erosion control, bank stability, channel undercutting, recent disturbance, large woody debris, reduction in algal growth or temperature, overstory building for shade, etc. | Site has a high need and significant potential for restoring habitat. | Site has some need and potential for restoration. | Site is in good shape. No/Limited enhancement needed. | 3 | 2 | 1
Irrigation availability | Assessment of watering needs including accessibility to an available water source for irrigation. | Site has irrigation or a water supply in close proximity. | Water is available through a limited duration water right or a supply that is located far away or requires regular site visits (e.g., watering truck or crew). | Limited or no water availability. | 3 | 2 | 1
Restrictive Site Conditions/ Limitations | Assessment of site conditions that would reduce the survival of seedlings including: soil conditions, invasives, existing uses of area and potential for vandalism. | Lots of constraints and difficult site conditions identified. |  | Limited/no constraints. | 1 | 2 | 3
Key habitat area | Includes assessment of connectivity potential to other habitat areas and T&E spp. Presence, sensitive wetland feature or adjacent to sensitive area including a cultural resource area. | Key/critical habitat. High value. | Important habitat, disturbed, moderate value. | Low value. Highly disturbed site. | 3 | 2 | 1
Flood Abatement/ Storage | Assess areas potential for flood storage and abatement. | High potential, floodplain connection, existing storage provided. | Moderate storage provided. | Low storage. Low/limited connectivity (e.g., incised, narrow channel). | 3 | 2 | 1
Site preparation | How much preparation will be needed before the site is planted (blackberry removal, soil amendments, etc) prior to plantings? | Significant preparation needed. Lots of invasives, soil amendments needed, tough site conditions. | Some preparation needed. | Minimal preparation work needed. | 1 | 2 | 3
Proximity to stream/river | Will the planting shade the stream or provide riparian protection (e.g., buffers)? | Yes. Planting of the site will result in increasing the overstory vegetation and the aspect will greatly reduce the amount of direct solar loading to the stream. |  | Planting will provide minimal shade benefits only. | 3 | 2 | 1
Fire Risk | Is area a potential fire risk? Dead trees, invasive plants, dense small diameter forest, etc. This does not include areas that were already burned. | High fire risk. Lots of invasive species, no/low water, lots of fire prone species, close to source area (e.g., I-5, Greenway). High fire occurrence history. | Moderate fire risk. | Low fire risk. | 1 | 2 | 3
Invasive species presence | Does the site have a high percentage of invasive species? | Dominated by invasive species (<50%). | 25-50% invasives. | <25 % invasives. | 1 | 2 | 3
Potential/Existing Recreational Area | Is there existing recreation at or near the site? Is there the potential to incorporate new recreation/recreational access to the site? | Yes. Existing trail or greenway. | Some. Opportunity for future connection/path. | No. | 3 | 2 | 1
Potential for adoption of site monitoring/ maintenance | Is there an established or the potential for an established entity to conduct site maintenance and monitoring? Entities could be local schools, watershed groups, watershed councils, Municipalities, the Job Council, contractors, and others. | Yes. | There are potential groups, but no agreements are in place to complete monitoring and maintenance. | No. | 3 | 2 | 1
Shading Potential/Shading Needs | Is there an identified shading need at the site? Identified need could be from a watershed survey, visual surveys, air photos, shade surveys, etc.? | High potential for shade (shade potential). | Moderate shade potential. | Low shade potential (existing | 3 | 2 | 1
Thermal Credits Available | Is there potential for thermal credits to be available for the project and funding provided by the Freshwater Trust? | Yes. |  | No. | 3 | 2 | 1
Other TMDL Parameters or Need Addressed | Are there other pollutants or TMDL parameters that will benefit by restoring or protecting this site? e.g., wetland function. Are there other needs addressed? E.g. education and outreach, demonstration site, BMP/LID location, etc. | Yes. |  | No. | 3 | 2 | 1
Other potential parameters to add
Aspect | Sites that will block southern exposure to afternoon sun in the summer are higher priority.
Planting plan completed? | Is there a planting plan completed for the site, so the site is essentially ready to go?
Proximity to another restoration site, planting project, or healthy riparian zone. | If there is a site nearby or adjacent that the project would connect to, the potential benefits increase resulting in a higher overall benefit for the project.
Public Land | Is the site located on public land?
Public benefit | Does the project benefit the public?
Regulatory Compliance | Does the project meet the needs of multiple regulations?
Funding | Is there funding available for the project? E.g., smaller projects may be achievable with the amounts available.
Stream/River Size | Is the flow or size of the stream greater than some set threshold? 50 feet? 200 cfs?
Other?

## Sites Prioritzed
Planting Site |  | Waterbody: See Codes Below | DMA(s): See Below | Site code | Accessibility | Partner interest | Coordination with exist. plans | Habitat enhancement need | Irrigation availability | Restrictive Site conditions/Limitations* | Key habitat area | Flood abatement/storage | Site preparation minimal | Proximity to stream/ wetland | Fire risk | Invasive Species presence/ potential | Potential/ existing recreational area | Potential for adoption of site monitoring/ maintenance | Shade Potential/Shading Need | Thermal Credits Available | Other TMDL Parameter Addressed | Total Score | Rank | Notes
| Tom Pierce Park - Pollinator Gardens | RR | GP, JoCo | TPP 2021dr | 3 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 39 | 8
| Tom Pierce Park - Overall | RR | GP, JoCo | TPP2021ur | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 40 | 7
| SE Mill and SE M Street | NA | GP, JoCo | Mill_M | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 24 | 8 | Drainage needing Invasive Species Work
| Baker Park | RR | GP, JoCo | Baker 2021 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 41 | 6
| Riverside Park near playground | RR | GP, JoCo | RVSD Play | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 42 | 3
| Reinhart Park near Dog Park | RR | GP, JoCo | RHDP | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 42 | 3 | Pollinator Patch
| Reinhart Park near WWTP | RR | GP, JoCo | RHPWWTP 2021 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 42 | 3 | Pollinator Patch
| Tussing Park - Allen Creek | AC | GP, JoCo | TS 2021 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 38 | 3
| Post Ivy Removal Restoration - Reinhart Park | RR | GP, JoCo | RHP IVY | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 43 | 1
| Post Knotweed Removal Reinhart Park | RR | GP, JoCo | RHP - Knotweed | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 43 | 1
Planting Site |  | Waterbody: See Codes Below | DMA(s): See Below | Site code | Accessibility | Partner interest | Coordination with exist. plans | Habitat enhancement need | Irrigation availability | Restrictive Site conditions/Limitations* | Key habitat area | Flood abatement/storage | Site preparation minimal | Proximity to stream/ wetland | Fire risk | Invasive Species presence/ potential | Potential/ existing recreational area | Potential for adoption of site monitoring/ maintenance | Shade Potential/Shading Need | Thermal Credits Available | Other TMDL Parameter Addressed | Total Score | Rank | Notes
Recent Activity (Implementation Year)
Sites Completed
Sites Actively being worked on

## Articles
Article link: | https://southernoregonfamily.com/do-your-part-and-be-stream-smart/

## TMDL Stats
|  | Bear Creek |  | Josephine County/Grants Pass | Other Stats
|  | TMDL | SW | TMDL
Activity | Participants
Fire Volunteers | 256 | 256 | 256 |  |  | Number of trees
Acres Restored
Invasive Species Managed
Pounds of Trash
Willow Staking | 52 |  |  |  | 4900 | Number of trees
[5 empty] | 1 | Acres Restored | miles
Invasive Species Managed
Pounds of Trash
Geocaches | 72 | 29 | 43 | 72 |  | Number of trees
Acres Restored
Invasive Species Managed
Pounds of Trash
Salmon Watch | 794 | 794 | 794 | 794 |  | Number of trees
Acres Restored
Invasive Species Managed
Pounds of Trash
Bear Creek Clean-ups | 215 |  |  |  |  | Number of trees
Acres Restored
[5 empty] | 0.3 | Invasive Species Managed
[5 empty] | 6960 | Pounds of Trash
Rogue Clean-ups | 60 |  |  | 60 |  | Number of trees
Acres Restored
Invasive Species Managed
[6 empty] | Pounds of Trash | 50 cubic yards
Event(s) | 52 | 52 | 52 | 52 |  | Number of trees
Acres Restored
Invasive Species Managed
Pounds of Trash
ISM - Jackson | [5 empty] | Number of trees
Acres Restored
Invasive Species Managed
Pounds of Trash
ISM - Josephine |  |  |  | 25 |  | Number of trees
Acres Restored
[5 empty] | 0.3 | Invasive Species Managed
Pounds of Trash
other | [5 empty] | Number of trees
Acres Restored
Invasive Species Managed
Pounds of Trash
[5 empty] | 4900 | Number of trees
| 1501 | 1131 | 1145 | 1003 |  | Acres Restored
[5 empty] | 0.6 | Invasive Species Managed
[5 empty] | 6960 | Pounds of Trash
[5 empty] | 50 | cubic yards of trash
[5 empty] | 1 | stream mile restored

## Salmon Watch
Date | Program | Number of Participants
2020-11-12 | Salmon Watch Interactive | 35
2021-04-27 | Salmon Watch Virtual Session (am) | 300
2021-04-28 | Salmon Watch Virtual Session (am and pm)
2021-04-29 | Salmon Watch Virtual Session (am)
2021-05-04 | Kids Unlimited Salmon Watch Session | 109
2021-05-13 | Kids Unlimited Salmon Watch Session
2021-05-17 | Salmon Watch at Scenic | 250
2021-05-17 | Salmon Watch at Scenic
2021-05-18 | Salmon Watch at Scenic
2021-05-18 | Salmon Watch Session (Scenic)
2021-05-19 | Salmon Watch Session (Scenic)
2021-05-20 | Salmon Watch at Scenic
2021-05-20 | McGloughlin Salmon Watch Session | 100
2021-05-21 | Salmon Watch at Scenic
2021-05-21 | McGloughlinSalmon Watch Session
|  | 794 | Total

## Previous 5 Year Plan
Source or Program | Strategy | Specific Actions | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost | Reporting Year or Plan Year | Activity (Reporting) Summary
I. Implement TMDL Program using existing programs and updating or creating programs as needed. | A. Use existing programs and available resources to implement programs. | 1. Develop an inventory or schedule of anticipated TMDL related activity being conducted by the City including department responsibilities. | 1. Draft List by November 1st, revised list in March, final updated for annual report. | City Staff - Public Works, Parks, Planning, and Engineering. | Annually
|  | 2. Work with the Josephine SWCD, RVCOG, Grants Pass Irrigation District, OSU Extension, the Rogue River Watershed Council, the Rogue Basin Partnership, Middle Rogue Steelheaders Assoc, RCC and/or local schools to implement and promote TMDL programs. | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Annually
|  | 3. Identify resources available for program (e.g. staff hours, available funds, etc.) and program needs (gaps). | 3. Summary of available resources and needs. | Public Works Staff, Engineering and Planning Staff | Annually
|  | 4. Review existing code and ordinances to evaluate the status of other TMDL related concerns from DEQ's Key Strategies for Rogue River Implementation that are not addressed in other matrix sections including Floodway/Floodplains and wetlands. | 4. Summary of existing code sections and potential changes or additions that may be needed. | Public Works Staff, Engineering and Planning Staff | Year 1
|  | 5. Review existing code and enforcement procedures to evaluate adequacy to address riparian and wetland issues and other TMDL related concerns. | 5. Summary of existing code and identify sections that may need to be revised and/or updated. | Public Works Staff, Engineering and Planning Staff | Year 1
| B. Update codes, ordinance, and other programs (e.g. incentives) as needed to assist in program implementation. | 1. Develop an schedule of anticipated TMDL needs including code and ordinance revision and other activities. | 1. Summary included in annual report/matrix. | City Staff - Public Works, Parks, Planning, and Engineering. | Year 2-3
|  | 2. Modify matrix with proposed schedule for revisions and other activities. Potential activities may include revising/updating/creating floodway and floodplain protection, wetland protection, and incentives for riparian protection | 2. List of groups, contact information, etc. | Public Works Staff, Engineering and Planning Staff, RVCOG | Years 3-4
II. Solar Radiation – Near-Stream vegetation disturbance/ removal. Increase effective shade through restoration and protection. | A. Continue to identify and inventory new areas to restore, plant, and protect by reviewing and updating maps, lists, and/or other materials as needed. | 1. Continue to use open space, public lands, wetlands and parks inventories, watershed assessments, local knowledge, and GIS maps to identify areas. | 1. Updated maps, lists, and/or other materials. Shape files will be created for identified areas. Shape file attributes will be updated as sites are prioritized, invasives are removed, and/or the sites are planted. | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually
| B. Prioritize any newly identify areas. | 1. Use established criteria to prioritize identified sites. As of 2014, the prioritization criteria outlined in 2010 Bear Creek and Rogue Basin Riparian Planting Plan are being used to prioritize sites. | 1. Updated summary/list of prioritized sites as needed. | City Staff - Public Works, Parks, Planning, and Engineering, RVCOG, other partners. | Annually
|  | 2. Field check prioritized areas to verify needs for implementation. | 2. Summary of field checks completed | Public Works Staff, Parks Staff, Engineering and Planning Staff | Annually
| C. Restore, protect, and plant areas. | 1. Seek opportunities to plant native trees and shrubs in public areas, open spaces, city parks and along streams and rivers. Specific creeks to evaluate include Gilbert Cr., Skunk Cr., Mill Cr., Grouse Cr., Jones Cr., Sand Cr. and the Rogue River along City Park property. | 1. List of areas planted including numbers of trees and shrubs. In addition, create shape files of areas planted. | Public Works Staff, Parks Staff, Public Contracts, Volunteers, County work crews, RVCOG, Partners | Annually
|  | 2. Identify partnering opportunities, for public and private lands, during each plan year by contacting local groups (the Rogue Basin Partnership, Rogue River Watershed Council, Middle Rogue Steelheaders, Roe Motors, Josephine SWCD, Josephine County Public Works, local volunteer groups and schools) and summarizing project opportunities. | 2. Summary of opportunities available. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually
|  | 3. Work with local groups to schedule and complete projects annually as time and funding permit. | 3. Summary of projects scheduled and completed including number and locations of trees and shrubs planted. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually
|  | 4. Evaluate funding options for restoring, planting, and protecting priority sites and pursue finding options as time and resources permit. | 4. Summary of funding sources identified, applications submitted, and funding received. | Public Works Staff, Parks Staff, RVCOG, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually
| D. Riparian Ordinance –Evaluate, strengthen, or develop riparian ordinances as needed (Goal 5) to protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under the City of Grants Pass jurisdiction. | 1. Draft new ordinances or revise ordinance as needed based on recommendations from earlier TMDL reports and/or other programs. | 1. Completed draft ordinance. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations.
|  | 2. Public notice of new or revised ordinances and Grants Pass review procedure. | 2. Summary of noticing and procedures used to move the ordinance towards adoption. | Public Works Staff, Engineering and Planning Staff | Pending, based on new Phase II regulations.
|  | 3. Adopt new ordinances or revised ordinances as needed. | 3. Adopted ordinances or ordinance revisions. | Public Works, Planning and Engineering Staff, Public Safety and Code Enforcement | Pending, based on new Phase II regulations.
III. Solar Radiation –Near stream vegetation disturbance - overrun by invasive species. | A. Continue to implement invasive species management programs in public areas. | 1. Manage invasive species in parks and other City owned properties. | 1. Summary of acres of invasive areas treated. | Public Works Staff, Engineering, Planning Staff, Volunteers, Partners. | Annually
|  | 2. Train staff on noxious/invasive weeds including identification and treatment options. | 2. Summary of any training conducted, promoted, or that staff was sent to. | City Staff | Annually
|  | 3 Work with watershed groups to manage invasive species on private land and protect and/or plant native species in riparian areas where invasives are removed. | 3. Number of trees and shrubs planted annually. Number of acres of invasives removed. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually
|  | 4. Coordinate invasive weed management activities with the County Weed Management Area. | 4. Activity Summary. | Public Works Staff, Parks Staff, Josephine County Public Works, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually
IV. Other Anthropogenic Sources: Urban Runoff – Reduce runoff, promote infiltration and low impact development practices. | A. Promote the use of methods and practices that reduce urban runoff and impervious surface area. | 1. Create or update map locations where low impact development practices are being used or will be used to reduce urban runoff and creation of impervious surface area. | 1. Map of Locations. | Public Works Staff, Planning and Engineering Staff | Annually
|  | 2. Work with the development of the stormwater program (V) to revise codes and ordinances revision to incorporate low impact development practices. | 2. Summary of revised code. | Public Works, Planning and Engineering Staff | Annually - summary after NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 3. Require new construction to minimize impervious surface and treat stormwater onsite using LID techniques or other appropriate methods. | 3. Summary of requirements. | Public Works, Planning and Engineering Staff | Incorporate in V.
V. Other Anthropogenic Sources: Urban Runoff – Stormwater Management Program. | A. Develop a stormwater management program addressing the six elements of Phase II Stormwater Management. | 1. Outline existing programs that meet each of the six minimum control measures for NPDES Phase II Stormwater Management. | 1. Existing program summary. | Public Works, Planning and Engineering Staff | Year 1
|  | 2. Identify gaps, needs, and next steps needed to develop program. | 2. Summary of gaps and next steps. | Public Works, Planning and Engineering Staff | Year 2
|  | 3. Develop or adopt a Storm and Surface Water standards manual | 3. Draft manual (year 4) and completed manual (year 5) | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 4. Develop a Pollution Prevention/Good Housekeeping Program | 4. Summary of Program | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 5. Develop and implement an erosion prevention and sediment control program. | 5. Summary of programs and procedures. | Public Works Staff, Planning and Engineering Staff | Year 1
|  | 6. Provide incentives to developers and homeowners to install or retrofit landscapes and to provide on-site stormwater treatment and detention. | 6. Summary of incentives | Public Works, Planning and Engineering Staff | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 7. Revise and update maintenance program for existing stormwater management structures or features. | 7. Revise and update training and education programs for maintenance and a schedule for inspection and maintenance as needed. | Public Works, Planning and Engineering Staff | Annually
VI. Fecal Sources: Animal waste management – pet, wildlife, and livestock waste. Properly manage animal waste. | A. Provide bags for dog owners to pick up pet waste. | 1. Update inventory of parks / public areas that have pet waste disposal dispensers. | 1. List of parks and public areas with pet waste disposal dispensers | Public Works and Parks Staff | Annually
|  | 2. Identify additional areas where bag dispensers are scheduled to be or have been placed since the previous inventory. | 2. Document number of bags provided and number and location of new bag dispensers in annual report. | Public Works and Parks Staff | Annually
| B. Develop partnerships with SWCDs, ODA, and other groups to work on animal waste management programs in agricultural areas. | 1. Summary of any programs indentified addressing animal waste management with landowners, agriculture, ODA, IDs, County programs, and other groups. | 1. Summary of programs | Public Works and Parks Staff | Annually
|  | 2. Partner with local groups to encourage proper manure, upland irrigation and nutrient management. | 2. Summary of partnerships. | Public Works Staff, Parks Staff, Josephine County Soil and Water, Middle Rogue Steelheaders, Local Volunteer groups. | Annually
VII. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | A. Establish and/or refine illegal dumping/illicit discharge detection and elimination (IDDE) program. | 1. Create, adopt, or revise and strengthen IDDE program as needed. The development of program with element V. Development of a Stormwater Management Program. | 1. Summary of IDDE program. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 2. Implement IDDE program | 2. Program implementation summary. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 3. Create, update, or refine storm drain system map for the City. | 3. A summary of the existing status of the storm drainage system mapping including what format it's in, any updates, and if not completed, a general strategy for completing the mapping. | Public Works, Engineering and Planning Staff. | Completed once NPDES Phase II rules finalized by DEQ and implemented in the City. Anticipated year 3-4.
|  | 4. Evaluate the use of stormwater system maps to assist in identifying illegal dumping and sources of bacteria. Revise and/or create maps or use existing maps. | 4. Map identified areas of high bacteria. | Public Works, Engineering and Planning Staff. | Completed after VII.A.3 is completed.
|  | 5. Track any IDDE concerns reported in the City. | 5. Summaries of any concerns identified, tracked, and/or reported. | Public Works, Engineering and Planning Staff. RVCOG, DEQ, other partners. | Annually
|  | 6. Enforce illegal dumping as identified or found. | 6. Description of enforcement including number of contacts made, warnings issue and fines levied. | Public Works (Drainage and Utilities) and Engineering Staff and Public Safety. | Annually
VIII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | A. Notify DEQ of failing systems when found. | 1. The City of Grants Pass will notify DEQ of failing systems when found. | 1. Summarized referrals. | Public Works (Drainage and Utilities) and Engineering Staff. RVCOG. | Annually
IX. Outreach and Education | A. Continue to implement outreach strategy that addresses water quality parameters in the TMDL. | 1. Review materials (e.g., brochures, activities, web sites) from educational programs. | 1. Summary of review in annual report including examples of materials and/or links. | Public Works and Engineering Staff, RVCOG | Annually
|  | 2. Adopt, customize, and/or develop regional materials from programs reviewed. | 2. Copies of information created, customized, and/or distributed. | Public Works and Engineering Staff, RVCOG | Annually
|  | 3. Promote local and/or regional success stories as applicable by preparing information for summary on websites and contacting media outlets. | 3. Summary of information on regional projects. | Public Works and Engineering Staff, RVCOG | Annually
|  | 4. Participate in regional education opportunities with other groups and DMAs in the Rogue Basin. | 4. List of activities. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually
| B. Hold, participate in, and/or promote annual water quality events. | 1. Update list of annual events related to water quality, riparian planting, the benefits of healthy riparian areas, native plants and other TMDL topics. | 1. Event list or summary of events in annual report. | Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually
| C. Provide citizens, landowners and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. Revise and update list of local agencies, nurseries, and other resources for planting as needed. | 1. Summary of updates and/or updated list of resources including contact information and location. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually
|  | 2. Distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually
|  | 3. Coordinate partnerships with DMAs and other organizations to provide technical assistance and other resources as needed. | 3. Document technical assistance and resources provided, including the number of any plants distributed and associated planting locations. | Public Works and Engineering Staff, RVCOG, Local Watershed groups, Josephine SWCD | Annually
| D. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Continue to target areas of high animal usage including public areas near waterways and dog oriented businesses. | 1. Activity summary in annual report. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually
|  | 2. Collect, develop, and/or distribute brochures, pamphlets and other materials to target areas. | 2. Documentation of materials distributed. | ODA, Public Works and Engineering Staff, RVCOG, Local Watershed groups | Annually
| E. Provide outreach and technical assistance to private landowners and the public above the removal of invasives and weed control. | 1. Work with the Josephine County Weed Management Area (CWMA), O.S.U. Extension, and/or other groups working on weeds to provide technical assistance, educational opportunities, and/or materials on managing invasive weeds. | 1. Summary of activity with groups including any meetings attended, materials collected and distributed, contacts made, and documentation of any assistance provided. | Public Works and Engineering Staff, RVCOG, CWMA, OSU Extension, other local groups | Annually
|  | 2. Promote and/or support activities for the public to participate in opportunities to learn about weeds and participate in training and events related to invasive weed control. | 2. List of events promoted, supported, and/or attended by staff or a city representative (e.g., RVCOG). Potential events include the Annual Josephine County Weed Pull, and OSU's Land Steward workshops. | Public Works and Engineering Staff, RVCOG, CWMA, other local groups | Annually
| F Staff Training | 1. Train staff as needed on topics related to TMDL Implementation. (Include Management Staff and Elected Officials) | 1. List of how training was conducted and frequency. | Public Works, Planning, Building and Engineering Staff | Annually
X. Regional Water Quality Coordination | A. Continue participation in the TMDL program. | 1. The City of Grants Pass will continue participation in the TMDL program. | 1. Attendance (in person, phone or video conferencing if available) at quarterly meeting and other meetings as requested. | Public Works, Planning, Building and Engineering Staff | Annually
XI. Funding | A. Evaluate the costs of program implementation. | 1. Establish costs of program implementation for the next plan year and identify funding sources as needed including staff time, grant funding, and other resources. | 2. List program costs and sources (e.g., staff time, direct funding, grants, etc.). | Public Works, Planning, Building and Engineering Staff | Annually
| B. Identify program funding opportunities. | 1. Evaluate existing resources available to begin program implementation. | 1. Summary of existing resources used. | Public Works Staff, RVCOG, Local Watershed groups | Annually
|  | 2. Provide an inventory of funding, potential Regional Program grants. | 2. List of identified funding sources and deadlines provided to The City of Grants Pass and other agencies. | Public Works Staff, RVCOG, Local Watershed groups | Annually
|  | 3. Collectively (regionally) apply for funding for implementation and region-wide projects. | List of participation in regional implementation opportunities. | Public Works Staff, RVCOG, Local Watershed groups | Annually
|  | 4. Document any funding and/or in-kind support for projects or partner projects. | List of funding and in-kind support. | Public Works Staff, RVCOG, Local Watershed groups | Annually
XII. Monitoring and Reporting | A. Use the matrix as a template to track the implementation plan. | 1. Compile information from completed activities into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually
| B. Submit annual reports to DEQ. | 1. Submit annual reports to DEQ. | 1. Completed annual reports submitted to DEQ by September 30 of each year, reporting on implementation actions for the July 1-June 30 plan year. | Public Works Staff, Parks, Engineering and Planning Staff and Public Safety | Annually, September 30 of each year.
| C. Use existing programs to track program effectiveness. | 1. Work with DEQ, RVCOG, and other DMAs to evaluate methods for evaluating and tracking program effectiveness. | 1. Summary of methods evaluation. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually
|  | 2. Work with DEQ, RVCOG, and other DMAs to use existing programs (DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. | 2. Summary of regional water quality. | Public Works Staff, Parks, Engineering Staff, RVCOG, other DMAs. | Annually
| D. Adaptive Management Plan. This is an ongoing plan and modifications and adjustments will take place. | 1. Modify plans as needed. | 1. Summary of any revisions to Water Quality Implementation Plans. | Public Works, Planning, Engineering Staff, RVCOG, other DMAs. | Annually
Note on C27: gstabach:III.A.3 and II.A.4 were the same so I deleted one.

## Annual Activity Summary
Summary Information
General Statistics
Date | Event/Activity | Time and Location (if needed) | Description
2020-07-20 | Interview with JPR regarding Water Quality Monitoring and Bacteria. To air 7/24/20. | 3:00 p.m. - 3:30 p.m.
2021-07-15 | Quarterly TMDL Meeting | 1:00 pm to 3:00 pm
2020-07-20 | Interview with JPR regarding Water Quality Monitoring and Bacteria. To air 7/24/20. | 3:00 p.m. - 3:30 p.m.
2020-07-22 | Loaned tools for an English Ivy Pull
2020-08-11 | Rogue Basin Partnership (RBP) Meeting | 10:00 a.m. - 12:00 p.m.
2020-09-16 | Stream Smart Quarterly Meeting | 9:00 a.m. - 11:00 a.m. | Discussed bylaws, website updates, making the website live, and the pledg updates
2020-09-18 | Harmful Algal Bloom Workshop Call
2020-09-28 | Southern Oregon Family - Do Your Part and Be Stream Smart! Article |  | https://southernoregonfamily.com/do-your-part-and-be-stream-smart/?fbclid=IwAR09LkFO-txlMumvT0lN7hSZg2aXL7pqchJsOw8YyqlZClch7aldNDnNx2M
2020-10-06 | Grants Pass Restoration Surveys | 10:00 a.m. - 12:30 p.m. | Using Survey 1-2-3, logged surveys for potential restoration sites, pollinator patches, clean-ups within Grants Pass and Josephine County.
2020-10-08 | Grants Pass Restoration Surveys | 1:00 p.m. - 1:45 p.m. | Using Survey 1-2-3, logged surveys for potential restoration sites, pollinator patches, clean-ups within Grants Pass and Josephine County.
2020-10-13 | Equipment on Loan - RRK |  | Loaning older model turbidimeter, thermometer, and conductivity meter to Sara Mosser with RRK for Almeda Fire WQ Monitoring field run.
2020-10-21 | Quarterly TMDL Meeting | 1:00 p.m. - 3:30 p.m.
2020-10-22 | Tools on Loan - Kristi Reynolds
2020-11-05 | Emergency Watershed Monitoring Meeting | 11:00 a.m. - 12:00 p.m. | Sub-group from the post-fire water quality meeting group that will focus on formulating a grant proposal to the Oregon Health Authority for funding to purchase a continuous turbidity and dissolved organic carbon sonde. This will help with monitoring the effects of the Almeda and Obenchain fires.
2020-11-05 | Mail Tribune - Greenway Crews Prepare Erosion Areas for Rain Article |  | https://mailtribune.com/news/top-stories/greenway-crews-prepare-erosion-areas-for-rain?fbclid=IwAR3sttjczzWgFoK5eCYRIvW8z6hWCTQUdWxyPbIwbrP1k37yetH-R0sjpiQ
2020-11-05 | NBC 5 - Volunteers Needed Article |  | https://kobi5.com/news/volunteers-needed-to-help-prep-bear-creek-greenway-for-winter-139916/
2020-11-06 | NBC 5 - Greenway Articles |  | https://kobi5.com/tag/greenway/
2020-11-10 | Rogue Drinking Water Partnership (RDWP) Meeting | 1:00 p.m. - 3:00 p.m.
2020-11-12 | Salmon Watch Interactive | 10:00 a.m. to Noon | Pilot interactive program for the Salmon Watch Program with Alyssum Barber from McGloughlin Middle School and students from Grants Pass, Talent, Phoenix, and Medford.
2020-12-04 | Clean Rivers Coalition Forum |  | Attended the Clean Rivers Coalition to learn more about the statewide education program, the campaigns, how it might be used locally, and how it might tie into our education and outreach programs for TMDL and stormwater.
2020-12-16 | Stream Smart Quarterly Meeting | 9 am to 11 am | Stream Smart Advisory Committee Quarterly Meeting
2021-01-13 | Rogue Basin Wildfires and Drinking Water Supplies Workshop | 8:30 a.m. - 4:00 p.m.
2021-01-19 | Almeda Fire - Water Quality Monitoring Meeting | 1:00 p.m. - 2:00 p.m.
2021-01-20 | Rogue Basin Quarterly TMDL Meeting | 1:00 p.m. to 3:00 p.m. Zoom | Major discussion points of the meeting centered around the Almeda Fire and ETART response.
2021-01-25 | Southern Oregon Regional Environmental education Leaders) SOREEL Winter Meeting | 10:00 a.m. to 11:00 a.m.
2021-02-01 | Salmon Watch Meeting | 10:00-10:30 | Discussed salmon watch for the spring of 2021
2021-02-09 | County Weed Management Area (CWMA) Meeting | 3:00 p.m. - 4:00 p.m. | Mentioned the Rogue River Clean-Up and interest in partnering up with the JoCo CWMA, as well as the ivy and garlic mustard pulling event in Grants Pass with Dutch Bros. volunteers.
2021-02-22 | Volunteer Event Zoom Call with Dutch Bros. Engagement | 2:30 p.m. - 2:45 p.m. | Discussed ivy and garlic mustard pulling activities, as well as park clean-up activities. Dutch Bros. will determine which date in late March/early April will work for them.
2021-03-09 | Volunteer Event Zoom Call with Dutch Bros. Engagement | 11:00 a.m. - 11:15 a.m. | English Ivy/Garlic Mustard pulling event scheduled for Wednesday, April 7th; a clean-up event is being organized for Thursday, April 22nd at two park locations.
2021-03-10 | Rogue River Clean-up (RRCU) Meeting with JoCo Parks | 10:30 a.m. - 11:30 a.m.
2021-03-11 | Salmon Watch Kits loaned to Applegate Partnership for Programs | 9:30 a.m.
2021-03-17 | Stream Smart Quarterly Meeting | 10:00 a.m. - 11:30 a.m.
2021-03-24 | RVCOG Board Meeting | 12:00 p.m. - 1:00 p.m. | Presented on the work of the Bear Creek Stewards, the next Bear Creek Stewardship Day Clean-Ups, and the Rogue River Clean-Up, and how these events fit into TMDL, stormwater, public outreach and education, and volunteer work and opportunities.
2021-04-07 | Dutch Bros. English Ivy and Garlic Mustard Pulling Event | 9:00 a.m. - 11:00 a.m., 1:00 p.m. - 3:00 p.m. | 20
2021-04-07 | Southern Oregon Regional Envirothon Host - Aquatic Ecology | 8:00 a.m. to 12:00 p.m.
2021-04-14 | Clean-Up Supply Pick-Up | 1:00 p.m. - 4:30 p.m.
2021-04-20 | Salmon Watch Virtual Session - Test
2021-04-21 | TMDL Quarterly Meeting
2021-04-22 | Dutch Bros. Trash Clean-Up | 9:00 a.m. - 11:00 a.m., 1:00 p.m. - 3:00 p.m. | 21
2021-04-24 | EcoQuest Earth Day Activity - Pine Street | 10:00 a.m. - 12:30 p.m.
2021-04-27 | Salmon Watch Virtual Session |  | At Bear Creek Park
2021-04-28 | Salmon Watch Virtual Session |  | At Bear Creek Park
2021-04-28 | RDWP Meeting | 1:00 p.m. - 3:00 p.m.
2021-04-29 | Salmon Watch Virtual Session |  | At Bear Creek Park
2021-05-04 | Kids Unlimited Salmon Watch Session | 9:30 a.m. - 1:30 p.m.
2021-05-05 | Meeting with Josephine County Parks | 3:30 p.m. | At TouVelle State Park
2021-05-13 | Kids Unlimited Salmon Watch Session | 9:30 a.m. - 1:30 p.m. | At TouVelle State Park
2021-05-17 | Salmon Watch Session at Scenic Middle School
2021-05-17 | Salmon Watch Session at Scenic Middle School
2021-05-18 | Salmon Watch Session at Scenic Middle School
2021-05-18 | Salmon Watch Session at Scenic Middle School
2021-05-19 | Salmon Watch Session at Scenic Middle School
2021-05-20 | Salmon Watch Session at Scenic Middle School
2021-05-20 | Salmonwatch Session with McGloughlin Middle School |  | At TouVelle State Park
2021-05-21 | Salmonwatch Session with McGloughlin Middle School | 9:50 a.m. - 1:00 p.m. | At TouVelle State Park
2021-05-21 | Salmon Watch Session at Scenic Middle School
2021-05-22 | 29th Annual Rogue River Clean-Up | 8:30 a.m. - 12:00 p.m. | Attendance of about 60 people. 15 cubic yards of trash picked up, and invasive weeds removed.
2021-06-02 | Careers in Technical Education (CTE) Board Meeting | 9:00 a.m. - 10:00 a.m. | RVCOG serves on the board of the CTE program for Crater Renaisasance Academy. The program is focused on providing training for students for future careers in natural resources including water quality work, watershed stewardship, education, stormwater/urban runoof, and restoration.