## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Provide pet waste bags and trash cans for pet owners at local parks and public areas for owners to pick up after their pets. RM support as requested. | Staff Time | Track number of stations maintained and bags ordered. Any new stations will be added to existing inventories and maps. | Ongoing (annually) | Summary in annual report. Data submitted to regional manager (RM) will be summarized in the regional report. In addition, data provided in an ESRI or Google Earth Format will be added to the TMDL tracking maps on ArcGIS. As needed the RM can assist DMAs with surveying, tracking, mapping, and reporting. | Year 1: July 2025-June 2026 - Data was received from the City of Jacksonville and included in their report. The City purchased 40 cases of bags (2,000 bags per case) for the stations located throughout the City at a cost of $2,239.20. Information on surveys and maps can be found on the Tracking_Reporting_Surveys_Map tab.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Urban Runoff (ties to/supports Phase II programs and/or provides meeting basic goals for DMAs that are not MS4s) | Reduce runoff volume. Post Construction | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. RM support as requested. | Staff Time, Project Funding (utility fees & grants as applicable) | Track any features installed, detailing the size and treatment expectations as designed. | Ongoing as development occurs. | This strategy is dependent on funding availability for funding designs and construction of capital improvements, as well as private investment in new and redevelopment projects. Report and map features installed and maintained. As requested, RM can pursue funding for project implementation. Information/updates will be posted online. In addition, RM will map and track as needed including using forms designed in Survey 123 designed for tracking these features. Annual reports will summarize activity and provide links to relevant maps and spreadsheets. | Year 1: July 2025-June 2026 - No features were tracked by the RM during the implementation year. Information on surveys and maps can be found on the Tracking_Reporting_Surveys_Map tab. Refer to MS4 reports for detailed information.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education activities through DMA channels, with partners, and RVCOG through the Stream Smart Program. | Staff time, Project Funding Work with RVCOG (SW Utility Fees, grants as applicable). | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed | Ongoing once the program is established. | Number of projects: number of downspouts disconnected, rain gardens constructed. Information on rain gardens, downspout disconnects, and other measures will be added to or updated on the Stream Smart website. In addition, Stream Smart can host workshops as requested and promote events through the Stream Smart website and social media platforms. The needs tie directly to the stormwater pledge program. Information will also be tie to the stormwater pages on the RVCOG website. RM will report on annual regional activities. | Year 1: July 2025-June 2026- The RM works with DMAs, MS4s, and regional partners on the Stream Smart Program. Stormwater content is included on the Stream Smart website (including the Rain Garden Guide) and social media campaigns. In addition, the RM coordinates with the Regional Stormwater Advisory Team (SWAT), the Statewide Clean Rivers Coalition (CRC), and other partners to expand the reach of the outreach and educational programs. The Stream Smart events page also includes any available trainings. No disconnects, rain gardens, or workshops were hosted during the implementation year. Stormwater content including rain gardens, reducing impervious surface areas, and native plants were included at the Ashland CO-OP presentations, clean-ups, meetings onsite with St. Mary's regarding a Stream Steward program, and at Crater High School's Renaissance Academy Envirothon Club presentation. Additionally, native pollinator species were incorporated into stormwater facilities. Overall, 6 related presentations and projects were completed.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Implement WQ BMPs identified in the DMAs Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. RM has survey forms available for tracking and can assist with tracking and mapping activities. | Year 1: July 2025-June 2026 - No features were tracked by the RM during the implementation year. Information on surveys and maps can be found on the Tracking_Reporting_Surveys_Map tab. Refer to MS4 reports for detailed information.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Lead by Example - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage sediment controls, street sweeping to prevent pollution to the maximum extent practicable. RM support as requested. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. RM can organize workshops through RVPSA or another venue as needed. In addition, RM can assist DMAs in summarizing existing procedures or recommending practices. RM participated in the Eco Biz training. | Year 1: July 2025-June 2026 - No activity completed by the RM in 2025-2026.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain) part of the RVCOG Monitoring program. | Review and refine illicit discharge and hot spot water sampling program as needed. RM will continue the storm drain and hot spot monitoring program that is part of the TMDL monitoring program. | RVCOG (RM) - This is included for all DMAs that participate in the Regional Monitoring Program. Staff Time to follow up on DMA specific concerns. | As part of the regional monitoring program, RVCOG staff respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program. In addition, we also investigate concerns reported to us by the public, DMAs, partners, and agencies. We also conduct monitoring on storm drains throughout the watershed 3 times during the implementation year. Visual inspections occur as part of the site visit and the RM will document the inspections once per implementation year using Survey 1-2-3. | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis. Document concerns as appropriate using the hot spot monitoring forms. Annual report generated by RVCOG for regional activity. Hot Spot map updated as new reports are submitted. Data summary of all monitoring included in the annual report and links to the survey form for the storm drain inspections. | Year 1: July 2025-June 2026 - - As part of the annual TMDL program, the RM serves as a point of contact for water quality concerns and also investigates specific concerns on a limited basis. Investigations include additional sampling, tracking of the source, documentation, and reporting to the appropriate agencies based on the nature of the concern. Additionally, DMAs responds to reported concerns within jurisdictional limits and forwards concerns onto OERS, DEQ, the RM, or others as appropriate. Hot spot and storm drain survey forms are in the Tracking_Reporting_Surveys_Maps tab. A storm drain data summary is included in the Storm Drain Tab. Complete storm drain data is in the Storm Drain Monitoring Data and Trends attachment located on https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/ .
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations (MS4s). | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Update on the number investigations and any enforcement actions taken. This could be summarized in the NPDES Phase II program report if applicable. | Year 1: July 2025-June 2026 - In 2025-2026, 5 hot spots were followed up and documented by the RM (see hot spot tab). Refer to the Hot Spots 2025-2026 tab for more information.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Erosion Prevention and Sediment Control | Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. This could be summarized in the NPDES Phase II program report if applicable. | Year 1: July 2025-June 2026 - The RM tracks and refers any calls received or field observations to the appropriate agency or jurisdiction. Action summaries in MS4 reports.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Septic Systems | Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time, RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. Any calls received regarding septic concerns will be logged, followed up ,and reported as part of the hot spot monitoring program as appropriate. In addition, monitoring results (bacteria) will also be reviewed periodically to identify areas of high bacteria levels. | Year 1: July 2025-June 2026 - No septic systems were identified and no calls were received. In reviewing the monitoring data throughout the year, no results stood out for further investigation. New technology (e DNA) is being evaluated for use in identifying underlying bacteria concerns. The methodology was tested in the Wagner Creek hot spot. Bacteria trends can be found in the Bacteria Trends Tab and all monitoring data for streams and storm drains in the region can be found on the City Water Quality Page (https://rvcog.org/jacksonville-water-quality-page/).
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Regional sources - Effectiveness Monitoring | Monitor and maintain awareness of bacteria levels in the Bear Creek watershed by monitoring creek sites and storm drains. | Monitor Creek temperatures. RM will continue conducting the water quality monitoring program. | RVCOG, Staff time for additional sampling outside of the monitoring program | Regional | Ongoing | Annual completion of monthly sampling and analysis for creek sites, and storm drains three times during the implementation year. | Year 1: July 2025-June 2026 - Completed. RM conducts stream monitoring monthly in streams throughout the Bear Creek Watershed. Storm drains are monitored three times during the implementation year to look at the impact of TMDL parameters during dry conditions, a flushing event, and a large storm event. The E Coli Data Summaries (stream) tab has exceedance data for all stations in the summer and winter seasons and the E. coli trends (stream) has graphs of results from all stream stations. The Storm Drain Data 2025-2026 tab has exceedance data for all stations in the summer and winter seasons and the E. coli trends (storm) has graphs of results from all stream stations. Results of the monthly sampling is sent to DMAs quarterly and storm drains annually once all runs are completed.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. The RM will work with DMAs to explore new topics at TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the TMDL program. | Staff time, RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. The RM (RVCOG) will work with DMAs to bring new topics to TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the bacteria TMDL. | Year 1: July 2025-June 2026 - In 2025 and 2026, the RM, DMAs, and regional partners evaluated the use of eDNA to evaluate underlying causes of bacteria concerns. Information on the technology was presented at TMDL meetings, at hot spot meetings, and was used on Wagner Creek to evaluate the underlying causes of a "hot spot".
Year 2: July 2026-June 2028
Year 3: July 2027-June 2029
Year 4: July 2028-June 2030
Year 5: July 2029-June 2031

## Tracking_Reporting_Surveys_Maps
Map/Survey | Description | Survey Link | Results Link | Map
TMDL Project Implementation Tracking | Survey 123 form and ArcGIS map of results tracking selected ongoing TMDL Implementation and MS4 projects. | https://arcg.is/1eiPrO2 | https://arcg.is/fiijS | https://arcg.is/0TXaz80
Hot Spot Survey Form | Forms and maps for tracking hot spots reported to the RM or observed in the field. Includes follow up notes, pictures, and other information. | https://arcg.is/0nHOv0 | https://arcg.is/00TWeD
Storm Drain Monitoring and Inspection form | Form for documenting annual storm drain visits. | https://arcg.is/W0juz | https://arcg.is/1LTSKW0
Garlic Mustard | Summary of the CWMA Garlic Mustard Program including sites in and near Grants Pass. |  |  | https://storymaps.arcgis.com/stories/8195d7393fe14fc6aa74d94f74f30d88
Water Primrose and Parrotfeather | Summary and map of RAIN work on the Rogue River to treat target aquatic weeds. Program has expanded to include mussels, snails, and other species. |  |  | https://storymaps.arcgis.com/stories/4d5ef77af504406e9d07ed00458f2a26

## Hot Spots 2025-2026
Summary Information
General Statistics
Date | Event/Activity | Description
2025-07-02 | Hot Spot - Elk Creek Campground | Caller stated that a large group of people swam in Elk Creek and then displayed vomiting and diarrhea. Jackson County Public Health was informed and reached out to the caller. This incident was deemed unrelated to the water quality in Elk Creek and rather norovirus.
2025-08-25 | Hot Spot - Wagner Creek E. coli & eDNA Sampling | Concern from Rogue River Keeper regarding high bacteria levels recorded in Wagner Creek above City limits. Reports led to discussion with RRK, RVSS, DEQ, ODA, and Jackson SWCD. Resolution was to conduct sampling of EDNA and bacteria on the creek and investigate the underlying cause. The TMDL "hot spot" program supported the sample collection and bacteria anaylsis, RVSS paid for the eDNA analysis, and Jackson SWCD provided materials.
2025-08-29 | Hot Spot - Wagner Creek E. coli & eDNA Sampling | Concern from Rogue River Keeper regarding high bacteria levels recorded in Wagner Creek above City limits. Reports led to discussion with RRK, RVSS, DEQ, ODA, and Jackson SWCD. Resolution was to conduct sampling of EDNA and bacteria on the creek and investigate the underlying cause. The TMDL "hot spot" program supported the sample collection and bacteria anaylsis, RVSS paid for the eDNA analysis, and Jackson SWCD provided materials.
2025-09-29 | Hot Spot - Talent - Garbage/Graywater Dumping | RM received a call regarding a garbage and graywater dumping onto the Bear Creek Greenway from the trailer park near the Talent Truck Stop. Amie was out on the TMDL Run and investigated. Photos were taken and this was then reported to DEQ and RVSS. Bill followed up with the complainant.
2025-11-15 | Hot Spot - Skunk Creek (Grants Pass) | While out on the Stream Smart Adopt-A-Street section picking up trash, soap suds were observed in the water of Skunk Creek (11/15/25). On 11/17/25, RVCOG notified City of Grants Pass Public Works. City of GP said they would investigate, although this is a longstanding issue that they haven't been able to track down.
2025-12-03 | eDNA Meeting - Wagner Creek | Post sampling meeting to discuss results and next steps.
2026-03-03 | eDNA Meeting (Wagner Creek) | Post sampling meeting to discuss results and next steps.
2026-03-04 | Hot Spot - White City | Turbid brown/yellowish discharge noted in a sgtorm drain in White City off Pacific Avenue near Carestream as part of the Stormwater Patrol. Contacted RVSS and MWC. RVSS investigated and found it was the result of gold minimg being done in a parking lot. High pressure water was being used to wash river rock. Mining activity ceased after visit from RVSS and no further activity has been noted on monthly stormwater patrols to date.

## E coli Data Summaries (stream)
Summer Exceedance: May 1 - October 31 | [5 empty] | Winter Exceedance: November 1 - April 30
Site # | Location | E. coli Exceedance at Standard (406 MPN) | Count | WQ % | WQ Grade | Site # | Location | E. coli Exceedance at Standard (406 MPN) | Count
E1 | Walker Ck. @ Belle Fiore | 40% | 2/5 | 60% | D | E1 | Walker Ck. @ Belle Fiore | 0% | 0/6
E3 | Neil Ck. @ Dead Indian Memorial | 50% | 3/6 | 50% | F | E3 | Neil Ck. @ Dead Indian Memorial | 0% | 0/6
E4 | Ashland Ck. @ Granite St. | 0% | 0/2 | 100% | A | E4 | Ashland Ck. @ Granite St. | 0% | 0/3
E5 | Ashland Ck. below STP | 40% | 2/5 | 60% | D | E5 | Ashland Ck. below STP | 0% | 0/6
E6 | TID Canal @ Eagle Mill Rd. | 0% | 0/4 | 100% | A | E6 | TID Canal @ Eagle Mill Rd. | - | -
E7 | Bear Ck. @ S. Valley View Rd. | 16.67% | 1/6 | 83% | B | E7 | Bear Ck. @ S. Valley View Rd. | 0% | 0/6
E8 | Bear Ck. @ Greenway (S. Talent) | 33.33% | 1/3 | 67% | D | E8 | Bear Ck. @ Greenway (S. Talent) | 0% | 0/5
E9 | Bear Ck. @ Lynn Newbry Park | 16.67% | 1/6 | 83% | B | E9 | Bear Ck. @ Lynn Newbry Park | 0% | 0/6
E10 | MID Diversion @ Suncrest Rd. | 60% | 3/5 | 40% | F | E10 | MID Diversion @ Suncrest Rd. | - | -
E11 | Bear Ck. @ B. H. Park (Phoenix) | 66.67% | 4/6 | 33% | F | E11 | Bear Ck. @ B. H. Park (Phoenix) | 16.67% | 1/6
E12 | Bear Ck. @ Fern Valley Rd. | 50% | 3/6 | 50% | F | E12 | Bear Ck. @ Fern Valley Rd. | 16.67% | 1/6
E13 | Bear Ck. @ JNC (S. Medford) | 16.67% | 1/6 | 83% | B | E13 | Bear Ck. @ JNC (S. Medford) | 16.67% | 1/6
E14 | Bear Ck. @ 9th St. (Medford) | 33.33% | 2/6 | 67% | D | E14 | Bear Ck. @ 9th St. (Medford) | 16.67% | 1/6
E15 | Bear Ck. @ Table Rock Rd. | 50% | 3/6 | 50% | F | E15 | Bear Ck. @ Table Rock Rd. | 33.33% | 2/6
E16 | Griffin Ck. @ Beall Ln. | 16.67% | 1/6 | 83% | B | E16 | Griffin Ck. @ Beall Ln. | 20% | 1/5
E17 | Jackson Ck. @ Beall Ln. | 50% | 3/6 | 50% | F | E17 | Jackson Ck. @ Beall Ln. | 0% | 0/6
E18 | Jackson Ck. @ Jacksonville | - | - | - | - | E18 | Jackson Ck. @ Jacksonville | 60% | 3/5
E19 | Jackson Ck. @ W. Ross Ln. | 33.33% | 2/6 | 67% | D | E19 | Jackson Ck. @ W. Ross Ln. | 0% | 0/6
E20 | Bear Ck. @ Pine St. (CP) | 16.67% | 1/6 | 83% | B | E20 | Bear Ck. @ Pine St. (CP) | 33.33% | 2/6
E22 | Griffin Ck. @ I-5 | 16.67% | 1/6 | 83% | B | E22 | Griffin Ck. @ I-5 | 16.67% | 1/6
E23 | Jackson Ck. @ Blackwell Rd. | 66.67% | 4/6 | 33% | F | E23 | Jackson Ck. @ Blackwell Rd. | 16.67% | 1/6
E24 | Bear Ck. @ Kirtland Rd. | 16.67% | 1/6 | 83% | B | E24 | Bear Ck. @ Kirtland Rd. | 0% | 0/6
E25 | Bear Ck. @ Upton Creekside (CP) | 33.33% | 2/6 | 67% | D | E25 | Bear Ck. @ Upton Creekside (CP) | 50% | 2/4

## Stormdrain Data - 2025-2026
2025-2026 - Stormdrain Data | [10 empty] | 2025-2026 - Stormdrain Data
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD17 | 13:55 | 9.4 | 54.7 | 0.68 | 3.495 | 7.3 | 7.21 | 210 |  | Dry Weather | SD9
2026-04-01 | Wet Weather | SD17 | - | - | - | - | - | - | - | - |  | First Flush | SD9
2026-06-01 | Dry Weather | SD17 | - | - | - | - | - | - | - | - |  | Wet Weather | SD9
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD18 | 13:40 | 9.9 | 2419.2 | 0.341 | 4.255 | 30.5 | 7.44 | 131.3 |  | Dry Weather | SD10
2026-04-01 | Wet Weather | SD18 | 13:05 | 10.6 | 980.4 | 0.428 | 5.28 | 5.67 | 7.78 | 291 |  | First Flush | SD10
2026-06-01 | Dry Weather | SD18 | - | - | - | - | - | - | - | - |  | Wet Weather | SD10
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD19 | - | - | - | - | - | - | - | - |  | Dry Weather | SD11
2026-04-01 | Wet Weather | SD19 | - | - | - | - | - | - | - | - |  | First Flush | SD11
2026-06-01 | Dry Weather | SD19 | 13:30 | 20.4 | 75.4 | 0.125 | 3.911 | 3.43 | 6.75 | 114.2 |  | Wet Weather | SD11
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD4 | - | - | - | - | - | - | - | - | 2026-02-01 | First Flush | SD12 | 11:25 | 9.1 | 2419.2 | 0.512 | 4.62 | 179 | 7.68 | 182.9
2026-04-01 | Wet Weather | SD4 | - | - | - | - | - | - | - | - | 2026-04-01 | Wet Weather | SD12 | 11:15 | 9.8 | 133.4 | 0.11 | 1.977 | 38.7 | 8.02 | 292.7
2026-06-01 | Dry Weather | SD4 | 12:50 | 18.8 | 1299.7 | 0.106 | 4.255 | 3.17 | 8.11 | 507 | 2026-06-01 | Dry Weather | SD12 | - | - | - | - | - | - | - | -
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD5 | 12:40 | 9.8 | 95.8 | 0.082 | 3.053 | 22.9 | 7.26 | 95.7 | 2026-02-01 | First Flush | SD13 | 11:10 | 10.9 | 1732.9 | 0.151 | 3.88 | 46 | 7.56 | 112
2026-04-01 | Wet Weather | SD5 | - | - | - | - | - | - | - | - | 2026-04-01 | Wet Weather | SD13 | 11:00 | 11.7 | 275.5 | 0.087 | 7.509 | 2.82 | 7.54 | 298.8
2026-06-01 | Dry Weather | SD5 | - | - | - | - | - | - | - | - | 2026-06-01 | Dry Weather | SD13 | 10:55 | 21.3 | 298.7 | 0.129 | 2.894 | 2.18 | 8.39 | 383.4
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD6 | 12:25 | 10.9 | 217.8 | 0.323 | 3.588 | 33.8 | 7.63 | 300 | 2026-02-01 | First Flush | SD14 | 10:10 | 9.6 | 1986.3 | 0.261 | 4.112 | 67.8 | 7.45 | 65.4
2026-04-01 | Wet Weather | SD6 | 11:55 | 12.9 | 6.3 | 0.291 | 2.29 | 11.2 | 8.03 | 456 | 2026-04-01 | Wet Weather | SD14 | 10:25 | 9.7 | 172.3 | 0.134 | 2.989 | 38.1 | 7.99 | 271.1
2026-06-01 | Dry Weather | SD6 | 12:00 | 18.2 | 160.7 | 0.287 | 3.31 | 14.4 | 8.1 | 435.3 | 2026-06-01 | Dry Weather | SD14 | - | - | - | - | - | - | - | -
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
2026-02-01 | First Flush | SD7 | - | - | - | - | - | - | - | - | 2026-02-01 | First Flush | SD15 | 10:35 | 10.3 | 121.1 | 0.184 | 4.297 | 45.2 | 7.46 | 123.8
2026-04-01 | Wet Weather | SD7 | - | - | - | - | - | - | - | - | 2026-04-01 | Wet Weather | SD15 | 10:40 | 11 | 71.7 | 0.104 | 2.434 | 29.2 | 7.88 | 304.6
2026-06-01 | Dry Weather | SD7 | - | - | - | - | - | - | - | - | 2026-06-01 | Dry Weather | SD15 | 10:30 | 20.9 | 143.9 | 0.166 | 4.898 | 27.2 | 7.92 | 520
Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity | Month/Year | Sample Type | Site # | Time of Day | Temp. (C°) | E. coli MPN | Phosphorus (mg/L) | BOD | Turbidity | pH | Conductivity
| Dry Weather | SD8 | [8 empty] | 2026-02-01 | First Flush | SD16 | 9:55 | 9.8 | 1553.1 | 0.432 | 7.79 | 73 | 7.46 | 105.7
| First Flush | SD8 | [8 empty] | 2026-04-01 | Wet Weather | SD16 | 10:05 | 12.8 | 2419.2 | 0.189 | 4.206 | 4.12 | 8.06 | 365.5
| Wet Weather | SD8 | [8 empty] | 2026-06-01 | Dry Weather | SD16 | - | - | - | - | - | - | - | -