## Education and Outreach
2025-2030 TMDL Implementation Plan
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under City jurisdiction (includes Dissolved Oxygen, pH, Nutrients). | Promote Cultural Awareness through Public Education and Involvement. | Add TMDL or water quality related articles to City newsletters, blogs, and/or other periodicals. | Staff, RVCOG (Stream Smart) | RC will complete a minimum of 4 articles, press releases, and/or blogs. City to contribute additional articles. Topics will be determined through discussions at TMDL meetings, with City and the RM, or at other meetings. | Annually | Annual report summarizing activity. | Year 1: July 2025-June 2026 - Press releases were completed for the Rogue River Clean-up in May and the Whitehorse Weed Pull. Blogs posted on the Stream Smart website included a summary of the Salmon Watch Program, Who to Contact for Concerns Regarding Water Quality, Managing Garlic Mustard in the Rogue Basin (Invasive weeds), and Programs that Stream Smart Program supports.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Maintain City website for water quality including stormwater and TMDL topics. Add link to Stream Smart website to City website. RC will maintain the general TMDL and stormwater websites monthly, the City of Grants Pass Page, and provide links to City websites from the Stream Smart website. The RC will also maintain and update the Stream Smart website in conjunction with the MS4 programs. | Staff, RVCOG (Stream Smart) | Completed updates to the appropriate webpages. Provide tracking statistics as relevant (e.g., Google Analytics for Stream Smart). | Ongoing | Annual Report summarizing changes & relevant links, if changed. | Year 1: July 2025-June 2026 - The City's TMDL website is updated monthly by the RC on an as needed basis. In addition, the page has information (copies) of the annual reports, quarterly reports, and links to Stream Smart and other pages. The Stream Smart pages are actively updated with content, activity photos, events, new programs, and information. In 2026-2027, the Stream Smart webpage is being updated. Work began in 2025-2026 with meetings to revise content, draft pages, and other activities. Additionally, Stream Smart keeps an active social media presence primarily through Facebook and Instagram. The Web and Social Media Summary has details on the website and social media including Google Analytics summarizing visitation, users, content accessed, and other information). Per Analytics, the website had 4,514 visitors and the top ten pages included the Landing Page (#1), Rogue Aquatics Invasives Network/RAIN (#3), Salmon Watch (#4), and the Rogue River Clean-up (#5). For social media Facebook had 24,639 views and Instagram has 674 followers. Grants Pass has the second highest percentage of viewers (18.5%). The document also contains examples of content.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Engage residents in experiential learning opportunities that promote cultural awareness as well as tools for changing behavior. Examples may include: Rain Garden Workshops, downspout disconnects, demonstration workshops, Salmon Watch Program. | Staff, RVCOG (Stream Smart) | Documentation of all relevant statistics - Workshop/Program participation, number of rain gardens installed, downspouts disconnected, number of students participating in Salmon Watch, etc.). | Annually | Annual report summarizing outreach. RC will summarize activity in the annual report and provide links, photos, summaries, and other information on programs. RC will also provide updates at quarterly meetings and quarterly reports that will be posted online and emailed to the City. | Year 1: July 2025-June 2026 - 94 Students from school in Grants Pass participated in the program. In addition, 209 students from schools with regional enrollment also participated. Field sites used included Fish Hatchery Park (County) and Reinhart Volunteer Park (City). Other activities based near or in the City included the Rogue River Clean-up, the Whitehorse Weed Pull, and the Rogue Aquatics Invasives Network (RAIN) trainings and workdays on the water. Details information on Events and Activates, Meetings, Working with Schools outside the Salmon Watch Programs, and the overall activity summary of all activities are included in the Activity Summary Document and in quarterly reports. Quarterly reports are presented at all TMDL meetings and SWAT (Stormwater Advisory Team Meetings).
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Actively participate in the Stream Smart. | Staff, RVCOG (Stream Smart) | Link Stream Smart website to City website and provide link. Review link from Stream Smart to City website to ensure link goes to the correct department. Documentation of participation in Stream Smart activities. | Ongoing | Annual report summarizing outreach. RC will summarize activity in the annual report and provide links, photos, summaries, and other information on programs. RC will also provide updates at quarterly meetings and quarterly reports that will be posted online and emailed to the City. | Year 1: July 2025-June 2026 - City staff serve on the Stream Smart Advisory Committee and attend meetings. Additionally, the City has links to the program, shares materials and posts, and uses the logo and materials in City Programs as appropriate. City staff attended the Stream Smart Meeting in June.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Participate in a basin-wide riparian restoration program and provide outreach to target areas. | Staff, RVCOG (Stream Smart) | Focus is on identifying, prioritizing, and moving toward implementation of projects. Summarize number of projects and development stage in annual report. | Annually | TMDL annual report summarizing outreach and participation in the program. | Year 1: July 2025-June 2026 - The RC continues to work with regional partners and volunteer groups to identify and completed restoration projects. In 2025-2026, the RC worked with Allendale Elementary School on a service learning project at RVP as part of a Salmon Watch Class. Additional work on managing invasive species was done with the CWMA at volunteer events (Clean-up and weed pulls), as part of the Adopt-A-River Activities, and RAIN workdays.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Explore new projects and program innovations to meet the goals of the TMDL. | Staff, RVCOG | Summary of any new approaches will be in response to new technology, innovations or adaptive management. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops in annual report. | Year 1: July 2025-June 2026 New innovations to meet the TMDL. As mentioned in previous years reports, much of the interaction between the public and Stream Smart/Education programs has been through social media so the Regional Programs have focused on expanding blogs, sharing posts, stories, volunteer activities, and boosting posts. The RC has also begun discussions with the Clean Rivers Coalition about ways their programming can tie into the Stream Smart Program. The Follow Your River Campaign for the Rogue is being considered. The RC has also worked with the CWMA and programs including the Rogue Aquatics Invasives Network (RAIN) to expand volunteer opportunity for residents of the City and to increase awareness of what's being done through branded marketing materials (e.g. water bottles, t-shirts) and partnerships including the weed pull and on the water elements of the Rogue River Clean-up, the Whitehorse Park and Pull, and other events.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program and other methods to evaluate and track program effectiveness. | RVCOG, Staff time for additional sampling outside of the monitoring program | Participate in regional monitoring program. | Annually | Report on water quality samples and tracking metrics. | Year 1: July 2025-June 2026 - The City does not operate a monitoring program as part of the TMDL Program. Samples are collected as part of the City's drinking water program
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
TMDL Reporting | Continued participation in TMDL Program. | City to update Councils/Commissions on Stormwater/TMDL related actions. RC will continue to provide periodic updates at RVCOG Board meetings on TMDL related topics and present to the City Council or other groups as requested. | City Staff, RVCOG | City staff will keep the Board of Commissioners updated on Stormwater/TMDL related actions. | Ongoing | Annual report. | Year 1: July 2025-June 2026 - The RC updates the RVCOG board on Department Activities which includes work on Regional Tmall Programs, Stream Smart, and MS4 programs. Representatives from the City and Josephine County serve of the Board. Additionally, as part of the Rogue River Clean-up, the RC present information on the Rogue River Clean-up.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | City will continue attend quarterly TMDL meetings. RC will continue to assist with organizing and hosting TMDL Quarterly meetings and other meetings on TMDL related programs. | City Staff, RVCOG | City will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by City representatives. RC will host (or help arrange locations), attend meetings, and help facilitate meetings. | Year 1: July 2025-June 2026 - The City attended all TMDL meetings. The RC assisted DEQ in coordinating and hosts the TMDL meetings.
Year 2: July 2026-June 2026
Year 3: July 2027-June 2027
Year 4: July 2028-June 2028
Year 5: July 2029-June 2029
|  | Continue to Participate in the TMDL program. | City Staff, RVCOG | Attendance (in person or via videoconference) at quarterly meetings and other meetings as requested. | Ongoing | Attendance summary in annual report. | Year 1: July 2025-June 2026 - City Staff attended the TMDL meeting in July, October, January, and April. Staff also attended the Stream Smart meeting in June 2026 and the regional SWAT meetings.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | City will submit a TMDL annual implementation plan report yearly to DEQ. RC will prepare an annual report summarizing activities completed for the regional program. Reports will be posted on the RVCOG website for the appropriate TMDL program. In addition, the RC is available for meeting with the City. | City Staff, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Report. | Year 1: July 2025-June 2026 - Completed with the submittal of the report and the supplemental information con the Grants Pass TMDL Website on the RVCOG Page (https://rvcog.org/grants-pass-tmdl/).
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030