## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Provide pet waste bags and trash cans for pet owners at local parks and public areas for owners to pick up after their pets. | Staff Time | Track number of stations maintained and bags ordered. Any new stations will be added to existing inventories and maps. | Ongoing (annually) | Summary in annual report. Data submitted to regional manager (RM) will be summarized in the regional report. In addition, data provided in an ESRI or Google Earth Format will be added to the TMDL tracking maps on ArcGIS. | Year 1: July 2025-June 2026 - In 2025-2026, the City purchased 40 cases of bags (2,000 bags per case) for the stations located throughout the City at a cost of $2/239.20. No new stations were added or planned to be added in the near future.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Urban Runoff - the City is not an MS4, but will implement the following as time and funding allow. | Reduce runoff volume. Post Construction | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. | Staff Time, Project Funding (utility fees & grants as applicable) | Track any features installed, detailing the size and treatment expectations as designed. | Ongoing as development occurs. | This strategy is dependent on funding availability for funding designs and construction of capital improvements, as well as private investment in new and redevelopment projects. Report and map features installed and maintained. As requested, RM can pursue funding for project implementation. In addition, RM will map and track as needed including using forms designed in Survey 123 designed for tracking these features. Annual reports will summarize activity and provide links to relevant maps and spreadsheets. | Year 1: July 2025-June 2026 - The Regional Manager (RM) electronic survey form is available to inventory and map features (https://arcg.is/1zbb5e) that was created for regional use and will inventory DMAs as requested. Most annual work is completed under local Phase II programs and included in their annual MS4 reports. Any tracking and/or other information collected by the RM is included in the annual reports and added to these forms. In addition, online maps show up to date tracking (https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=018eec42042b4216b7812956b974593f). No sites were inventoried by the RM in 2025-2026. Jacksonville does not currently have an MS4 program, but will track installation of any low impact development features.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education activities through DMA channels, with partners, and RVCOG through the Stream Smart Program. | Staff time, Project Funding Work with RVCOG (SW Utility Fees, grants as applicable). | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed | Ongoing once the program is established. | Number of projects: number of downspouts disconnected, rain gardens constructed. Information on rain gardens, downspout disconnects, and other measures will be added to and/or updated on the Stream Smart website. In addition, Stream Smart will host workshops as requested and promote events through the Stream Smart website and social media platforms. The program ties directly to the stormwater pledge program which will be promoted at events. Information will also be tie to the stormwater pages on the RVCOG website. RM will report on annual regional activities. | Year 1: July 2025-June 2026 - The City partners with the RM and regional partners on the Stream Smart Program. Stormwater content is included on the Stream Smart website (including the Rain Garden Guide) and social media campaigns. In addition, the RM coordinates with the Regional Stormwater Advisory Team (SWAT), the Statewide Clean Rivers Coalition (CRC), and other partners to expand the reach of the outreach and educational programs. The Stream Smart events page also includes any available trainings. No disconnects, rain gardens, or workshops were hosted during the implementation year.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Implement WQ BMPs identified in the DMAs Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | Year 1: July 2025-June 2026 - No grant funds for implementation of Stormwater BMPS were pursued by the RM during the implementation year. Jackson SWCD does have a stormwater rebate program which could be used to fund smaller scale BMPs and was promoted as an option for the region. The RM will work with the DMAs as requested to evaluate potential funding for BMP implementation and apply for funding. Jacksonville is not a designated MS4, but does conduct stormwater related activities annually (staff, volunteers, or contracts with RVSS) including street sweeping and maintaining the storm drain system (street sweeping, ditch cleaning, creek cleaning, and storm drain cleaning). Details on the activities and cost ($82,951.47) can be found in the City Match Tab.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Lead by Example - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage sediment controls, street sweeping to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. | Year 1: July 2025-June 2026 - The City performs street sweeping monthly and contracts RVSS to perform additional maintenance activities. In 2025 and 2026, the City spent $8,208.00 on Street Sweeping (personnel costs) and $1,203.00 on contracted services to RVSS. See City Match Tab for the breakdown.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain) part of the RVCOG Monitoring program. | Review and refine illicit discharge and hot spot water sampling program as needed. RM will continue the storm drain and hot spot monitoring program that is part of the TMDL monitoring program. | The City will continue to work with RVCOG on the regional program. Additional staff time to follow up on concerns within the City. | As part of the regional monitoring program, RVCOG staff respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program. In addition, we also investigate concerns reported to us by the public, DMAs, partners, and agencies. We also conduct monitoring on storm drains throughout the watershed 3 times during the implementation year. Visual inspections occur as part of the site visit and the RM will document the inspections once per implementation year using Survey 1-2-3. | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis. Document concerns as appropriate using the hot spot monitoring forms. Annual report generated by RVCOG for regional activity. Hot Spot map updated as new reports are submitted. Data summary of all monitoring included in the annual report and links to the survey form for the storm drain inspections. | Year 1: July 2025-June 2026 - As part of the annual TMDL program, the RM serves as a point of contact for water quality concerns and also investigates specific concerns on a limited basis. Investigations include additional sampling, tracking of the source, documentation, and reporting to the appropriate agencies based on the nature of the concern. Additionally, the City responds to reported concerns in City Limits and forwards concerns onto OERS, DEQ, the RM, or others as appropriate. Storm drain survey form link (https://arcg.is/W0juzhttps://arcg.is/W0juz) and survey data ( https://arcg.is/1LTSKW0). Two storm drains are monitored in Jacksonville (4th and Pine at Doc Griffin Park and at the inlet to Jackson Creek near Blackstone Alley). Storm drain data is included in the Storm Drain Tab.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations (MS4s). | Continue to investigate illicit discharges on an annual basis and follow up per City Code. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. | Ongoing | Update on the number investigations and any enforcement actions taken. | Year 1: July 2025-June 2026- In 2025-2026, 5 hot spots were followed up and documented by the RM (see hot spot tab). None of the hot spots were in Jacksonville.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Erosion Prevention and Sediment Control | Continue to require erosion and sediment control at construction sites | Continue ongoing inspection of projects (planning) per City programs. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. | Year 1: July 2025-June 2026 - The City is not a designated MS4. The City works with regional partners (DEQ, RVCOG, RVSS) if there are concerns with erosion and water quality.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Septic Systems | Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time, RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. Any calls received regarding septic concerns will be logged, followed up on as appropriate, and reported to DEQ. In addition, monitoring results (bacteria) will also be reviewed periodically to identify areas of high bacteria levels. | Year 1: July 2025-June 2026 - No septic systems were identified and no calls were received. In reviewing the monitoring data, Jackson Creek in Jacksonville was dry through the summer season and no high readings were recorded. Storm drains had higher readings during the first flush, but the levels were below 406 during the wet and dry weather runs. Bacteria trends can be found in the Bacteria Trends Tab and all monitoring data for streams and storm drains in the region can be found on the City Water Quality Page (https://rvcog.org/jacksonville-water-quality-page/).
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Regional sources - Effectiveness Monitoring | Monitor and maintain awareness of bacteria levels in the Bear Creek watershed by monitoring creek sites and storm drains. | Monitor Creek temperatures. City will work with the RM to continue conducting the water quality monitoring program. | RVCOG, Staff time for any additional sampling outside of the monitoring program | Regional | Ongoing | Annual completion of monthly sampling and analysis for creek sites and storm drains three times during the implementation year within City limits as part of the regional monitoring program. | Year 1: July 2025-June 2026 -Completed. RM conducts storm drain monitoring three times during the implementation year to look at the impact of TMDL parameters during dry conditions, a flushing event, and a large storm event. Two drains are located in Jacksonville. Additionally, the RM conducts monthly sampling on streams throughout the Bear Creek Watershed including Jackson Creek in and around Jacksonville and Griffin Creek outside of City Limits. The Bacteria trend tab has a data summary for the TMDL stations. During the reporting year, there was no flow from Jackson Creek in Jacksonville and not bacteria samples taken. Overall storm drain trends are summarized in the storm drain tab.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. The RM will work with DMAs to explore new topics at TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the TMDL program. | Staff time, RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. The RM (RVCOG) will work with DMAs to bring new topics to TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the bacteria TMDL. | Year 1: July 2025-June 2026 - In 2025 and 2026, the RM, DMAs, and regional partners evaluated the use of eDNA to evaluate underlying causes of bacteria concerns. Information on the technology was presented at TMDL meetings, at hot spot meetings, and was used on Wagner Creek to evaluate the underlying causes of a "hot spot".
Year 2: July 2026-June 2028
Year 3: July 2027-June 2029
Year 4: July 2028-June 2030
Year 5: July 2029-June 2031

## City Match Tab
|  | Activity | Technical Assistance | Education and Outreach | Sample Collection | Street Sweeping | Cleaning Storm Drains, Culverts, Catch Basin | Installing/Replacing Culverts | Ditch Cleaning | Creek Cleaning | Cleaning Silt Traps | Blackberry Brush Removal | Parking Lot Grading | TMDL Reporting | RVSS Labor/ Equipment | Foret Park Volunteers | Cost
| Month | [12 empty] | 1 |  |  | 36
2025 | July |  |  |  |  | 16 | 2 | [6 empty] | 1 |  | 34.25 | 1973.855
| August |  |  |  |  | 20 | 100 |  |  | 52.5 |  |  |  | 1 |  | 63 | 8618.58
| September |  |  |  |  | 16 |  |  |  | 56.5 |  |  |  | 1 |  | 107.75 | 6703.865
| October |  |  |  |  | 40 | 50 |  |  | 22 |  |  |  | 1 | 1203.84 | 96.5 | 8906.03
| November |  |  |  |  | 24 |  |  |  | 16.5 |  |  |  | 1 |  | 128 | 6314.48
| December |  |  |  |  | 24 | 29 | [6 empty] | 1 |  | 178 | 8647.48
2026 | January |  |  |  |  | 20 |  |  |  | 44.5 |  |  |  | 1 |  | 194.25 | 9673.455
| February |  |  |  |  | 16 | 1 | [6 empty] | 1 |  | 175.55 | 7259.213
| March |  |  |  |  | 16 |  |  |  | 16 |  |  |  | 1 |  | 209 | 9058.94
| April |  |  |  |  | 16 | 15 | [6 empty] | 1 |  | 216 | 9286.56
| May |  |  |  |  | 20 | [7 empty] | 1 |  | 150.85 | 6437.011
| June | [12 empty] | 1 |  |  | 36
Totals |  |  | 0 | 0 | 0 | 228 | 197 | 0 | 0 | 208 | 0 | 0 | 0 | 13 | 1203.84 | 1553.15 | 82951.469

## Hot Spots 2025-2026
Summary Information
General Statistics
Date | Event/Activity | Description
2025-07-02 | Hot Spot - Elk Creek Campground | Caller stated that a large group of people swam in Elk Creek and then displayed vomiting and diarrhea. Jackson County Public Health was informed and reached out to the caller. This incident was deemed unrelated to the water quality in Elk Creek and rather norovirus.
2025-08-25 | Hot Spot - Wagner Creek E. coli & eDNA Sampling | Concern from Rogue River Keeper regarding high bacteria levels recorded in Wagner Creek above City limits. Reports led to discussion with RRK, RVSS, DEQ, ODA, and Jackson SWCD. Resolution was to conduct sampling of EDNA and bacteria on the creek and investigate the underlying cause. The TMDL "hot spot" program supported the sample collection and bacteria anaylsis, RVSS paid for the eDNA analysis, and Jackson SWCD provided materials.
2025-08-29 | Hot Spot - Wagner Creek E. coli & eDNA Sampling | Concern from Rogue River Keeper regarding high bacteria levels recorded in Wagner Creek above City limits. Reports led to discussion with RRK, RVSS, DEQ, ODA, and Jackson SWCD. Resolution was to conduct sampling of EDNA and bacteria on the creek and investigate the underlying cause. The TMDL "hot spot" program supported the sample collection and bacteria anaylsis, RVSS paid for the eDNA analysis, and Jackson SWCD provided materials.
2025-09-29 | Hot Spot - Talent - Garbage/Graywater Dumping | RM received a call regarding a garbage and graywater dumping onto the Bear Creek Greenway from the trailer park near the Talent Truck Stop. Amie was out on the TMDL Run and investigated. Photos were taken and this was then reported to DEQ and RVSS. Bill followed up with the complainant.
2025-11-15 | Hot Spot - Skunk Creek (Grants Pass) | While out on the Stream Smart Adopt-A-Street section picking up trash, soap suds were observed in the water of Skunk Creek (11/15/25). On 11/17/25, RVCOG notified City of Grants Pass Public Works. City of GP said they would investigate, although this is a longstanding issue that they haven't been able to track down.
2025-12-03 | eDNA Meeting - Wagner Creek | Post sampling meeting to discuss results and next steps.
2026-03-03 | eDNA Meeting (Wagner Creek) | Post sampling meeting to discuss results and next steps.
2026-03-04 | Hot Spot - White City | Turbid brown/yellowish discharge noted in a sgtorm drain in White City off Pacific Avenue near Carestream as part of the Stormwater Patrol. Contacted RVSS and MWC. RVSS investigated and found it was the result of gold minimg being done in a parking lot. High pressure water was being used to wash river rock. Mining activity ceased after visit from RVSS and no further activity has been noted on monthly stormwater patrols to date.

## Bacteria Trends - Monthly TMDL
Summer Exceedance: May 1 - October 31
Site # | Location | E. coli Exceedance at Standard (406 MPN) | Count | WQ % | WQ Grade
E1 | Walker Ck. @ Belle Fiore | 40% | 2/5 | 60% | D
E3 | Neil Ck. @ Dead Indian Memorial | 50% | 3/6 | 50% | F
E4 | Ashland Ck. @ Granite St. | 0% | 0/2 | 100% | A
E5 | Ashland Ck. below STP | 40% | 2/5 | 60% | D
E6 | TID Canal @ Eagle Mill Rd. | 0% | 0/4 | 100% | A
E7 | Bear Ck. @ S. Valley View Rd. | 16.67% | 1/6 | 83% | B
E8 | Bear Ck. @ Greenway (S. Talent) | 33.33% | 1/3 | 67% | D
E9 | Bear Ck. @ Lynn Newbry Park | 16.67% | 1/6 | 83% | B
E10 | MID Diversion @ Suncrest Rd. | 60% | 3/5 | 40% | F
E11 | Bear Ck. @ B. H. Park (Phoenix) | 66.67% | 4/6 | 33% | F
E12 | Bear Ck. @ Fern Valley Rd. | 50% | 3/6 | 50% | F
E13 | Bear Ck. @ JNC (S. Medford) | 16.67% | 1/6 | 83% | B
E14 | Bear Ck. @ 9th St. (Medford) | 33.33% | 2/6 | 67% | D
E15 | Bear Ck. @ Table Rock Rd. | 50% | 3/6 | 50% | F
E16 | Griffin Ck. @ Beall Ln. | 16.67% | 1/6 | 83% | B
E17 | Jackson Ck. @ Beall Ln. | 50% | 3/6 | 50% | F
E18 | Jackson Ck. @ Jacksonville | - | - | - | -
E19 | Jackson Ck. @ W. Ross Ln. | 33.33% | 2/6 | 67% | D
E20 | Bear Ck. @ Pine St. (CP) | 16.67% | 1/6 | 83% | B
E22 | Griffin Ck. @ I-5 | 16.67% | 1/6 | 83% | B
E23 | Jackson Ck. @ Blackwell Rd. | 66.67% | 4/6 | 33% | F
E24 | Bear Ck. @ Kirtland Rd. | 16.67% | 1/6 | 83% | B
E25 | Bear Ck. @ Upton Creekside (CP) | 33.33% | 2/6 | 67% | D