## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Provide pet waste bags and trash cans for pet owners at local parks and public areas for owners to pick up after their pets. | Staff Time. Regional Coordinator (RC - RVCOG) as requested. | Track number of stations maintained and bags ordered. Any new stations will be added to existing inventories and maps. | Ongoing (annually) | Summary in annual report. | Year 1: July 2025-June 2026 - The City maintains pet stations annually by deploying approximately 145,000 bags this reporting year. All parks and public facilities have bag dispensers. Any new stations will be summarized in the annual report.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Urban Runoff (ties to/supports Phase II programs and/or provides meeting basic goals for DMAs that are not MS4s) | Reduce runoff volume. Post Construction | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. All large capital road improvement projects in the City now implement LID stormwater improvements to be consistent with the Stormwater Management Manual. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track any features installed, detailing the size and treatment expectations as designed. This strategy is tied into the Phase II program. | Ongoing as development occurs. | This strategy is dependent on funding availability for funding designs and construction of capital improvements, as well as private investment in new and redevelopment projects. Report and map features installed and maintained. | Year 1: July 2025-June 2026 - See Phase II Report. The RC (RVCOG) has developed a Survey 123 form that can be used to document and map facilities. As requested, the RC will document features installed.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education activities through City channels, with partners, and RVCOG through the Stream Smart Program. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. Part of Phase II program. | Ongoing once the program is established. | Annual update on program development and relevant statistics in Phase II report (e.g., number of projects: number of downspouts disconnected, rain gardens constructed. This is part of the MS4 Permit relating to Low Impact Development and will be shown in the annual reports there as well. | Year 1: July 2025-June 2026 - See Phase II Report.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Implement WQ BMPs identified in the City Stormwater Master Plan as funds are available. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | Year 1: July 2025-June 2026 - See Phase II Report. The RC (RVCOG) has developed a Survey 123 form that can be used to document and map BMPs. As requested, the RC will document features installed.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Lead by Example - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, proper material storage, sediment controls, street sweeping to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken in NPDES Phase II report. | Year 1: July 2025-June 2026 - Documented in the Phase II Report.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain) part of the RVCOG Monitoring program. | Review and refine illicit discharge program as needed. | Staff Time. RVCOG. | Respond to and investigate the potential sources of illicit discharge as discovered and/or reported. City will meet with the RC as needed to discuss any needs and protocol changes. RC is available as needed to assist the City hot spot (illicit discharge) investigations and documentation. | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis. Document concerns as appropriate using the hot spot monitoring forms. | Year 1: July 2025-June 2026 - See Phase II Report. As part of the TMDL Program, the RC serves as a point of contact for regional water quality concerns including hot spots/illicit discharge. In 2025-2026, the RC documented 5 hot spots including a potential foam/suds concern that was reported to the City and followed up on. See hot spot tab for more information. Additionally, there is a list for general concerns that can be accessed at the following link (https://rvcog.org/wp-content/uploads/2017/01/Hot-Spot-Contact-List-General-Page-Only.pdf). The link is on the City's TMDL page on RVCOGs website for residents use.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations (MS4s). | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Annual update on actions taken in NPDES Phase II report. | Year 1: July 2025-June 2026 - See Phase II Report.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Erosion Prevention and Sediment Control | Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Annual update on actions taken in NPDES Phase II report. | Year 1: July 2025-June 2026 - See Phase II Report.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Septic Systems | Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time, RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. Any calls received regarding septic concerns will be logged, followed up, and reported as part of the annual report | Year 1: July 2025-June 2026 - No calls were received by the RC during the implementation year. The RC documents calls on the tracking sheet and also on the hot spot survey form (Survey 123) as appropriate. The RC notifies the City of any calls received and follows up with DEQ or other agencies as needed.
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. | Staff time, RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Year 1: July 2025-June 2026 - In 2025 and 2026, the RC, DMAs, and regional partners evaluated the use of eDNA to evaluate underlying causes of bacteria concerns. Information on the technology was presented at TMDL meetings, at hot spot meetings, and was used in a hot spot investigation to evaluate the underlying causes of bacteria to help address a long term solution.
Year 2: July 2026-June 2028
Year 3: July 2027-June 2029
Year 4: July 2028-June 2030
Year 5: July 2029-June 2031

## Survey 123 Links
Survey | Link to Survey | Link to Results
Hot Spot Tracking Form | https://arcg.is/0nHOv0 | https://arcg.is/00TWeD
BMP/LID Documentation | https://arcg.is/01jHK0 | https://arcg.is/1nvn5O
General Activity Tracking | https://arcg.is/1eiPrO2 | https://arcg.is/fiijS
Restoration Tracking | https://arcg.is/0GDevD2 | https://arcg.is/19aSvu0